## A1. ED Processs
|  |  |  | Plan the product |  | Feedback -Iteration, recursion, decomposition, improvingthe quality (value) of the product
Development contract-problem assignment
Integrated Product Development Product planning and development process |  |  |  | [Obtain basic information ]- [Clarify Basic Information] | ➡️
| Engineering Design Process-Designing |  |  | Problem assigment to engineering designers | ➡️
|  | I. Elaborating the assigned Problem | P1 | Establish a list of requirement - investigate alternatives | ➡️
|  |  | P1.1 | Establish rough factors for all life phases (technology, operators, inputs, outputs of each life stage)
|  |  | P1.2 | Analyse life phases, establish requirements on the technical process and technical system
|  |  | P1.3 | Analyse environment of the individual life cycle processes especially TS(s)-operational process, the TP(s), and its users
|  |  | P1.4 | Establish importance (priority level) or individual requirements, processes and operators (fixed requirements-wishes)
|  |  | P1.5 | Quantify and create room for tolerance for the requirements where possible
|  |  | P1.6 | Allocate the requirements to life phases, operators, and classes of properties
|  |  | P1.7 | Establish requirements for a supply chain, and environmental concerns
|  |  | P1.8 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] | ⬅️
Design Specification
|  |  | P2 | Establish a plan for the design work-investigate alternatives
|  |  | P2.1 | Analyze and categorize the technical process and technical system from viewpoints which influence design work and planning
|  |  | P2.2 | Select overall strategy, partial strategies and operations for important partial systems
|  |  | P2.3 | Establish degree of difficulty of the design work
|  |  | P2.4 | Establish tasks of operators and individual staff members
|  |  | P2.5 | Plan the anticipated design work, under time pressure
|  |  | P2.6 | Estimate the design costs
|  |  | P2.7 | Establish further goals, for example, masters, forms, catalogs, and so forth
|  |  | P2.8 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] | ⬅️
Design Specificaition and plan
|  | II. Conceptural design-conceptualizing | P3a | Establish the transformation process - investigate alternatives | ➡️
|  |  | P3.1 | Analyze the TS(s)- operational process- TrfP, TP(s)
|  |  | P3.1.1 | Establish input to the operational process- TP(s) operand stade Od
|  |  | P3.1.2 | Establish operators of the operational process - assumed
|  |  | P3.1.3 | Establish technology principle, technology-operations, sequencing.
|  |  | 3.1.4 | Establish necessary effects acting on the operand-technology in individual operations
|  |  | P3b | Establish the TS-function structure | ➡️
|  |  | P3.2 | Work out the complete function structure of the TS(s)
|  |  | P.3.2.1 | Establish distribution of effect between human and technical systems (and environment)
|  |  | P3.2.2 | Establish TS(s)-main functions or individual technical system.
|  |  | P.3.2.3 | Allocate and distribute the main function among individual TS(s)
|  |  | P.3.2.4 | Establishing additonal function from an analysis of th erelationships "human-technical system" and " environment-technical system"
|  |  | P3.2.5 | Establishing the assisting functions from analysis of the transformation functions: auxillary, propelling, regulating and controlling, and so forth.
|  |  | P.3.2.6 | Establish possibly evoked funcitons from important properties
|  |  | P.3.2.7 | Establish TS(s) - inputs, check of TS(s) -output regarding environment
|  |  | P3.3 | Represent TS-function structures.
|  |  | P3.4 | Assess and evaluate the variants of the function structure
|  |  | P3.5 | Function structures -{[improve, optimze],[substantiate, evaluate, select, decide],[verify, check, reflect]} | ⬅️
Optimal function structure
|  |  | P4 | Establish the TS(s)-organ structure-investigate alternatives | ➡️
|  |  | P4.1 | Enter the TS function form function structure into first column of morphological matrix
|  |  | P4.2 | Find action principles, possible modes of action
|  |  | P4.3 | Establish organs or organisms as means (function carriers)
|  |  | P4.4 | Combine individiual organs to a unity (a proposed organ structure)
|  |  | P4.5 | Evaluate organ structure proposals and select the best
|  |  | P4.6 | Establish assiting functions and their organs, and evoked functions for organs where needed
|  |  | P4.7 | Examine evoked secondary outputs and necessity of further organs
|  |  | P4.8 | Establish functions of complex organs, action locations
|  |  | P4.9 | Establish fundamental situations and orders (topology arrangement)
|  |  | P4.10 | Represent final technical system proposals as organ structures with enough detail for evaluation and selection
|  |  | P4.11 | [Organ structures (concepts)] - {[improve, optimize]-[substantiate, evaluate, select, decide]-[verify, check, reflect]} | ⬅️
Optimal Organ Structure
|  | III. Layout out-embodying | P5a | Establish the contructional structure (1) - investigate alternatives | ➡️
|  |  | P5.1 | Establish and analyze the requirements for the contructional structure and constructional parts
Characterize the design situation
Analyze the conceptualized organ structure for potential contructional problems.
Extract from the design specification for each group:
-The external requirements
-The internal requirements for General Design Properties
-The requirement for evoked function
Order, categorize, classify, establish importance and tolerances of requirement- transfer to constructional parts or groups.
List of requirement for constructional structure and parts
|  |  | P5.2 | Establish a conception of the contructional structure
Establish leading sizes (dimensions) of actions locations
Establish mode of contruction, and basic arrangement
Establish construction groups (assembly groups, sub-assemblies)
Establish basic form- refine the arrangement
Concept of constructional structure
|  |  | P5.3 | Establish rough constructional sturcture as preliminary layout
|  |  | P5.3.1 | Define contructional design groups. Select masters
|  |  | P5.3.2 | Establish rough form for each constructional design group
-consider requirement
-concretize the evoked specification
-Consider reuse of existing or purchasable organs, assembly groups, modules or constructional design groups
-For constructional parts to be designed, establish
rough arrangements
Form
Dimension(establish leading sizes)
Material
Kind of manufacturing/production
|  |  | P5.3.3 | Elaborate the rough constructional structure- integrate into the developing total constructional structure (synthesis)
|  |  | P5.3.4 | Represent preliminary layout(s)
Preliminary layout
|  |  | P5.3.5 | Choose optimal variants
|  |  |  | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] | ⬅️
Optimal constructional structure (1) - preliminary
|  |  | P5b | Establish the constructional structure (2) -investigate alternative
|  |  | P5.4 | Establish the difinitive constructional structure | ➡️
|  |  | P5.4.1 | Review the requirements, clear up, compete, perfect, optimize
|  |  | P5.4.2 | Dinitively establish the arrangement for each construction zone and for each constructional part:
Establish local arrangement
Establish form-giving
Establish dimensions (sizes)
Select materials and treatment
Select classes of manufacturing processes
Establish tolerances (dimensional and geometric)
Establish surface qualities
Establish state of assembly
|  |  | P5.4.3 | Represent the definitive dimensional layout
Constructional structure- dimensional layout
|  |  | P.5.4.4 | Select the optimal variants
|  |  |  | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] | ⬅️
Optimal constructional structure (2) - dimensional layout
Release for detailing
|  | IV. Detailing-elaborating | P6 | Establish the constructional structure(3)- investigate alternative | ➡️
|  |  | P6.1 | Prepare detail drawings for each constructional part
complete the form-giving of all constructional parts
Represent all constructional parts
Establish all design properties
|  |  | P6.2 | Prepare a control assembly drawing and part list
|  |  | P6.3 | Consider constructional parts for evoked functions, add details
Constructional parts and structure-assembly (and control)
|  |  | P6.4 | Prepare any additonal documentation: drafts of design report, special instructions for manufacture, instructions for assembly and adjustment, user manuals, and so forth
Manufacturing documents
Additional documentation
|  |  | P6.5 | Control, correct, coordinate, check, audit
|  |  |  | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] | ⬅️
Optimal construction structure (3)- Representation and description of complete technical system
Manufacture, test, develop prototype
Correct for changes, release for manufacture and distribution

## D5.0 Project Traceability & Sou
Prepared by |  | Tool title | D5.0 Project Traceability & Source Links |  | Date filled |  | Quality Target | 4 |  | Related Tool | Doc Control
Role |  | Project Title |  |  | Time Started |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | P1 - P5.4
Checked by |  | Phase Name | Project Brief Handover |  | Time cmpltd |  | Bus. Const | Cost and Risk |  | Next Sheet Ref | P6.1 / D6.5.2 | IMHO GEN
Org/Dept. | Engineering | Activity Name | Source Linking |  | Duration |  | Iteration Num. | 0 |  | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID | D5.0 |  | Date Checked |  |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version | v2.0 (Linked Traceability) |  | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
1.0 EXECUTIVE SUMMARY (TL;DR)
Project Name: | ERider Chassis - Prototype
Brief Statement: | Design, detail, and prototype the structural chassis and sheet metal enclosures for the ERider, strictly following upstream constraints.
2.0 UPSTREAM SOURCE DOCUMENTS (SINGLE SOURCE OF TRUTH)
Phase Ref | Source Document Name |  |  |  |  | Description / What it contains |  |  |  | File Link (URL) |  | Status | Owner
Pr1 - Pr8 | Design Specifications (Consolidated) |  |  |  |  | All priority requirements (Functional,Mfg,Env,Human) |  |  |  | [Paste Google Drive Link Here] |  | Approved | D.E. Braimah
P3.1 | Transformation Process Diagram |  |  |  |  | Black box inputs/outputs and assumed operations |  |  |  | [Paste Google Drive Link Here] |  | Approved | D.E. Braimah
P3.3 | TS-Function Structures |  |  |  |  | Optimal functional structures and evoked properties |  |  |  | [Paste Google Drive Link Here] |  | Approved | D.E. Braimah
P4.2 | Final Organ Structure |  |  |  |  | Selected concepts and topology layout |  |  |  | [Paste Google Drive Link Here] |  | Approved | D.E. Braimah
P5.4.1 | Definitive Constructional Structure,Materials, tolerances, strength analysis, and 3D layout | [8 empty] | [Paste Google Drive Link Here] |  | Approved | D.E. Braimah
3.0 REFERENCE MATERIAL & TEMPLATES
Ref Type | Item Name |  |  | Purpose |  |  |  |  | File Link (URL) |  |  | Status | Owner
CAD Master | electric scooter chassis.1.iam |  |  | Master 3D Assembly File |  |  |  |  | [Paste Google Vault Link] |  |  | Released | David Awe
Template | IMHOGEN_Standard.dwg |  |  | Official drawing template for all D6.5.3 outputs |  |  |  |  | [Paste Google Drive Link Here] |  |  | Active | D.E. Braimah
Guide | Previous_Revision_Drawings.pdf |  |  | Baseline for dimensioning and QMS excellence |  |  |  |  | [Paste Google Drive Link Here] |  |  | Active | D.E. Braimah

## P0.0 Admin & Resource Traceabil
Prepared by |  | Tool title | P0.0 Admin & Resource Traceability | Date filled | Quality Target | 4 |  | Related Tool | Doc Control
Role |  | Project Title |  | Time Started | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1 - D4
Checked by |  | Phase Name | Project Kick-Off & Traceability | Time cmpltd | Bus. Const | Cost and Risk |  | Next Sheet Ref | P1.1 |  | IMHO GEN
Org/Dept. | Engineering | Activity Name | Source Linking | Duration | Iteration Num. | 0 |  | Rev Reason |  |  | IMHOGEN LTD
Signature |  | Docu. ID | P0.0 | Date Checked |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  | Sheet Version | v2.0 (Integrated QMS Launchpad) | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
1.0 PROJECT ONBOARDING TRUTH (D1 Series)
Process Ref | Source Document Name |  | Description / What it contains for Engineering |  |  |  | File Link (URL) |  |  | Status |  | B
D1.8 | Needs Assessment Notes |  | Synthesized engineering constraints and operational environment |  |  |  | [Paste Link Here] |  |  | Approved |  | Lead Engineer
D1.13 | Scope of Work (SOW) |  | Explicit boundaries of included deliverables and excluded scope |  |  |  | [Paste Link Here] |  |  | Approved |  | Project Manager
D1.15 | Project Brief & Draft Budget |  | Executive summary and core objectives of the product |  |  |  | [Paste Link Here] |  |  | Approved |  | Project Manager
2.0 CONTRACT TRACKING & ADMINISTRATION (D2 Series)
Process Ref | Source Document Name |  | Description / What it contains for Engineering |  |  |  | File Link (URL) |  |  | Status |  | Owner
D2.12 | Executed Contract & Audit Trail |  | Legally binding delivery terms and IP ownership rules |  |  |  | [Paste Link Here] |  |  | Active |  | Contract Admin
D2.14 | Phase Initiation Notice |  | Official engineering green-light and target delivery dates |  |  |  | [Paste Link Here] |  |  | Active |  | Contract Admin
3.0 FUND MANAGEMENT & PAYMENT SCHEDULING (D3 Series)
Process Ref | Source Document Name |  | Description / What it contains for Engineering |  |  |  | File Link (URL) |  |  | Status |  | Owner
D3.1 | Payment Terms Extract |  | Milestone deliverables required to trigger client billing |  |  |  | [Paste Link Here] |  |  | Approved |  | Finance
D3.10 | Phase Unblock Notice |  | Confirmation of cleared funds to safely begin/continue engineering work |  |  |  | [Paste Link Here] |  |  | Active |  | Finance
4.0 TEAM ASSIGNMENT & CAPACITY PLANNING (D4 Series)
Process Ref | Source Document Name |  | Description / What it contains for Engineering |  |  |  | File Link (URL) |  |  | Status |  | Owner
D4.3 | Team Assignment & Provisioning Record |  | Locked team roster and allocated days per engineer |  |  |  | [Paste Link Here] |  |  | Active |  | Project Manager
D4.8 | Locked Project Baseline |  | The frozen schedule milestones and baseline labor hours |  |  |  | [Paste Link Here] |  |  | Active |  | Project Manager

## P1.0 Master Requirements Design
Prepared by |  | Tool title |  | P1.0 Master Requirements Matrix | Date filled | Quality Target | 4 | Related Tool | Doc Control
Role |  | Project Title |  |  | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref | P0.0 Launchpad
Checked by |  | Phase Name |  | Task Clarification & Spec | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref | P2.1 Capacity | IMHO GEN
Org/Dept. | Engineering | Activity Name |  | Requirements Consolidation | Duration | Iteration Num. | 0 | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID |  | P1.0 | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version |  | v1.0 (Master Engine) | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
1.0 CONSOLIDATED DESIGN SPECIFICATIONS(This should be filled after the completion of the phase 2)
Req ID | P0.0 Source Ref |  | Requirement Description |  |  | Category (Pr1-Pr8) | Target Life Phase | Priority (D/W) | Target Value / Constraint | Tolerance (Min/Max) | Verification Method
REQ-001 | D1.13 (SOW) |  | Chassis must withstand 150kg static payload |  |  | Pr1C - Operational | Usage / End-User | Demand | 150 kg | +25kg / -0kg | Analysis (FEA)
REQ-002 | D1.8 (Needs) |  | Main frame tubes must be locally sourcable steel |  |  | Pr2 - Manufacturing | Production | Demand | S235JR Steel | Equivalent yield | Inspection
REQ-003 | D1.15 (Budget) |  | Prototype unit cost must not exceed allocated limit |  |  | Pr1B - Functionally Det. | Prototyping | Demand | GHS 43000 | +/- 5% margin | Demonstration
REQ-004 | ONB.1.1 |  | Paint finish should be matte black |  |  | Pr5 - Human System | Usage / End-User | Wish | Matte Black (RAL 9005) | Visual Match | Inspection
REQ-005 | [Type Here] |  | [Type Requirement Here] |  |  | [Dropdown] | [Dropdown] | [Dropdown] | [Type Here] | [Type Here] | [Dropdown]

## P2.0 Master Capacity & Executio
Prepared by |  | Tool title | P2.0 Master Capacity & Execution Plan | Date filled |  |  | Quality Target |  | 4 |  | Related Tool |  | Doc Control
Role |  | Project Title |  | Time Started |  |  | Bus. Target |  | Qlty Delivery |  | Prev. Sheet Ref |  | P1.0 Master Matrix
Checked by |  | Phase Name | Capacity Planning & Strategy | Time cmpltd |  |  | Bus. Const |  | Cost and Risk |  | Next Sheet Ref |  | P3.1 Trans. Process |  | IMHO GEN
Org/Dept. | Engineering | Activity Name | Task Allocation & Scheduling | Duration |  |  | Iteration Num. |  | 0 |  | Rev Reason |  |  |  | IMHOGEN LTD
Signature |  | Docu. ID | P2.0 | Date Checked | [6 empty] | Change Dscrpt. |  |  |  | Copyright IMHO GEN 2026.
|  | Sheet Version | v1.0 (Command Center) | Date Approved | [10 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
1.0 PROJECT CONSTRAINTS (Pulled from P0.0 & D4.8)
Total Eng. Days Allocated: |  | 40 Days | [7 empty] | Project Start Date: |  |  | [DD/MM/YY]
Total Labor Budget: |  | GHS 15000 | [7 empty] | Target Handover: |  |  | [DD/MM/YY]
2.0 MASTER EXECUTION PLAN (Consolidates P2.1 - P2.5 & Pr2.2)
Task ID | EDPM Phase Ref | Activity / Deliverable Description |  |  | Assignee | Complexity |  | Est. Days |  | Start Date |  | Target Date |  | Deliverable Format |  | Status
TSK-001 | P3.1 - P3.3 | Establish Transformation & Function Structures |  |  | D.E. Braimah | High |  | 3 |  | [Date] |  | [Date] |  | Black Box Diagram |  | Not Started
TSK-002 | P4.1 - P4.2 | Morphological Matrix & Concept Synthesis |  |  | David Awe | High |  | 5 |  | [Date] |  | [Date] |  | Topology Layout |  | Not Started
TSK-003 | P5.4.1 | Definitive Constructional Structure (Main Frame) |  |  | David Awe | Medium |  | 7 |  | [Date] |  | [Date] |  | 3D Assembly (.iam) |  | Not Started
TSK-004 | P5.4.1 | Definitive Constructional Structure (Sheet Metal Covers) |  |  | C. Kelvin | Low |  | 4 |  | [Date] |  | [Date] |  | 3D Parts (.ipt) |  | Not Started
TSK-005 | P6.1 | Detail Drafting & Tolerancing (Control Assembly) |  |  | C. Kelvin | Medium |  | 5 |  | [Date] |  | [Date] |  | PDF & DWG |  | Not Started
TSK-006 | [Dropdown] | [Type Activity Here] |  |  | [Dropdown] | [Dropdown] |  | [Number] |  | [Date] |  | [Date] |  | [Type Here] |  | [Dropdown]

## P1.1 Tool Requirement
Prepared by |  |  | Tool title |  | Date filled |  | Quality Target | Related Tool
Role |  |  | Project Title |  | Time Started |  | Bus. Target | Prev. Sheet Ref | P0.0
Checked by |  |  | Phase Name |  | Time cmpltd |  | Bus. Const | Next Sheet Ref | P1.2 | IMHO GEN
Org/Dept. |  |  | Activity Name |  | Duration |  | Iteration Num. | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | P1.1 | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version |  | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.1 |  | Establish rough factors for all life phases (purpose, operand, technology, operators, inputs, outputs of each life stage)
Process Code |  | Process Description |  |  |  | Requirements
P1 | P1.1a | Technology
| P1.1b | Operator
| P1.1c | Inputs
| P1.1d | Outputs
Review Comments

## P1.2 Tool Requirement
Prepared by |  |  | Tool title | Date filled |  | Quality Target | Related Tool | ED Processes
Role |  |  | Project Title | Time Started |  | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd |  | Bus. Const | Next Sheet Ref | P1.2 | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration |  | Iteration Num. | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.2 |  | Analyze life phases, establish requirement on the technical process and technical systemy, operators, inputs, outputs of each life stage)
Process Code |  | Process Description |  |  | Requirements
P1 | P1.2a | Design Phase
| P1.2b | Prototyping and Testing Phase
| P1.2c | Production Phases
| P1.2d | Usage and End-of-Life Phase
Review Comments

## P1.3 Tool Requirement
Prepared by |  |  | Tool title | Date filled |  | Quality Target | Related Tool
Role |  |  | Project Title | Time Started |  | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd |  | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration |  | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.3 |  | Analyze environment of the individual life cycle processes, especially TS(s)-operational process (TP) and its users
Process Code |  | Process Description |  |  | Requirements
P1 | P1.3a | Technical Processes
| P1.3b | Technical Systems
Review Comments

## P1.4 Tool Requirement
Prepared by |  |  | Tool title | Date filled |  | Quality Target | Related Tool
Role |  |  | Project Title | Time Started |  | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd |  | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration |  | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.4 |  | Establish importance(priority level) of individual requirements, processes, and operators (fixed requirements-wishes)
Process Code |  | Process Description |  |  | Requirements
P1 | P1.4a | Input Operand Requirement Priority
| P1.4b | Output Operand Requirement Priority
| P1.4c | Process Requirement Priority
| P1.4a | Operator Requirement Priority
Review Comments

## P1.5 Tool Requirement
Prepared by |  |  | Tool title |  | Date filled | Quality Target | Related Tool
Role |  |  | Project Title |  | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name |  | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name |  | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID |  | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version |  | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.5 |  | Quantify and create room for tolerance for the requirements where possible
Process Code |  | Process Description |  | Requirements
P1 | P1.5a | Requirements with tolerances
Review Comments

## P1.6a Tool Requirement
Prepared by |  |  |  | Tool title |  |  |  | Date filled |  |  |  | Quality Target |  | Related Tool
Role |  |  |  | Project Title |  |  |  | Time Started |  |  |  | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  |  | Phase Name |  |  |  | Time cmpltd |  |  |  | Bus. Const |  | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  |  | Activity Name |  |  |  | Duration |  |  |  | Iteration Num. |  | Rev Reason | IMHOGEN LTD
Signature |  |  |  | Docu. ID |  |  |  | Date Checked | [5 empty] | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version |  |  |  | Date Approved | [6 empty] | All Rights Reserved
P1 |  | Establish a list of requirement - investigate alternatives
P1.6 |  | Allocate the requirement to life phase, operators, and classes of properties
Process Code |  | Life Phases | [6 empty] | Operators |  |  |  | Requirement
P1 | P1.6a | A | B | C | D | E | F | G | H | I | J | K
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
A | Design |  |  |  |  | H | Human Operators |  |  |  | Review Notes
B | Manufacturing |  |  |  |  | I | Technical System
C | Assembly |  |  |  |  | J | Environment
D | Transport |  |  |  |  | K | Information System
E | Use/Operation | [5 empty] | Cont'd
F | Maintenance
G | Disposal /Recycling

## P1.6b Tool Requirement
Prepared by |  |  |  | Tool title |  |  |  | Date filled |  |  |  | Quality Target |  | Related Tool
Role |  |  |  | Project Title |  |  |  | Time Started |  |  |  | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  |  | Phase Name |  |  |  | Time cmpltd |  |  |  | Bus. Const |  | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  |  | Activity Name |  |  |  | Duration |  |  |  | Iteration Num. |  | Rev Reason | IMHOGEN LTD
Signature |  |  |  | Docu. ID |  |  |  | Date Checked | [5 empty] | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version |  |  |  | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.6 |  | Allocate the requirement to life phase, operators, and classes of properties
Process Code |  | Oprts | Class Properties | [9 empty] | Requirement
P1 | P1.6b | L | M | N | O | P | Q | R | S | T | U | V
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
L | Management System |  |  |  |  | S | Ergonomic |  |  |  | Review Notes
M | Functional |  |  |  |  | T | Safety
N | Performance |  |  |  |  | U | Manufacturibility
O | Energy |  |  |  |  | V | Assembly
P | Material | [5 empty] | Cont'd
Q | Geometrical
R | Structural

## P1.6c Tool Requirement
Prepared by |  |  |  | Tool title |  |  |  | Date filled | Quality Target | Related Tool
Role |  |  |  | Project Title |  |  |  | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  |  | Phase Name |  |  |  | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  |  | Activity Name |  |  |  | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  |  | Docu. ID |  |  |  | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version |  |  |  | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.6 |  | Allocate the requirement to life phase, operators, and classes of properties
Process Code | [6 empty] | Requirement
P1 | P1.6b | W | X | Y | Z | AA
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
|  | FALSE | FALSE | FALSE | FALSE | FALSE
W | Maintenance |  |  |  |  | Review Notes
X | Reliability
Y | Economic
Z | Environmental
AA | Control/Information

## P1.7a Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.7 |  | Establish requirements for supply chain, and environmental concerns
Process Code |  | Requirements
P1 | P1.7a : Supply Chain
Review Comments

## P1.7b Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.7 |  | Establish requirements for supply chain, and environmental concerns
Process Code |  | Requirements
P1 | P1.7b : Environmental Concerns
Review Comments

## Pr1 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr1 |  | DESIGN SPECIFICATION
| SN | Priority | PURPOSE
P1
Review Comments

## P1.8 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
P1.8 |  | Review Summaries
Process Code |  | Requirements
P1 | P1.1 | Establish rough factors for all life phases (purpose, operand, technology, operators, inputs, outputs of each life stage)
| P1.2 | Analyze life phases, establish requirement on the technical process and technical system
| P1.3 | Analyze environment of the individual life cycle processes, especially TS(s)-operational process (TP) and its users
| P1.4 | Establish importance(priority level) of individual requirements, processes, and operators (fixed requirements-wishes)
| P1.5 | Quantify and create room for tolerance for the requirements where possible
| P1.6 | Allocate the requirement to life phase, operators, and classes of properties
| P1.7 | Establish requirements for supply chain, and environmental concerns
| P1.8 | Overall Review
Review Comments

## Pr1A Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr1A |  | DESIGN SPECIFICATION
| SN | Priority | Function Properties
P1
Review Comments

## Pr1B Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr1B |  | DESIGN SPECIFICATION
| SN | Priority | Functionally Determined Properties
P1
Review Comments

## Pr1C Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr1C |  | DESIGN SPECIFICATION
| SN | Priority | Operational Properties
P1
Review Comments

## Pr2 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr2 |  | DESIGN SPECIFICATION
| SN | Priority | Manufacturing properties
P1
Review Comments

## Pr3 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr3 |  | DESIGN SPECIFICATION
| SN | Priority | Distribution Properties
P1
Review Comments

## Pr4 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr4 |  | DESIGN SPECIFICATION
| SN | Priority | Liquidation Properties
P1
Review Comments

## Pr5 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr5 |  | DESIGN SPECIFICATION
| SN | Priority | Human System Factors
P1
Review Comments

## Pr6 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr6 |  | DESIGN SPECIFICATION
| SN | Priority | Technical System Factors-for all life cycle phases
P1
Review Comments

## Pr7 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr7 |  | DESIGN SPECIFICATION
| SN | Priority | Environmental Factors-for all life cycle phases
P1
Review Comments

## Pr8 Tool Requirement
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P1 |  | Establish a list of requirement - investigate alternatives
Pr8 |  | DESIGN SPECIFICATION
| SN | Priority | Information System factors-forall life cycle
P1
Review Comments

## P2.1 EDPM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P2 |  | Establish a plan for the design work-investigate alternatives
P2.1 |  | Analyze and categorize the technical process and technical system from viewpoints that influence design work and planning.
| SN | Delivery
P2
Review Comments

## P2.2 EDPM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P2 |  | Establish a plan for the design work-investigate alternatives
P2.2 |  | Select overall strategy, partial strategies and operations for important partial system.
| SN | Delivery
P2
Review Comments

## P2.3 EDPM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P2 |  | Establish a plan for the design work-investigate alternatives
P2.3 |  | Establish degree of difficulty of the design work
| SN | Delivery
P2
Review Comments

## P2.4 EDPM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P2 |  | Establish a plan for the design work-investigate alternatives
P2.4 |  | Establish tasks of operators and individual staff members
| SN | Delivery
P2
Review Comments

## P2.5 EDPM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P2 |  | Establish a plan for the design work-investigate alternatives
P2.5 |  | Plan the anticipated design work, under time pressure
| SN | Delivery
P2
Review Comments

## P2.6 EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
P2 |  | Establish a plan for the design work-investigate alternatives
P2.6 |  | Estimate the design cost
| SN | Delivery
P2
Review Comments

## P2.7 EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P2 |  | Establish a plan for the design work-investigate alternatives
P2.7 |  | Establish further goals, for example, masters, forms, catalogs, and so forth
| SN | Delivery
P2
Review Comments

## P2.8 EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P2 |  | Establish a list of requirement - investigate alternatives
P2.8 |  | Review Summaries
Process Code |  | Requirements
P1 | P2.1 | Analyze and categorize the technical process and technical system from viewpoints that influence design work and planning.
| P2.2 | Select overall strategy, partial strategies and operations for important partial system.
| P2.3 | Establish degree of difficulty of the design work
| P2.4 | Establish tasks of operators and individual staff members
| P2.5 | Plan the anticipated design work, under time pressure
| P2.6 | Estimate the design cost
| P2.7 | Establish further goals, for example, masters, forms, catalogs, and so forth
| P2.8 | Overall Review
Review Comments

## Pr2.1 EPDM Gantt
Prepared by |  | Tool title |  |  | Date filled | [7 empty] | Quality Target | [10 empty] | Quality Target
Role |  | Project Title |  |  | Time Started | [7 empty] | Bus. Target | [10 empty] | Bus. Target
Checked by |  | Phase Name |  |  | Time cmpltd | [7 empty] | Bus. Const | [10 empty] | Bus. Const | [10 empty] | IMHO GEN
Org/Dept. |  | Activity Name |  |  | Duration | [7 empty] | Iteration Num. | [10 empty] | Rev Reason | [10 empty] | IMHOGEN LTD
Signature |  | Docu. ID |  |  | Date Checked | [18 empty] | Change Dscrpt. | [10 empty] | Copyright IMHO GEN 2026.
|  | Sheet Version |  |  | Date Approved | [29 empty] | All Rights Reserved
Link to External Project Planning and Mgt. tool | [6 empty] | PROJECT REQUEST ID: [Enter ID]
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
P3a | Establish the transformation process ->Iteratable: investigate alternatives
P3.1 | Analyze the TS(s)- operational process- TrfP, TP(s) |  | 2018-03-12 | 2018-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
P3.1.1 | Establish input to the operational process- TP(s) operand stade Od |  | 2018-03-15 | 2018-03-16 | 1 | 100% | bar: WEEK 2 W
P3.1.2 | Establish operators of the operational process - assumed |  | 2018-03-15 | 2018-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
P3.1.3 | Establish technology principle, technology-operations, sequencing. |  | 2018-03-16 | 2018-03-22 | 6 | 40% | bar: WEEK 2 R to WEEK 3 R
P3.1.4 | Establish necessary effects acting on the operand-technology in individual operations |  | 2018-03-18 | 2018-03-22 | 4 | 70% | bar: WEEK 3 M to WEEK 3 R
P3b | Establish the TS-function structure
P3.2 | Work out the complete function structure of the TS(s) |  | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
P3.2.1 | Establish distribution of effect between human and technical systems (and environment) |  | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
P3.2.2 | Establish TS(s)-main functions or individual technical system. |  |  |  | 0 | 0%
P3.2.3 | Allocate and distribute the main function among individual TS(s) |  |  |  | 0 | 0%
P3.2.4 | Establishing additonal function from an analysis of th erelationships "human-technical system" and " environment-technical system" |  |  |  | 0 | 0%
P3.2.5 | Establishing the assisting functions from analysis of the transformation functions: auxillary, propelling, regulating and controlling, and so forth. |  |  |  | 0 | 0%
P3.2.6 | Establish possibly evoked funcitons from important properties |  |  |  | 0 | 0%
P3.2.7 | Establish TS(s) - inputs, check of TS(s) -output regarding environment |  |  |  | 0 | 0%
P3.3 | Represent TS-function structures. |  |  |  | 0 | 0%
P3.4 | Assess and evaluate the variants of the function structure |  |  |  | 0 | 0%
P3.5 | Function structures -{[improve, optimze],[substantiate, evaluate, select, decide],[verify, check, reflect]} |  |  |  | 0 | 0%
P4 | Establish the TS(s)-organ structure->Iteratable investigate alternatives
P4.1 | Enter the TS function form function structure into first column of morphological matrix |  |  |  | 0 | 0%
P4.2 | Find action principles, possible modes of action |  |  |  | 0 | 0%
P4.3 | Establish organs or organisms as means (function carriers) |  |  |  | 0 | 0%
P4.4 | Combine individiual organs to a unity (a proposed organ structure) |  |  |  | 0 | 0%
P4.5 | Evaluate organ structure proposals and select the best |  |  |  | 0 | 0%
P4.6 | Establish assiting functions and their organs, and evoked functions for organs where needed |  |  |  | 0 | 0%
P4.7 | Examine evoked secondary outputs and necessity of further organs |  |  |  | 0 | 0%
P4.8 | Establish functions of complex organs, action locations |  |  |  | 0 | 0%
P4.9 | Establish fundamental situations and orders (topology arrangement) |  |  |  | 0 | 0%
P4.10 | Establish fundamental situations and orders (topology arrangement) |  |  |  | 0 | 0%
P4.11 | [Organ structures (concepts)] - {[improve, optimize]-[substantiate, evaluate, select, decide]-[verify, check, reflect]} |  |  |  | 0 | 0%
P5a | Establish the contructional structure (1) -> investigate alternatives
P5.1 | Establish and analyze the requirements for the contructional structure and constructional parts |  |  |  | 0 | 0%
P5.2 | Establish a conception of the contructional structure |  |  |  | 0 | 0%
P5.3.1 | Define contructional design groups. Select masters |  |  |  | 0 | 0%
P5.3.2 | Establish rough form for each constructional design group |  |  |  | 0 | 0%
P5.3 | Elaborate the rough constructional structure- integrate into the developing total constructional structure (synthesis) |  |  |  | 0 | 0%
P5.3.4 | Represent preliminary layout(s) |  |  |  | 0 | 0%
P5.3.5 | Choose optimal variants |  |  |  | 0 | 0%
P3.5.6 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] |  |  |  | 0 | 0%
P5.b | Establish the constructional structure (2) -investigate alternative
P5.4 | Establish the definitive constructional structure |  |  |  | 0 | 0%
P5.4.1 | Review the requirements, clear up, compete, perfect, optimize |  |  |  | 0 | 0%
P5.4.2 | Definitively establish the arrangement for each construction zone and for each constructional part: |  |  |  | 0 | 0%
P5.4.3 | Represent the definitive dimensional layout |  |  |  | 0 | 0%
P.5.4.4 | Select the optimal variants |  |  |  | 0 | 0%
P.5.4.5 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] |  |  |  | 0 | 0%
P6 | Establish the constructional structure(3)- investigate alternative
P6.1 | Prepare detail drawings for each constructional part |  |  |  | 0 | 0%
P6.2 | Prepare a control assembly drawing and part list |  |  |  | 0 | 0%
P6.3 | Consider constructional parts for evoked functions, add details |  |  |  | 0 | 0%
P6.4 | Prepare any additonal documentation: drafts of design report, special instructions for manufacture, instructions for assembly and adjustment, user manuals, and so forth |  |  |  | 0 | 0%
P6.5 | Control, correct, coordinate, check, audit |  |  |  | 0 | 0%
P6.6 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect] |  |  |  | 0 | 0%

## Pr2.2a EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target |  | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
Pr2.2 |  | Phase progress Management Sheet
Pr2.2a |  | P3a Establish the transformation process - investigate alternatives
Process Code |  | Task |  |  | Assignee(s) | Status(B,P,R,C) | Date Complete | Delivery tool | Iteration No | Note files(link)
Pr2 | P3.1 | Analyze the TS(s)- operational process- TrfP, TP(s)
| P3.1.1 | Establish input to the operational process- TP(s) operand stade Od
| P3.1.2 | Establish operators of the operational process - assumed
| P3.1.3 | Establish technology principle, technology-operations, sequencing.
| P3.1.4 | Establish necessary effects acting on the operand-technology in individual operations
Phase Output Documents and Files
|  | Output Document Name |  | Description | File format | Creation Tool | File source | Iteration | Status(R,I,A) | Handler
| P3a.o.1 | Transformation Process Diagram |  | A black box diagram | .dwg,pdf | AutoCAD
| P3.a.o.2 | Technical Process Diagram |  | A more detailed diagram | .dwg, pdf | AutoCAD
| P3.a.o.3 | Evaluation log |  | Phase evaluation document | .pdf, sheet | Google sheet
Review Comments

## Pr2.2b EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target |  | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
Pr2.2 |  | Phase progress Management Sheet
Pr2.2b |  | P3b Establish the TS-function structure
Process Code |  | Task |  |  | Assignee(s) | Status(B,P,R,C) | Date Complete | Delivery tool | Iteration No | Note files(link)
Pr2 | P3.2 | Work out the complete function structure of the TS(s)
| P3.2.1 | Establish distribution of effect between human and technical systems (and environment)
| P3.2.2 | Establish TS(s)-main functions or individual technical system.
| P3.2.3 | Allocate and distribute the main function among individual TS(s)
| P3.2.4 | Establishing additonal function from an analysis of the relationships "human-technical system" and " environment-technical system"
| P3.2.5 | Establishing the assisting functions from analysis of the transformation functions: auxillary, propelling, regulating and controlling, and so forth.
| P3.2.6 | Establish possibly evoked funcitons from important properties
| P3.2.7 | Establish TS(s) - inputs, check of TS(s) -output regarding environment
| P3.3 | Represent TS-function structures.
| P3.4 | Assess and evaluate the variants of the function structure
| P3.5 | Function structures -{[improve, optimze],[substantiate, evaluate, select, decide],[verify, check, reflect]}
Phase Output Documents and Files
|  | Output Document Name |  | Description | File format | Creation Tool | File source | Iteration | Status(R,I,A) | Handler
| P3a.o.1 | Optimal Functional Structures |  | A black box diagram | .dwg,pdf | AutoCAD
| P3.a.o.2 | Evaluation logs |  | Phase evaluation log | .pdf, sheets | Google sheets
Review Comments

## Pr2.2c EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target |  | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
Pr2.2 |  | Phase progress Management Sheet
Pr2.2c |  | P3b Establish the TS-function structure
Process Code |  | Task |  |  | Assignee(s) | Status(B,P,R,C) | Date Complete | Delivery tool | Iteration No | Note files(link)
Pr2 | P4.1 | Enter the TS function form function structure into first column of morphological matrix
| P4.2 | Find action principles, possible modes of action
| P4.3 | Establish organs or organisms as means (function carriers)
| P4.4 | Combine individiual organs to a unity (a proposed organ structure)
| P4.5 | Evaluate organ structure proposals and select the best
| P4.6 | Establish assiting functions and their organs, and evoked functions for organs where needed
| P4.7 | Examine evoked secondary outputs and necessity of further organs
| P4.8 | Establish functions of complex organs, action locations
| P4.9 | Establish fundamental situations and orders (topology arrangement)
| P4.10 | Establish fundamental situations and orders (topology arrangement)
| P4.11 | [Organ structures (concepts)] - {[improve, optimize]-[substantiate, evaluate, select, decide]-[verify, check, reflect]}
Phase Output Documents and Files
|  | Output Document Name |  | Description | File format | Creation Tool | File source | Iteration | Status(R,I,A) | Handler
| P4.c.o.1 | Optimal Organ Structure(Concept) |  | Diagrams of concepts | .dwg,pdf | AutoCAD
| P4.c.o.2 | Evaluation logs |  | Phase evaluation log | .pdf, sheets | Google sheets
Review Comments

## Pr2.2d EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target |  | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
Pr2.2 |  | Phase progress Management Sheet
Pr2.2d |  | P5a Establish the contructional structure (1) -> investigate alternatives
Process Code |  | Task |  |  | Assignee(s) | Status(B,P,R,C) | Date Complete | Delivery tool | Iteration No | Note files(link)
Pr2 | P5.1 | Establish and analyze the requirements for the contructional structure and constructional parts
| P5.2 | Establish a conception of the contructional structure
| P5.3.1 | Define contructional design groups. Select masters
| P5.3.2 | Combine individiual organs to a unity (a proposed organ structure)
| P5.3 | Elaborate the rough constructional structure- integrate into the developing total constructional structure (synthesis)
| P5.3.4 | Represent preliminary layout(s)
| P5.3.5 | Choose optimal variants
| P3.5.6 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect]
Phase Output Documents and Files
|  | Output Document Name |  | Description | File format | Creation Tool | File source | Iteration | Status(R,I,A) | Handler
| P5.b.o.1 | Cnstrt' strtr' and prts sketch and rqrmnts tags |  | Diag. and rqrmnts tags | .dwg,pdf | AutoCAD
| P5.d.o.2 | Conception of constructional strt. sketches |  | Conception drawings and notes | .pdf, sheets | Google sheets
| P5.d.o.3 | Mathematical model of conception |  | Model analysis and calcs. | .pdf, sheets | Google sheets
| P5.d.o.3 | Evaluation logs |  | Phase evaluation log | .pdf, sheets | Google sheets
Review Comments

## Pr2.2e EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target |  | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
Pr2.2 |  | Phase progress Management Sheet
Pr2.2e |  | P5b Establish the contructional structure (1) -> investigate alternatives
Process Code |  | Task |  |  | Assignee(s) | Status(B,P,R,C) | Date Complete | Delivery tool | Iteration No | Note files(link)
Pr2 | P5.4 | Establish the definitive constructional structure
| P5.4.1 | Review the requirements, clear up, compete, perfect, optimize
| P5.4.2 | Definitively establish the arrangement for each construction zone and for each constructional part:
| P5.4.3 | Represent the definitive dimensional layout
| P.5.4.4 | Select the optimal variants
| P.5.4.5 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect]
Phase Output Documents and Files
|  | Output Document Name |  | Description | File format | Creation Tool | File source | Iteration | Status(R,I,A) | Handler
| P5.e.o.1 | 3D models and Assemblies |  | 3D model files | .prt,.iam,.png | Inventor, Keyshot
| P5.e.o.2 | Design Failure Mode Analysis and Effects |  | Simulation results and DFEA Analysis | .pdf, sheets | Google sheets
| P5.e.o.3 | Evaluation and Revision logs |  | Evaluation records and documents | .pdf, sheets | Google sheets
Review Comments

## Pr2.2f EPDM
Prepared by |  |  | Tool title | Date filled | Quality Target |  | Related Tool
Role |  |  | Project Title | Time Started | Bus. Target |  | Prev. Sheet Ref
Checked by |  |  | Phase Name | Time cmpltd | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  |  | Activity Name | Duration | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
Pr2.2 |  | Phase progress Management Sheet
Pr2.2f |  | P6 Establish the constructional structure(3)- investigate alternative
Process Code |  | Task |  |  | Assignee(s) | Status(B,P,R,C) | Date Complete | Delivery tool | Iteration No | Note files(link)
Pr2 | P6.1 | Prepare detail drawings for each constructional part
| P6.2 | Prepare a control assembly drawing and part list
| P6.3 | Consider constructional parts for evoked functions, add details
| P6.4 | Prepare any additonal documentation: drafts of design report, special instructions for manufacture, instructions for assembly and adjustment, user manuals, and so forth
| P6.5 | Control, correct, coordinate, check, audit
| P6.6 | [Improve, optimize]-[Substantiate, evaluate, select, decide]-[verify,check,reflect]
Phase Output Documents and Files
|  | Output Document Name |  | Description | File format | Creation Tool | File source | Iteration | Status(R,I,A) | Handler
| P6.f.o.1 | Engineering Drawing planning and execution |  | Project management for detail drawings | sheets | Google sheets
| P6.f.o.2 | Engineering Drawings files |  | Detail drawing files | .pdf, .dwg | Inventor, AutoCAD
| P6.f.o.3 | Part List, Cut List, Bill of Materials and manufacturing documentations |  | Manufacturing support documents | .pdf, sheets | Google sheets
| P6.f.o.4 | Document control and Revision sheet
Review Comments

## P3.1
Prepared by |  | Tool title |  | Date filled |  | Quality Target |  | Related Tool
Role |  | Project Title |  | Time Started |  | Bus. Target |  | Prev. Sheet Ref
Checked by |  | Phase Name |  | Time cmpltd |  | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  | Activity Name |  | Duration |  | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID |  | Date Checked |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version |  | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P3a | Establish the Transformation Process Diagram
P3.1 | Establish the Transformation Process
Types of operands: 1. Material- M 2. Energy -E 3. Information -I 4. Living Thing -L |  | Human System | Technical System |  | Environment |  | Information System | Management System
Input Operands | [8 empty] | Output Operands
Type | Operand | [7 empty] | Operand |  | Type
Transformation Process
SN | Note Title | Note Description
Review Comments

## P3.1a
Prepared by |  | Tool title |  |  | Date filled |  |  | Quality Target |  | Related Tool
Role |  | Project Title |  |  | Time Started |  |  | Bus. Target |  | Prev. Sheet Ref
Checked by |  | Phase Name |  |  | Time cmpltd |  |  | Bus. Const |  | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name |  |  | Duration |  |  | Iteration Num. |  | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID |  |  | Date Checked |  |  |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version |  |  | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P3a | Establish the Transformation Process Diagram
P3.1.1 | Assumed Operations Process
SID | Process Stage |  | Upstream (SID) | Downsteam (SID) |  | Operator(s) | Operator Action Description |  | Technological Principles |  | Effects On operands
Review Comments

## P3.1b
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P3a | Establish the Transformation Process Diagram
P3.1.1 | Insert or Sketch Technical Process
Technical Process Diagram
Review Comments

## P3.2
Prepared by |  | Tool title |  |  | Date filled |  |  | Quality Target |  |  | Related Tool
Role |  | Project Title |  |  | Time Started |  |  | Bus. Target |  |  | Prev. Sheet Ref
Checked by |  | Phase Name |  |  | Time cmpltd |  |  | Bus. Const |  |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  | Activity Name |  |  | Duration |  |  | Iteration Num. |  |  | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID |  |  | Date Checked | [5 empty] | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version |  |  | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P3b | Establish the TS-function Structure
P3.1 | Establish the Transformation Process
Bold and or Underline the actions words in the Function Name
FID | Function Name |  | Parameters | Units |  | Quantities | Linked SID |  | Operators | Operators Description |  | Evoked Functions |  | Evoked Function Description
Review Comments

## P3.2a
Prepared by |  | Tool title |  |  | Date filled |  |  | Quality Target |  |  | Related Tool
Role |  | Project Title |  |  | Time Started |  |  | Bus. Target |  |  | Prev. Sheet Ref
Checked by |  | Phase Name |  |  | Time cmpltd |  |  | Bus. Const |  |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  | Activity Name |  |  | Duration |  |  | Iteration Num. |  |  | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID |  |  | Date Checked | [5 empty] | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version |  |  | Date Approved | [7 empty] | All Rights Reserved
P3b | Establish the TS-function Structure
P3.2 | Work out the complete function structure of the TS(s)
Bold and or Underline the actions words in the Function Name
FID | Function Name |  | Parameters | Units |  | Quantities | Linked SID |  | Operators | Operators Description |  | Evoked Functions |  | Evoked Function Description
Review Comments

## P3.2b
Prepared by |  | Tool title |  |  | Date filled |  |  | Quality Target |  |  | Related Tool
Role |  | Project Title |  |  | Time Started |  |  | Bus. Target |  |  | Prev. Sheet Ref
Checked by |  | Phase Name |  |  | Time cmpltd |  |  | Bus. Const |  |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  | Activity Name |  |  | Duration |  |  | Iteration Num. |  |  | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID |  |  | Date Checked | [5 empty] | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version |  |  | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P3b | Establish the TS-function Structure
P3.2 | Evoked Functions and Properties
Bold and or Underline the actions words in the Evoked Function name
EFID | Evoked Function Name |  | Parameters | Units |  | Quantities | Linked FID |  | Operators | Operators Description |  | Important Properties
Review Comments

## P3.3
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P3b | Establish the TS-function Structure
P3.3 | Represent TS-function structures
Sketch or insert the function structure
Review Comments

## P4.1
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Morphological Matrix
FID | PRINCIPLES AND ORGANS | [5 empty] | Remarks
Review Comments

## P4.1 Evoked Functions
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Morphological Matrix for Evoked Functions
EFID | PRINCIPLES AND ORGANS | [5 empty] | Remarks
Review Comments

## P4.1 Synthesis
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Selected Function Principles or Organs for Synthesis
FID | SYNTHESIS | [5 empty] | Remarks
Review Comments

## P4.1 Evoked Synthesis
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Selected Function Principles or Organs for Evoked Synthesis
EFID | SYNTHESIS | [5 empty] | Remarks
Review Comments

## P4.2 Topology In principle
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Topology In Principles
TIPID | SYNTHESIS No:
Review Comments

## P4.2 Topology In Iconic
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Topology In Iconic Representation
TOPID
Review Comments

## P4.2 Organ Design in Function R
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Function Ranged Organ Structure
ORGID | Funtion ID Groups
Review Comments

## P4.2 Final Organ Structure
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P4 | Establish the TS(s)-Organ Structure -Investigate alternatives
Final Organ Structure Notes
ORGID
Notes
Review Comments

## P5a.1.i List of Requirements
Prepared by |  | Tool title | Date filled | Quality Target | Related Tool
Role |  | Project Title | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  | Activity Name | Duration | Iteration Num. | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P5.a | Establish the Constructional Structure
P5.1.1 | Establish and analyze the requirements for the contructional structure and constructional parts
RQN | Requirement |  |  |  |  | Related Function group |  | Name
Review Notes

## P5a.1.ii List of Requirements
Prepared by |  | Tool title |  | Date filled |  | Quality Target |  | Related Tool
Role |  | Project Title |  | Time Started |  | Bus. Target |  | Prev. Sheet Ref
Checked by |  | Phase Name |  | Time cmpltd |  | Bus. Const |  | Next Sheet Ref |  | IMHO GEN
Org/Dept. |  | Activity Name |  | Duration |  | Iteration Num. |  | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID |  | Date Checked |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version |  | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P5.a | Establish the Constructional Structure
P5.1.2 | Establish and analyze the requirements for the contructional structure and constructional parts
RQN | Requirement |  | Category |  | Class |  | Tolerances |  | Priority |  | Analysis method
Reveiw Notes

## P5.2 Conception of construction
Prepared by |  | Tool title |  | Date filled | Quality Target | Related Tool
Role |  | Project Title |  | Time Started | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name |  | Time cmpltd | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name |  | Duration | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID |  | Date Checked |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version |  | Date Approved |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P5.2 | Establish rough constructional structure as preliminary layout
| Variants |  | Variant Title |  |  | Mathematical Model
Review Notes

## P5.3 Elaborate the Construction
Prepared by |  |  | Tool title |  | Date filled |  | Quality Target | Related Tool
Role |  |  | Project Title |  | Time Started |  | Bus. Target | Prev. Sheet Ref
Checked by |  |  | Phase Name |  | Time cmpltd |  | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  |  | Activity Name |  | Duration |  | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  |  | Docu. ID |  | Date Checked |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  |  | Sheet Version |  | Date Approved |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P5.3 | Establish rough form for each constructional design group
Constructional Group | [5 empty] | Requirement Reference |  | Mathematical Model Ref
SN | Dimension | Functions |  | Construction group concept
Review Notes

## P5.3.1 Represent Preliminary La
Prepared by |  | Tool title | Date filled |  | Quality Target | Related Tool
Role |  | Project Title | Time Started |  | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd |  | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration |  | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P5.3 | Establish rough form for each constructional design group
Constructional Group(s) |  |  |  | Requirement Reference |  | Mathematical Model Ref
Preliminary Layout with Dimensions and Parts
Review Notes

## P5.4 Establish the Construction
Prepared by |  | Tool title | Date filled |  | Quality Target | Related Tool
Role |  | Project Title | Time Started |  | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd |  | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration |  | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P5.3 | Establish rough form for each constructional design group
Constructional Group(s) |  |  |  | Requirement Reference |  | Mathematical Model Ref
Definitive Constructional Structure (3D Sketches and parts decomposition for CAD Modelling
Review Notes

## P5.4.1 Establish the Construct
Prepared by |  | Tool title | Date filled |  |  | Quality Target | Related Tool
Role |  | Project Title | Time Started |  |  | Bus. Target | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd |  |  | Bus. Const | Next Sheet Ref | IMHO GEN
Org/Dept. |  | Activity Name | Duration |  |  | Iteration Num. | Rev Reason | IMHOGEN LTD
Signature |  | Docu. ID | Date Checked |  |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
P5.3 | Part Definitive Constructional Structure
Material |  |  |  |  | Material Treatment
Strength Analysis Ref. |  |  |  |  | State of Assembly
CAD File Name |  |  |  |  | CAD Project Name
Manufacturing Notes |  |  |  | Part Sketch
Tolerance Notes
SN | Failure Modes
Review Notes

## P6 Master Model Decomposition (
Prepared by |  |  |  | Tool title |  | Master Model Decomposition |  | Date filled |  |  | Quality Target |  | 4 |  | Related Tool |  | Doc Control
Role |  |  |  | Project Reg. ID |  |  |  | Time Started |  |  | Bus. Target |  | Qlty Delivery |  | Prev. Sheet Ref |  | P5.4.1
Checked by |  |  |  | Phase Name |  | Eng. Design - Detailing |  | Time cmpltd |  |  | Bus. Const |  | Cost and Risk |  | Next Sheet Ref |  | D6.5.3 | IMHO GEN
Org/Dept. |  | Engineering |  | Activity Name |  | Hierarchy Mapping |  | Duration |  |  | Iteration Num. |  | 0 |  | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  |  | Docu. ID |  | D6.5.2 |  | Date Checked | [6 empty] | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version |  | v2.1 |  | Date Approved | [9 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
1.0 MASTER DECOMPOSITION & iPROPERTY DATA FEED
Item ID | Hierarchy Level |  | Category Type |  | Level 1 |  | Level 2 |  | Level 3 | Level 4 |  | Level 5 |  | Part Number (iProperty) |  | iProperty Description |  | Material Spec | Notes
1 | Level 1 |  | Sub-Assembly |  | Frames and Extras | [8 empty] | IMHO-FRM-001 |  | Main Chassis Weldment |  | Welded Assembly | [Enter Notes]
2 | Level 2 |  | Part |  | Frames and Extras |  | FR023:1 | [6 empty] | IMHO-PRT-023 |  | Lower Support Bracket |  | S235JR Steel (4mm) | [Enter Notes]
3 | Level 2 |  | Part |  | Frames and Extras |  | ISO 657-1 - L25x25x3:1 | [6 empty] | IMHO-STK-001 |  | Angle Iron 25x25x3 |  | S235JR Steel | [Enter Notes]
4 | Level 1 |  | Sub-Assembly |  | Wheels | [8 empty] | IMHO-WHL-000 |  | Wheel Sub-Assembly |  | Assembly | [Enter Notes]
5 | Level 2 |  | Sub-Assembly |  | Wheels |  | WH003:1 | [6 empty] | IMHO-WHL-003 |  | Front Wheel Hub Assy |  | Assembly | [Enter Notes]
6 | Level 3 |  | Sub-Assembly |  | Wheels |  | WH003:1 |  | Wheel assembly:1 |  |  |  |  | IMHO-WHL-003-A |  | Wheel Rim & Hub |  | Assembly | [Enter Notes]
7 | Level 4 |  | Part |  | Wheels |  | WH003:1 |  | Wheel assembly:1 | Disc 152F-406 |  |  |  | IMHO-PRT-152 |  | Brake Disc 152mm |  | AISI 304 Stainless | [Enter Notes]
8 | Level 4 |  | Part |  | Wheels |  | WH003:1 |  | Wheel assembly:1 | Tyre 324A 9.00-16 |  |  |  | COTS-TYR-324 |  | Pneumatic Tyre 9.00-16 |  | Rubber | [Enter Notes]