## Document Control
Prepared by |  | Tool title | Date filled | Quality Target | 4 | Related Tool
Role |  | Project Reg. ID | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref
Checked by |  | Phase Name | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref | IMHO GEN
Org/Dept. | R&D and ED | Activity Name | Duration | Iteration Num. | 0 | Rev Reason | IMHOGEN LTD
Signature | D.E.B | Docu. ID | Date Checked |  |  | Change Dscrpt. | Copyright IMHO GEN 2026.
|  | Sheet Version | Date Approved |  |  |  | All Rights Reserved
Project Request ID
DOCUMENT CONTROL
Find link to source files
DocID | Document Title |  |  | Link |  | Description
D1.1 | Client Email / Web Form |  |  | ➡️ |  | The form filled by a new client on the company's website
D.1.2 | Initial Inquiry Notification |  |  | ➡️ |  | The notification received and a pdf file through emails
D1.3 | Received Request Record |  |  | ➡️ |  | Recorded details of the project details
D.1.4 | Acknowledgment Email |  |  | ➡️ |  | Send standard acknowledgment email to the client stating.
D.1.5 | Meeting Time Proposal |  |  | ➡️ |  | Pre-analysis records and proposed meeting times
D1.6 | Calendar Invite & Agenda |  |  | ➡️ |  | Link to calender invite and meeting agenda
D.1.7 | Raw Meeting Notes |  |  | ➡️ |  | Standard template for meeting notes
D.1.8 | Needs Assessment Notes |  |  | ➡️ |  | Needs assessments records
T3.D1.8a | 3D Modeling Execution (Reverse Engineering) |  |  | ➡️ |  | his is the "Field Sheet." It ensures that before a machine leaves your sight (or you leave the client's site), all physical dimensions and metadata are captured accurately.
D1.9 | Internal Review Request |  |  | ➡️ |  | Internal memo for requesting a review of the assessment made
D.1.10 | Capability Assessment |  |  | ➡️ |  | Reports on capability Assessment
D.1.11 | Risk Assessment |  |  | ➡️ |  | Reports on Risk Assessment
D1.12 | Feasibility Report |  |  | ➡️ |  | Written Feasibility Report
D.1.13 | Draft Scope of Work |  |  | ➡️ |  | Written project brief document
D.1.14 | Cost Estimation Sheet |  |  | ➡️ |  | Cost analysis and breakdown records
D1.15 | Project Brief & Draft Budget |  |  | ➡️ |  | Records of hand
D.1.16 | Handoff Meeting Minutes |  |  | ➡️ |  | Records of handing over meeting with contract admin team
D1 | Updated System Status |  |  | ➡️ |  | The central meeting records
T3.D1.3a | Technical Intake (If CAD Request Form is selected, use T3-Series bypass sheets) |  |  | ➡️ |  | This sheet acts as a "3D/Drafting specific" extension of the standard D1.3 Received Request Record.
T3.D2.2a | Drafting Contract Mapping |  |  | ➡️
Confidential Notice |  |  |  | Client Name/Organization
Description of Primary activities of Organizaiton

## D1.1 Web Forms
Prepared by |  |  | Tool title | Web Forms |  | Date filled |  | Quality Target | 4 | Related Tool
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target | Qlty Delivery | Prev. Sheet Ref | Doc Control
Checked by |  |  | Phase Name |  |  | Time cmpltd |  | Bus. Const | Cost and Risk | Next Sheet Ref | D1.2 | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name | Web Form |  | Duration |  | Iteration Num. | 0 | Rev Reason |  | IMHOGEN LTD
Signature |  | D.E.B | Docu. ID | D1.1 |  | Date Checked |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version |  |  | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID
D1.1 Web Form Reference
1.0 CLIENT SUBMISSION REFERENCE
SN | FORM TYPE |  |  |  | DATE SUBMITTED |  | CLIENT/ORG NAME |  | DIRECT LINK |  | STATUS | NOTES
1 | Product Development Form
2 | CAD Request Form |  |  |  | 2026-04-05 |  | Syntropy Engineering Solutions |  |  |  | Received | Acknwoledgement email is being sent to client.
3 | Process Development Form
4 | Engineering Support/Consultancy
5 | Others
2.0 SUPPLEMENTARY UPLOADS (If applicable)
SN | DOCUMENT TYPE |  |  |  | DATE UPLOADED |  | PROVIDED BY |  | DIRECT LINK TO FILE |  | STATUS | NOTES
Confidential Notice | [7 empty] | Client Name/Organization
Description of Primary activities of Organizaiton

## D1.2 Initial Inquiry No
Prepared by |  | C.Fiannaa | Tool title | Initial Inquiry Notification | Date filled | 2026-04-05 | Quality Target | 4 | Related Tool
Role |  | Ops. Lead | Project Reg. ID |  | Time Started | 14:00 | Bus. Target | Qlty Delivery | Prev. Sheet Ref |  | D1.1
Checked by |  |  | Phase Name | Onboarding | Time cmpltd | 14:35 | Bus. Const | Cost and Risk | Next Sheet Ref |  | D1.3 | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name | Inquiry Receipt | Duration |  | Iteration Num. | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.2 | Date Checked |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: CAD-1775340276795
D1.2 INTITAL INQUIRY NOTIFICATION
1.0 NOTIFICATION METADATA
Notification Source (e.g. Web/Direct): |  |  |  | Web (CAD Request Submission Form) |  |  |  |  | Date Received |  | 2026-04-05
Sender Email Address: |  |  |  | dir@syntropyengineeringsolutionss.com |  |  |  |  | Time Received |  | 14:34
Recipient (IMHOGEN) Address: |  |  |  | IMHO GEN Official CAD Intake Channel (imhogen22@gmail.com) |  |  |  |  | Subject Line |  | CAD Request from Syntropy Engineering Solutions
DIGITAL RECORDS REFERENCE
SN | DOCUMENT TYPE |  |  |  | FILE NAME/DESCRIPTION |  |  |  | DIRECT LINK TO FILE |  |  | STATUS
1 | Patent Reference |  |  |  | Patent sample drawing.jpeg |  |  |  | Pantent sample drawing.jpeg |  |  | Received
2 | Prototype image |  |  |  | Prototype image 1.jpeg |  |  |  | prototype image 1.jpeg |  |  | Received
3 | Prototype image |  |  |  | Prototype image 2.jpeg |  |  |  | Prototype Image 2.jpeg |  |  | Received
4 | Prototype image |  |  |  | Prototype image 3.jpeg |  |  |  | Prototype image 3.jpeg |  |  | Received
5 | Prototype image |  |  |  | Prototype image 4.jpeg |  |  |  | prototype image 4.jpeg |  |  | Received
6 | Submission Record |  |  |  | CAD Request Form Data |  |  |  | Gmail - Fwd: New CAD Request from Syntropy Engineering Solutions |  |  | Logged
3.0 PRELIMINARY TRIAGE (Spam / Relevance Filter - PID 1.1.2)
SN | Checklist Item |  |  |  | Status (Pass/Fail) |  | Reviewer Notes
1 | Is the notification readable and free of malicious links? |  |  |  | PASS |  | Structured submission via official form. No suspicious links detected.
2 | Does the request broadly align with IMHOGEN's services? |  |  |  | PASS |  | Strong alignment with CAD modeling, engineering documentation, and product development.
3 | Is the contact information apparently valid and legible? |  |  |  | PASS |  | Email contains spelling irregularities (“egineerinsolutionss”), but phone number and organization context appear valid. Requires verification. But correct email is obtained.
TRIAGE DECISION: |  |  |  |  | [PROCEED TO D1.3 (Technical Intake) / REJECT AS SPAM]
Confidential Notice | [6 empty] | Client Name/Organization |  |  | Syntropy Engineering Solutions
Email anomaly detected: Recommend contact verification before contract stage Client located in Suame Magazine: strategic cluster relevance Request involves IP/patent documentation: Signaling High-value + Sensitive Work Attachments provided: Sufficient for initial intake progression | [6 empty] | Description of Primary activities of Organizaiton |  |  | General engineering fabrication, machining services, and product innovation focused on prototype development within the Suame Magazine industrial cluster.

## D1.3 Received Request Record
Prepared by |  |  |  | Tool title | Received Request Record | Date filled | Quality Target | 4 |  | Related Tool | Doc Control
Role |  |  |  | Project Reg. ID |  | Time Started | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.2
Checked by |  |  |  | Phase Name | Onboarding | Time cmpltd | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.4 | IMHO GEN
Org/Dept. |  | R&D and BI |  | Activity Name | Received Request Record | Duration | Iteration Num. | 0 |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  |  | Docu. ID | D1.3 | Date Checked |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version | v1.0 | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: CAD-1775340276795
D1.3 RECEIVED REQUEST RECORD (Universal Translation)
1.0 CLIENT & PROJECT METADATA
Request Source Form: |  |  |  |  | https://utfs.io/f/dhn4pYX1fjPsgIdTpoiN7TkPLH5ItxNhDSQYb8uafUiO2CoW |  |  |  |  | Client Name: | Frederick Opoku
Project/Product Name: |  |  |  |  | CAD-1775340276795 |  |  |  |  | Company Name: | Syntropy Engineering Solutions
Target Budget (if stated): |  |  |  |  | None |  |  |  |  | Contact Info:
Target Timeline: |  |  |  |  | 5 worrking days |  |  |  |  | Physical Address: | Suame Magazine
2.0 CORE OBJECTIVES & SCOPE (Client's Stated Vision)
| Primary Purpose / Business Goal: |  |  |  |  | To develop accurate engineering documentation of an existing prototype for Intellectual Property (IP) / Patent Registration, ensuring compliance with patent office illustration standards.
| Main Deliverables Requested: |  |  |  |  | 3D CAD Model of the prototype Patent-compliant technical drawings (line illustrations) Technical drawing package (dimensions & views) Rendered images for visualization Multi-format outputs (SVG, AI, EPS, PDF, STEP)
| Specific Constraints Noted: |  |  |  |  | All outputs must strictly match the prototype (no design changes) Visual style must replicate patent office sample drawing provided No additional features or redesign required Limited source data (images only, no dimensions provided) No periodic drafts requested (internal risk consideration)
3.0 SYSTEMS ENGINEERING TRANSLATION (Fill N/A if not applicable to request type)
SN | INPUT OPERANDS | [5 empty] | OUTPUT OPERANDS
M | Existing physical prototype (mechanical assembly) Prototype images (multiple views) | [5 empty] | Digitized 3D CAD model Structured geometric representation of the product
E | N/A
I | Patent sample drawing (format reference) Client instructions and constraints Visual interpretation from images | [5 empty] | Engineering drawings (ISO + patent format) Dimensional data and annotations Documentation for IP submission
L | N/A
3.3 OPERATORS (The System Environment)
Human System: |  |  | [Who interacts with it?] |  |  |  | Information System: |  | [Software/Data integration?]
Technical System: |  |  | [Required machinery/tools?] |  |  |  | Management System: |  | [Maintenance/Lifespan goals?]
Active Environment: |  |  | [Indoor/Outdoor/Constraints?]
SN | Technical Notes | [8 empty] | Assignee |  | Status
This is a Reverse Engineering + IP Documentation Project
Requires measurement validation before modeling finalization
No draft policy from client → internally override with validation checkpoint
High strategic value due to Suame Magazine ecosystem alignment

## T3.D1.3a Technical Intake
Prepared by |  | C.Fiannaa | Tool title |  | T3 Technical Intake (Drafting) | Date filled |  | 2026-04-05 | Quality Target | 4 |  | Related Tool | T3.D2.2
Role |  | Ops. Lead | Project Reg. ID |  | CAD-1775340276795 | Time Started |  |  | Bus. Target | Input Accuracy |  | Prev. Sheet Ref | D1.1
Org/Dept. |  | R&D and ED | Activity Name |  | Technical Intake | Duration |  |  | Iteration Num. | 0 |  | Rev Reason | IMHOGEN LTD | IMHO GEN
Signature |  |  | Docu. ID |  | T3.D1.3a | Date Checked | [5 empty] | Change Dscrpt. | Tier 3 Fast-Track | IMHOGEN LTD
Copyright IMHO GEN 2026.
All Rights Reserved
PROJECT REQUEST ID: CAD-1775340276795
T3.D1.3a Technical Intake
1.0 SOURCE ASSET EVALUATION (The Input)
SN | Asset Type |  |  | Format/Description |  |  |  | Condition |  |  | Action Required |  |  | Notes
1.1 | Existing 3D Model |  |  | Not Provided |  |  |  | N/A |  |  | Model from Scratch |  |  | No baseline CAD data available. Full reconstruction required.
1.2 | Physical Part |  |  | Prototype Provided (images only) |  |  |  | Working Prototype |  |  | Site Visit for Measurement |  |  | Critical to obtain accurate dimensions. Image-based estimation alone is insufficient for patent-level documentation.
1.3 | 2D Legacy PDF |  |  | Patent Office Sample Drawing (Image Format) |  |  |  | Reference Standard Only |  |  | Interpret & Replicate Format |  |  | Must strictly follow patent illustration conventions (line weights, views, no shading).
1.4 | Reference Images |  |  | Multiple Prototype Images (JPEG) |  |  |  | Moderate Clarity |  |  | Reverse Engineering |  |  | Images will guide geometry but not dimensions. Risk of distortion.
1.5 | Technical Specs |  |  | General instruction from client |  |  |  | Limited Detail |  |  | Define Assumptions + Validate |  |  | Missing explicit dimensions and tolerances. Requires clarification or controlled assumptions.
2.0 DRAFTING SPECIFICATIONS (The Output)
SN | Requirement |  |  | Standard (ISO/ASME) |  |  |  | Tolerance Class |  |  | File Format |  |  | Notes
2.1 | Manufacturing Dwgs |  |  | ISO 128 |  |  |  | Medium (m) |  |  | PDF & DXF |  |  | Ensure clarity for fabrication if required in future.
2.2 | Assembly Dwgs |  |  | ISO 128 |  |  |  | N/A |  |  | PDF |  |  | Exploded views may be required depending on complexity.
2.3 | 3D Model Output |  |  | N/A |  |  |  | N/A |  |  | STEP / PDF/PNG |  |  | Parametric model required for future edits and reuse.
2.4 | Paternt Drawings |  |  | Patent Office Standard (Black & White Line Art) + Colored Pictorial Representation on Realistic Background. |  |  |  | High Precision (Visual Accuracy) |  |  | SVG, AI, EPS, PDF |  |  | Must strictly match patent formatting style (no shading, consistent line hierarchy).
2.5 | Rendered Images |  |  | Internal Visualization Standard |  |  |  | N/A |  |  | PNG/JPEG |  |  | For presentation purposes only (not for patent submission).
3.0 QUALITY GATE: DATA SUFFICIENCY
Does the provided source data allow for the requested tolerances? (Yes/No): | [6 empty] | NO | No explicit dimensions or physical measurements provided. Image-based reconstruction alone cannot guarantee manufacturing or patent-level accuracy.
Is a site visit required for manual measurements? (Yes/No): | [6 empty] | YES | To: Capture precise dimensions Validate geometry Ensure patent compliance accuracy Reduce legal/IP risk

## D1.4 Acknowledgement Email
Prepared by |  |  | Tool title | Acknowledgement Email | Date filled | Quality Target | 4 | Related Tool | Doc Control
Role |  |  | Project Reg. ID |  | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref | D1.3
Checked by |  |  | Phase Name | Onboarding | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref | D1.5 | IMHO GEN
Org/Dept. | R&D and BI |  | Activity Name | Acknowledgement Email | Duration | Iteration Num. | 0 | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.4 | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.4 ACKNOWLEDGMENT EMAIL RECORD
1.0 DISPATCH METADATA
Sent To (Client Email): | [7 empty] | Date Sent:
CC / BCC: | [7 empty] | Time Sent:
Subject Line:
Sent By (IMHOGEN Rep):
2.0 STANDARD EMAIL TEMPLATE (Copy & Paste)
Dear Frederick,
Thank you for reaching out to IMHOGEN LTD. We have successfully received your project inquiry regarding Plastic Extruding Innovation for Patent Application and associated reference sample and Prototype images, submitted on Saturday, 4th April, 2026.
Your request has been assigned the tracking reference : CAD-1775340276795
Our Engineering and R&D team is currently reviewing the initial details you provided. A Project Onboarding Manager will contact you within the next 24-48 hours to propose a time for a brief Technical Discovery Meeting. This meeting will help us better understand your specific constraints to ensure we deliver tailored engineering solution.
If you have any supplementary documents information on scope, please share them.
We look forward to collaborating with you.
(P.S: Request Filled On your behalf by Technical Support Team, find the filled form attached)
Best regards,
3.0 CRM / DIGITAL RECORD REFERENCE
Link to sent Email |  | [Who interacts with it?]
Delivery Status |  | Delivered
Active Environment: |  | [Indoor/Outdoor/Constraints?]
Note /Replies

## D1.5 Meeting Time Proposal
Prepared by |  | Tool title |  | Meeting Time Proposal | Date filled |  | Quality Target | 4 |  | Related Tool | Doc Control
Role |  | Project Reg. ID |  |  | Time Started |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.4
Checked by |  | Phase Name |  | Onboarding | Time cmpltd |  | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.6 | IMHO GEN
Org/Dept. | R&D and BI | Activity Name |  | Meeting Time Proposal | Duration |  | Iteration Num. | 0 |  | Rev Reason |  | IMHOGEN LTD
Signature |  | Docu. ID |  | D1.5 | Date Checked |  |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  | Sheet Version |  | v1.0 | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.5 MEETING TIME PROPOSAL
1.0 PRE-MEETING CONTEXT (Internal Tracker)
SLOT No. |  |  | Date (DD/MM/YYY) |  |  | TIme(Zone) |  |  | Status (Pending/Accepted/Declined) |  |  | Client Moments
3.0 STANDARD SCHEDULING EMAIL SCRIPT
Dear [Client Name],
Following our initial review of your request for [Project Name]
This 30-45 minute session will allow our engineering team to understand your operational constraints and exact technical needs.
Please let us know which of the following times works best for you:
- Option 1: [Insert Option 1 Date & Time]
- Option 2: [Insert Option 2 Date & Time]
- Option 3: [Insert Option 3 Date & Time]
If none of these suit your schedule
We look forward to speaking with you.
Best regards,
4.0 FINAL MEETING CONFIRMATION
Agreed Date: | [6 empty] | Agreed Time:
Meeting Platform/Location: | [6 empty] | Direct Meeting Link:
Calendar Invite Sent?: | [6 empty] | Client Confirmed?:
Note

## D1.6 Calendar Invite & Agenda
Prepared by |  |  |  | Tool title |  | Calendar Invite & Agenda | Date filled |  | Quality Target | 4 |  | Related Tool | Doc Control
Role |  |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.5
Checked by |  |  |  | Phase Name |  | Onboarding | Time cmpltd |  | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.7 |  | IMHO GEN
Org/Dept. |  | R&D and BI |  | Activity Name |  | Calendar Invite & Agenda | Duration |  | Iteration Num. | 0 |  | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  |  | Docu. ID |  | D1.6 | Date Checked |  |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version |  | v1.0 | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.6 CALENDAR INVITE & AGENDA
1.0 FINALIZED MEETING DETAILS
Meeting Date: |  |  |  |  | Date (DD/MM/YYY) |  |  | Meeting Time (Zone)
Platform/Location | [7 empty] | Meeting ID/PINI:
IMHOGEN Attendees | [7 empty] | Client Attendees:
2.0 CALENDAR INTEGRATION
SN | Time Allotted |  | Agenda Topic |  |  |  |  | Lead Speaker |  |  | Meeting Objective / Focus
1 | 05 Mins |  | Introductions & Project Overview |  |  |  |  | Project Manager |  |  | Establish rapport and align on the high-level project vision.
2 | 15 Mins |  | Technical Requirements (Inputs/Outputs) |  |  |  |  | Lead Engineer |  |  | Extract specific missing data identified in D1.3 (Section 4).
3 | 10 Mins |  | Operational Environment & Constraints |  |  |  |  | Lead Engineer |  |  | Define the physical environment and human operator limits.
4 | 05 Mins |  | Commercial Expectations (Timeline/Budget) |  |  |  |  | Project Manager |  |  | Ensure IMHOGEN and the client are aligned on business realities.
5 | 05 Mins |  | Next Steps & Q&A |  |  |  |  | Project Manager |  |  | Outline the Feasibility Report and Project Briefing stages.
4.0 PRE-MEETING CHECKLIST
Task | [9 empty] | Assignee |  |  |  | Status
Has the Lead Engineer reviewed D1.3 (Received Request Record)? | [9 empty] | Lead Engineer
Is the meeting recording software/consent prepared? | [9 empty] | Project Manager
Have previous reference documents (D1.1) been opened for screen sharing? | [9 empty] | Project Manager
NOTES

## D1.7 Raw Meeting Notes
Prepared by |  |  |  | Tool title |  | Raw Meeting Notes | Date filled |  | Quality Target | 4 |  | Related Tool | Doc Control
Role |  |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.6
Checked by |  |  |  | Phase Name |  | Onboarding | Time cmpltd |  | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.8 |  | IMHO GEN
Org/Dept. |  | R&D and BI |  | Activity Name |  | Raw Meeting Notes | Duration |  | Iteration Num. | 0 |  | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  |  | Docu. ID |  | D1.7 | Date Checked |  |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version |  | v1.0 | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.7 RAW MEETING NOTES (Live Capture)
1.0 MEETING EXECUTION METADATA
Actual Date: |  |  |  |  | Date (DD/MM/YYY) |  |  | Actual Start Time:
Recording Link (If applicable): | [7 empty] | Actual End Time:
Attendees Present (IMHOGEN): | [7 empty] | Attendees Present (Client):
2.0 LIVE DISCUSSION CAPTURE (Aligns with D1.6 Agenda)
SN | Time Allotted |  | Agenda Topic |  |  |  |  | Raw Notes / Direct Client Statements |  |  | IMHOGEN Clarifications / Immediate Remarks
1 | 05 Mins |  | Introductions & Project Overview
2 | 15 Mins |  | Technical Requirements (Inputs/Outputs)
3 | 10 Mins |  | Operational Environment & Constraints
4 | 05 Mins |  | Commercial Expectations (Timeline/Budget)
5 | 05 Mins |  | Next Steps & Q&A
3.0 PARKING LOT (Unresolved Questions or Out-of-Scope Requests)
SN | Item Description | [12 empty] | Action Required / Who to resolve?
4.0 MEETING CLOSE-OUT
Primary Outcome: |  |  | [e.g. Needs Assessment Complete / Follow-up Call Required]
Client Next Step: |  |  | [e.g. Send existing site photos and layout dimensions]
IMHOGEN Next Step: |  |  | [e.g. Synthesize into D1.8 and begin Feasibility Report]

## D1.8 Needs Assessment Notes
Prepared by |  |  | Tool title | Needs Assessment Note |  | Date filled | Quality Target | 4 |  | Related Tool | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.8
Checked by |  |  | Phase Name | Onboarding |  | Time cmpltd | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.9 |  | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name | Needs Assessment Note |  | Duration | Iteration Num. | 0 |  | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.8 |  | Date Checked |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.8 NEEDS ASSESSMENT NOTES (Engineering Synthesis)
1.0 SYNTHESIS METADATA
Synthesized By (Lead Engineer):
Date of Synthesis:
Reference Raw Notes ID
Client/Project Name:
2.0 LIVE DISCUSSION CAPTURE (Aligns with D1.6 Agenda)
SN | Category |  |  |  | Confirmed Constraints / Specifications |  |  |  | Engineering Remarks (Risks/Clarifications)
1 | INPUT: Material
2 | INPUT: Energy
3 | INPUT: Information
4 | INPUT: Livingthing
5 | OUTPUT: Material
6 | OUTPUT: Energy
7 | OUTPUT: Information
8 | OUTPUT: Livingthing
9 | OPERATOR: Human System
10 | OPERATOR: Tech System
11 | OPERATOR: Active Env.
12 | OPERATOR: Mgt System
13 | OPERATOR: Information System
3.0 PRELIMINARY DESIGN SPECIFICATIONS (Draft Pr-Set)
SN | Requirement Category |  |  |  | Specific Requirement / Tolerance |  |  |  |  | Priority (Fixed/Wish) |  | Specific Requirement / Tolerance
3.1 | Function Properties
3.2 | Operational Properties
3.3 | Manufacturing Properties
3.4 | Environmental Properties
3.5 | Distribution Properties
3.6
3.7
3.8
3.9
4.0 SYNTHESIS APPROVAL & ROUTING
Synthesis Complete? (Yes/No): | [9 empty] | Date
Lead Engineer Signature:
Ready for Internal Review (D1.9)?

## T3.D1.8a Physical Metrology & M
Prepared by |  |  | Tool title |  | T3 Physical Metrology Log |  | Date filled |  | Quality Target |  | 5 | Related Tool |  | T3.D6.5.0a
Role |  |  | Project Reg. ID |  |  |  | Time Started |  | Bus. Target |  | Data Integrity | Prev. Sheet Ref |  | T3.D1.3a
Org/Dept. |  | Engineering | Activity Name |  | Physical Measurement |  | Duration |  | Iteration Num. |  | 0 | Rev Reason |  |  | IMHO GEN
Signature |  |  | Docu. ID |  | T3.D1.8a |  | Date Checked |  |  |  |  | Change Dscrpt. |  | Tier 3 Field Tool | IMHOGEN LTD
Copyright IMHO GEN 2026.
All Rights Reserved
1.0 MEASUREMENT EQUIPMENT VERIFICATION
Tool Used |  | Serial # / ID |  |  |  | Calibration Status |  |  | Accuracy Range |  |  |  |  | Notes
|  | [e.g. Digital Caliper] |  |  |  | [ID-101] |  |  | [Valid] |  |  |  |  | [+/- 0.02mm]
|  | [e.g. Laser Scanner] |  |  |  | [ID-202] |  |  | [Valid] |  |  |  |  | [+/- 0.10mm]
2.0 CRITICAL DIMENSION CAPTURE
SN | Feature Name |  |  | Measurement Method |  |  |  | Measured Value (mm) |  | Ref. Photo ID |  |  | Confidence (H/M/L) |  | Notes
2.1 | Main Shaft Dia. |  |  | [Caliper] |  |  |  | [Value] |  | [IMG_001] |  |  | [High] |  | [Measured at 3 points]
2.2 | Mounting Pattern |  |  | [Steel Rule] |  |  |  | [Value] |  | [IMG_002] |  |  | [Med] |  | [Center-to-center]
2.3 | Overall Envelope |  |  | [Laser Tape] |  |  |  | [Value] |  | [IMG_003] |  |  | [High] |  | [Max protrusion points]
3.0 PHOTOGRAPHIC EVIDENCE CHECKLIST
SN | View Required |  |  | Captured? (Y/N) |  |  |  | File Link / Folder |  |  | Quality Note
3.1 | Isometric / 3/4 View |  |  | [ ] |  |  |  | [Link] |  |  | [Must show overall machine context]
3.2 | Nameplate / Specs |  |  | [ ] |  |  |  | [Link] |  |  | [Serial numbers and motor ratings]
3.3 | Complex Interfaces |  |  | [ ] |  |  |  | [Link] |  |  | [Close-ups of gears/splines/connectors]
4.0 FIELD SIGN-OFF
I confirm that all critical dimensions have been captured and the physical machine can be released.
Lead Measurer Signature | [8 empty] | Date |  |  | [DD/MM/YYYY]

## D1.9 Internal Review Request
Prepared by |  |  | Tool title | Internal Review Request |  | Date filled | Quality Target | 4 |  | Related Tool | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.8
Checked by |  |  | Phase Name | Onboarding |  | Time cmpltd | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.10 | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name | Internal Review Request |  | Duration | Iteration Num. | 0 |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.9 |  | Date Checked |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.9 INTERNAL REVIEW REQUEST (Internal Memo)
1.0 REVIEW INITIATION METADATA
Requested By (Lead/PM): | [9 empty] | Project/Client Name:
Date of Synthesis: | [9 empty] | Required Completion Date:
Primary Review Objective: | [9 empty] | Priority Level:
Project/Client Name:
2.0 CONTEXT & REFERENCE MATERIAL (Required Reading)
SN | Document Name |  |  |  | Direct Link to Document |  |  |  | Status
1 | D1.3 Received Request Record
2 | D1.8 Needs Assessment Notes
3 | Client Supplementary Uploads (D1.1)
3.0 SPECIFIC REVIEW DIRECTIVES & ASSIGNMENTS
SN | Review Category |  |  |  | Assigned Reviewer |  | Specific Focus / Question for Reviewer | [5 empty] | Status
1 | Technical Feasibility |  |  |  | Engineering Risk Officer |  | Evaluate the physical constraints outlined in D1.8.
2 | Resource Availability |  |  |  | Head of Operations |  | Check workshop/personnel capacity for requested timeline.
3 | Commercial & Scope Alignment |  |  |  | Project Manager |  | Verify client budget expectations align with stated deliverables.
4 | Specialist Review (If required) |  |  |  | [Name] |  | [Type specific technical or supply chain question here]
5
6
4.0 REVIEW COMPLETION TRACKING
Are all reviews submitted? (Yes/No): | [9 empty] | Date
Lead Engineer Signature:
Ready for Capability Assessment (D1.10)?:

## D1.10 Capability Assessment She
Prepared by |  |  | Tool title | Capability Assessment Sheet | Date filled |  | Quality Target | 4 |  | Related Tool | Doc Control
Role |  |  | Project Reg. ID |  | Time Started |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.9
Checked by |  |  | Phase Name | Onboarding | Time cmpltd |  | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.10 | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name | Capability Assessment | Duration |  | Iteration Num. | 0 |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.10 | Date Checked |  |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.10 CAPABILITY ASSESSMENT SHEET
1.0 REVIEW INITIATION METADATA
Assessor (Head of Ops/Lead Eng): | [9 empty] | Project/Client Name:
Date of Assessment:
Primary Review Objective:
Reference Request ID:
2.0 TECHNICAL CAPABILITY (Engineering & Manufacturing)
SN | Evaluation Criteria |  |  |  |  | Status (Yes/No/Partial) |  |  | Justification / Identified Gaps
2.1 | Does IMHOGEN possess the core engineering expertise for this design?
2.2 | Can the physical product be fabricated using our standard workshop tools?
2.3 | Are the required raw materials reliably accessible in our local supply chain?
2.4 | Do we have the software/computing capability to run necessary simulations?
2.1
2.2
2.3
2.4
4.0 COMMERCIAL ALIGNMENT
SN | Evaluation Criteria |  |  |  |  | Status (Yes/No/Partial) |  |  | Justification / Identified Gaps
2.1 | Does the client's estimated budget align with the scale of work?
2.2 | Is this project aligned with IMHOGEN's long-term strategic goals?
2.3
2.4
2.1
2.2
2.3
2.4
5.0 CAPABILITY CONCLUSION
Overall Capability Status: | [8 empty] | Date:
Primary Bottleneck (If any):
Assessor Signature:

## D1.11 RiskAssessment Sheet
Prepared by |  |  | Tool title |  | Risk Assessment Sheet | Date filled |  | Quality Target | 4 |  | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref |  | D1.10
Checked by |  |  | Phase Name |  | Onboarding | Time cmpltd |  | Bus. Const | Cost and Risk |  | Next Sheet Ref |  | D1.12 | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name |  | Risk Assessment Sheet | Duration |  | Iteration Num. | 0 |  | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID |  | D1.11 | Date Checked |  |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version |  | v1.0 | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.11 RISK ASSESSMENT SHEET
1.0 ASSESSMENT METADATA
Assessor (Head of Ops/Lead Eng): | [10 empty] | Project/Client Name:
Date of Assessment: | [10 empty] | Overall Capability Status:
Primary Review Objective:
Reference Request ID:
2.0 TECHNICAL CAPABILITY (Engineering & Manufacturing)
SN | Risk Category |  |  | Specific Risk Description |  |  | Probability (H/M/L) |  | Impact (H/M/L) |  |  | Proposed Mitigation Strategy |  |  | Risk Owner
2.1 | Technical Risk |  |  | [e.g. Thermal distortion during welding fails ±1mm tolerance]
2.2 | Technical Risk |  |  | [Type here]
2.2 | Technical Risk |  |  | [Type here]
2.3 | Commercial Risk |  |  | [e.g. Client expands scope without budget increase]
2.4 | Commercial Risk |  |  | [Type here]
2.5 | Supply Chain Risk |  |  | [e.g. Specific sensors unavailable in local Kumasi market]
2.6 | Operational Risk |  |  | [e.g. Workshop capacity full during target fabrication week]
3.0 RISK CONCLUSION & GO/NO-GO DECISION
SN | Evaluation Question | [5 empty] | Status (Yes/No/Partial) |  |  | Remarks / Conditions
31 | Are there any "High Probability / High Impact" risks that cannot be mitigated?
3.2 | Does the mitigation of these risks push the project over the client's budget?
3.3 | Is IMHOGEN willing to accept the residual risk of this project?
3.4
3.4
2.2
2.3
2.4
5.0 CAPABILITY CONCLUSION
OVERALL RISK PROFILE: | [9 empty] | Date:
PROJECT GO/NO-GO DECISION:
Assessor Signature:

## D1.12 Feasibility Report
Prepared by |  |  | Tool title | Feasibility Report | Date filled | Quality Target | 4 | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref |  | D1.11
Checked by |  |  | Phase Name | Onboarding | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref |  | D1.13 | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name | Feasibility Report | Duration | Iteration Num. | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.12 | Date Checked |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.10 CAPABILITY ASSESSMENT SHEET
1.0 REVIEW INITIATION METADATA
Assessor (Head of Ops/Lead Eng): | [7 empty] | Project/Client Name:
Date of Assessment: | [7 empty] | Overall Capability Status:
Primary Review Objective:
Reference Request ID:
2.0 TECHNICAL CAPABILITY (Engineering & Manufacturing)
SN | Capability Domain | [5 empty] | Status[Capable/Partial] |  | Key Findings / Gaps to Bridge
2.1 | Engineering & Design
2.2 | Manufacturing & Tools
2.2 | Supply Chain & Materials
2.3 | Resource Bandwidth
3.0 CRITICAL RISKS & REQUIRED MITIGATIONS (Sourced from D1.11)
SN | Primary Risk Identified | [5 empty] | Impact Level |  | Mandatory Mitigation Strategy (Must be in Contract)
3.1
3.2
4.0 COMMERCIAL FEASIBILITY (Timeline & Budget Alignment)
Client's Target Timeline: | [6 empty] | IMHOGEN Realistic Timeline:
Client's Estimated Budget: | [6 empty] | IMHOGEN Estimated Cost Floor:
Commercial Alignment Notes:
5.0 FINAL RECOMMENDATION & ROUTING
Recommendation:
Head of R&D Signature:
Date:

## D1.13 Draft Scope of Work
Prepared by |  |  | Tool title | Draft Scope of Work |  | Date filled | Quality Target | 4 | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref |  | D1.12
Checked by |  |  | Phase Name | Onboarding |  | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref |  | D1.14 | IMHO GEN
Org/Dept. |  | R&D and BI | Activity Name | Draft Scope of Work |  | Duration | Iteration Num. | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.13 |  | Date Checked |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.13 DRAFT SCOPE OF WORK (SOW)
1.0 SOW METADATA & OVERVIEW
Drafted By (Lead Engineer/PM): | [8 empty] | Project/Client Name:
Date of Assessment:
Date of Draft:
Reference Request ID:
Project Vision / Primary Goal:
2.0 INCLUDED SCOPE (Specific Deliverables)
SN | Deliverable Category |  |  |  | Detailed Description of Deliverable |  |  | Format / Quantity |  | Delivery Phase
2.1 | Engineering Design |  |  |  | [e.g. 3D CAD modeling of the welding jig structure] |  |  | [e.g. .STEP / Native CAD] |  | [Phase 1]
2.2 | Manufacturing Documentation |  |  |  | [e.g. 2D fabrication drawings with GD&T limits] |  |  | [e.g. PDF (A3)] |  | [Phase 1]
2.3 | Physical Fabrication |  |  |  | [e.g. Fabrication and assembly of one (1) physical jig unit] |  |  | [e.g. Physical Unit] |  | [Phase 2]
2.4 | Technical Documentation |  |  |  | [e.g. Operator Manual and Maintenance Guide] |  |  | [e.g. PDF (A4)] |  | [Phase 3]
2.5 | Training & Handover |  |  |  | [e.g. Half-day on-site operator training at client facility] |  |  | [e.g. In-person] |  | [Phase 3]
3.0 EXCLUDED SCOPE (Out of Scope / "Not Included")
SN | Exclusion Category |  |  |  |  | Description of Excluded Work (To prevent scope creep) |  |  |  | Reasoning (Optional)
3.1
3.2
4.0 PHASED TIMELINE & MILESTONES
Phase | Phase Name |  |  |  |  | Key Activities / Milestones |  |  |  | Estimated Duration |  | Target Completion
5.0 CLIENT RESPONSIBILITIES & DEPENDENCIES
SN | Requirement |  |  |  |  | Description |  |  |  | Due Date |  | Status
6.0 SOW ROUTING
Scope Locked?: | [9 empty] | Date
PM / Lead Engineer Signature:
Ready for Cost Estimation (D1.14)?:

## D1.14 Cost Estimation
Prepared by |  |  | Tool title | Cost Estimation | Date filled | Quality Target | 4 | Related Tool | Finance tool
Role |  |  | Project Reg. ID |  | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref | D1.13
Checked by |  |  | Phase Name | Onboarding | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref | D1.15 | IMHO GEN
Org/Dept. |  | R&D and ED | Activity Name | Cost Estimation | Duration | Iteration Num. | 0 | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D1.14 | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.14 COST ESTIMATION SHEET (Executive Summary)
1.0 BASE TECHNICAL LABOR COST (From Pricing Calculator)
SN | Engineering Module (e.g. Mechanical/Electronics) |  |  |  |  | Estimated Days |  | Daily Rate (GHS) |  | Total Labor Cost (GHS)
1.1 | [Type here] |  |  |  |  | [Type here] |  | [e.g. 937.50] |  | [Type here]
1.2 | [Type here] |  |  |  |  | [Type here] |  | [e.g. 937.50] |  | [Type here]
1.3 | [Type here]
1.4
1.5
BASE LABOR SUBTOTAL
2.0 DIRECT PROJECT COSTS (Prototypes & Materials)
SN | Item Description |  |  |  |  | Quantity |  | Unit Cost (GHS) |  | Total Cost (GHS)
2.1 | [e.g. 3D Printing Housing] |  |  |  |  | [Type here] |  | [Type here] |  | [Type here]
2.2 | [e.g. Electronics Fabrication / PCB] |  |  |  |  | [Type here] |  | [Type here] |  | [Type here]
DIRECT COST SUBTOTAL:
3.0 INSTITUTIONAL MARKUP LAYERS (Protecting the Business)
SN | Cost Layer Category |  |  |  |  | Applied Rate (%) |  | Calculated Value (GHS) |  | Notes / Justification
3.1 | Project Management & QC |  |  |  |  | [e.g. 15%] |  | [Type here] |  | [Applied to Base Labor]
3.2 | Administrative Overhead |  |  |  |  | [e.g. 7%] |  | [Type here] |  | [Fixed Institutional Cost]
3.3 | Sustainability / Risk Margin |  |  |  |  | [e.g. 15%] |  | [Type here] |  | [Varies by Project Risk (D1.11)]
TOTAL PROJECT VALUE:
4.0 FINAL ALLOCATED BUDGET (Client-Facing Numbers)
SN | Deliverable Category (Must match SOW D1.13) |  |  |  |  | Fully Loaded Alloc. Cost (GHS) |  | Allocation Check
4.1 | [e.g. Product Architecture & System Design] |  |  |  |  | [e.g. 24,238] |  | [Labor + Prop. PM + Overhead + Margin]
4.2 | [e.g. Mechanical & Industrial Design] |  |  |  |  | [e.g. 37,356]
4.3 | [e.g. Prototype Fabrication & Testing] |  |  |  |  | [e.g. 43,656]
5.0 FINANCIAL ROUTING & APPROVAL
Is the minimum overhead recovery met? | [6 empty] | Ready for Project Briefing (D1.15)?:
Lead Engineer Signature: | [6 empty] | Head of R&D / Finance Sig:

## D1.15 Project Brief & Draft Bud
Prepared by | C.Fiannaa |  | Tool title |  | Project Brief & Draft Budget | Date filled |  | 2026-04-05 | Quality Target |  |  | Related Tool | Doc Control
Role | Ops. Lead |  | Project Reg. ID |  |  | Time Started |  |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D1.14
Checked by |  |  | Phase Name |  | Onboarding | Time cmpltd |  |  | Bus. Const | Cost and Risk |  | Next Sheet Ref | D1.16 |  | IMHO GEN
Org/Dept. | R&D and ED |  | Activity Name |  | Project Brief & Draft Budget | Duration |  |  | Iteration Num. | 0 |  | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID |  | D1.3 | Date Checked | [5 empty] | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version |  | v1.0 | Date Approved | [8 empty] | All Rights Reserved
PROJECT REQUEST ID: CAD-1775340276795
D1.15 PROJECT BRIEF & DRAFT BUDGET
1.0 PROJECT & CLIENT OVERVIEW
Client / Organization Name: |  |  |  | Syntropy Engineering Solutions | [7 empty] | Project Title: |  |  | Prototype Digitization & Patent Documentation Package
Primary Contact Person: |  |  |  | Frederick Opoku | [7 empty] | Estimated Project Duration: |  |  | 5 Working Days
Contact Email / Phone: |  |  |  | 0267384812 | [7 empty] | Target Start Date: |  |  | To be confirmed upon client approval
Reference Request ID: |  |  |  | CAD-1775340276795
2.0 EXECUTIVE SUMMARY & CORE OBJECTIVES
Project Vision: |  |  |  | To transform an existing physical prototype into a precise digital engineering asset, supported by patent-compliant technical documentation, enabling successful Intellectual Property (IP) registration and future product development.
Primary Objectives |  |  |  | Digitize the prototype into an accurate 3D CAD model
Develop detailed engineering drawings aligned with ISO standards
Produce patent-compliant technical illustrations based on provided reference
Deliver multi-format outputs suitable for documentation, submission, and presentation
Ensure dimensional accuracy through on-site measurement and validation
3.0 PHASED DELIVERABLES & TIMELINE (Abstracted from D1.13 SOW)
Phase No. |  | Phase Name |  |  |  |  | Key Deliverables Included |  |  |  | Estimated Duration |  |  |  | Target Completion
1 |  | Measurement & Validation |  |  |  |  | On-site prototype measurement and proportionality/dimensional data capture |  |  |  | 1 Day |  |  |  | Day 1
2 |  | 3D Modeling (Parts + Assembly) |  |  |  |  | Parametric 3D CAD model of prototype |  |  |  | 2 Days |  |  |  | Day 3
3 |  | Technical Drafting |  |  |  |  | 2D engineering drawings (ISO 128 compliant) |  |  |  | 1 Day |  |  |  | Day 4
4 |  | Patent Drawing Set |  |  |  |  | Patent-style line drawings (vector formats) |  |  |  | 1 Day |  |  |  | Day 5
5 |  | Rendering and Packaging |  |  |  |  | Rendered visuals and final file compilation |  |  |  | 1 Day |  |  |  | Day 5
4.0 PROJECT BUDGET SUMMARY (Value-Based Pricing - Sourced from D1.14 Sec 4.0)
SN |  | Project Deliverable / Component | [8 empty] | Allocated Value (GHS) |  |  |  | Payment Schedule
1 |  | Reverse Engineering & 3D Modeling | [8 empty] | 3312 |  |  |  | 50% at Project initiation
2 |  | Technical Drawing Package (ISO Standard) | [8 empty] | 662.4
3 |  | Patent Drawing Development (Compliance Formatting) | [8 empty] | 993.6 |  |  |  | 25% at patent compliance formatting
4 |  | Measurement, proportionation & Validation | [8 empty] | 331.2
5 |  | Rendering & Documentation Packaging | [8 empty] | 1324.8 |  |  |  | 25% Final delivery
TOTAL ESTIMATED INVESTMENT (GHS): | [14 empty] | 6624
5.0 KEY EXCLUSIONS & CLIENT RESPONSIBILITIES
Out of Scope (Not Included): |  |  | Structural analysis or FEA Material selection or engineering optimization Patent filing services (only documentation support provided) Fabrication or manufacturing execution Product redesign or feature modification
Client Dependencies: |  |  | Access to physical prototype for measurement Clarification of any hidden/internal features if required Timely communication and approval during execution Confirmation of patent drawing standard if required
6.0 APPROVAL & NEXT STEPS
Notice: |  |  |  |  | This is a Draft Budget for discussion purposes. A formal binding contract will be issued upon agreement of these terms.
Head of R&D Signature: | [10 empty] | Signature/Date: |  |  | Monday, 4th April 2026

## T3.D1.15a Drafting SOW
Prepared by |  | C.Fiannaa | Tool title | T3 Drafting SOW & Quote | Date filled |  | Quality Target |  | 4 |  | Related Tool | T3.D2.2a
Role |  | Ops. Lead | Project Reg. ID | CAD-1775340276795 | Time Started |  | Bus. Target |  | Conversion |  | Prev. Sheet Ref | T3.D1.3a
Org/Dept. |  | R&D and ED | Activity Name | Drafting Quoting | Duration |  | Iteration Num. |  | 0 |  | Rev Reason |  | IMHO GEN
Signature |  |  | Docu. ID | T3.D1.15a | Date Checked | [5 empty] | Change Dscrpt. | Tier 3 Fast-Track | IMHOGEN LTD
Copyright IMHO GEN 2026.
All Rights Reserved
PROJECT REQUEST ID: CAD-1775340276795
1.0 SCOPE OF DELIVERABLES
SN | Service Item |  |  | Technical Description |  |  | Qty |  |  | Delivery Timeline |  |  |  | Format
1.1 | 3D Modeling |  |  | Reverse engineering and parametric reconstruction of prototype into a precise 3D CAD model |  |  | 1 |  |  | 3–4 Working Days |  |  |  | STEP/Parasolid
1.2 | Drafting Package |  |  | Full 2D technical drawings (dimensions, orthographic views, sections) aligned with ISO 128 |  |  | 1 |  |  | 2–3 Working Days |  |  |  | PDF/DWG
1.3 | Patent Drawing Set |  |  | Patent-compliant technical illustrations (black line format, no shading, standardized views) |  |  | 1 |  |  | 2–3 Working Days |  |  |  | SVG / AI / EPS / PDF
1.4 | Rendered Images |  |  | High-quality visual renders for presentation and documentation support |  |  | 3 Views |  |  | 1–2 Working Days |  |  |  | PNG / JPEG
1.5 | Measurement & Validation |  |  | On-site measurement and dimensional validation of prototype at client location (Suame) |  |  | 1 Visit |  |  | 1 Day |  |  |  | Field Data + Notes
2.0 PRICING SUMMARY (GHS)
SN | Description |  |  |  | Rate (Ghs/hr) | Qty |  | Subtotal |  |  |  | Finance Notes
2.1 | Engineering Man-Hours (Drafting & Modeling) |  |  |  | 150 | 32 |  | 4800 |  |  |  | Covers 3D modeling, drawings, patent formatting
2.2 | Reverse Engineering (Measurement & Validation Support) |  |  |  | 5% | 1 |  | 240 |  |  |  | Includes short site visit + dimensional capture
2.3 | Patent Drawing Preparation Premium |  |  |  | 25% | 1 |  | 1200 |  |  |  | High-accuracy + compliance formatting
2.4 | Markup / Admin Fee |  |  |  | 8% | 1 |  | 384 |  |  |  | Coordination, QA, file packaging
TOTAL T3 PROJECT VALUE | [7 empty] | 6624
3.0 MANDATORY EXCLUSIONS
SN | Exclusion
1 | No Structural Analysis or FEA included.
2 | No Material Selection Advice.
3 | No Fabrication Liability.
4 | No Patent Filing Services (only drawing support)
5 | No redesign or feature modification beyond existing prototype

## D1.16 Hands Off Meeting
Prepared by |  |  | Tool title |  | Initial Inquiry Notification |  | Date filled | Quality Target | 4 | Related Tool | Doc Control
Role |  |  | Project Reg. ID |  |  |  | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref | D1.5
Checked by |  |  | Phase Name |  | Onboarding |  | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref | D1.7 |  | IMHO GEN
Org/Dept. |  | R&D and ED | Activity Name |  | Inquiry Receipt |  | Duration | Iteration Num. | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID |  | D1.16 |  | Date Checked |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version |  | v1.0 |  | Date Approved | [5 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D1.16 HANDOFF MEETING MINUTES (Engineering to Contracting)
1.0 HANDOFF METADATA
Meeting Date: |  |  |  | [DD/MM/YYYY] | [5 empty] | Meeting Time: |  |  | [00:00 AM/PM]
Lead Engineer (Handing Off): |  |  |  | [Type Name] | [5 empty] | Contract Admin (Receiving): |  |  | [Type Name]
Project/Client Name: |  |  |  | [Type Name] | [5 empty] | Project Value (GHS): |  |  | [From D1.15]
Reference Request ID:
2.0 PROJECT BRIEF & BUDGET TRANSFER
Reference Document: |  |  | D1.15 Project Brief & Draft Budget |  |  |  |  | Link to D1.15: |  | [Insert Hyperlink]
Scope Summary: |  |  | [Type a 2-sentence summary of what IMHOGEN has committed to delivering.]
Payment Terms Agreed: |  |  | [e.g. 40% Advance / 40% Fabrication / 20% Handover]
3.0 CONTRACTING DIRECTIVES (Critical Risks & Exclusions to enforce in Contract)
SN | Risk / Exclusion Category |  |  |  |  | Specific Directive for Contract Admin | [5 empty] | Source Reference
3.1 | Scope Exclusion |  |  |  |  | [e.g. Ensure contract explicitly states regulatory certification is NOT included.] | [5 empty] | [From D1.13]
3.2 | Timeline Risk |  |  |  |  | [e.g. Add clause: Phase 2 timeline begins ONLY after formal CAD sign-off.] | [5 empty] | [From D1.11]
3.3 | Financial Risk |  |  |  |  | [e.g. Add clause: Quote valid for 21 days due to material price fluctuations.] | [5 empty] | [From D1.15]
3.4 | [Type here] |  |  |  |  | [Type here] | [5 empty] | [Type here]
4.0 SYSTEM HANDOFF & ARCHIVAL CHECKLIST (PID 1.5.2 & 1.5.3)
Task / Action Item | [7 empty] | Assignee |  |  |  | Status
Has the central database status been updated to "Contracting Phase"? | [7 empty] | Contract Admin |  |  |  | [Pending / Done]
Have all D1.1 to D1.15 documents been moved to the permanent digital folder? | [7 empty] | Lead Engineer |  |  |  | [Pending / Done]
Is the Contract Admin fully clear on the technical deliverables to be billed? | [7 empty] | Contract Admin |  |  |  | [Pending / Done]
5.0 FINAL SIGN-OFF
Engineering Release: |  |  | [Signature] |  |  |  |  | Contracting Acceptance: |  | [Signature]
Date: |  |  | [DD/MM/YYYY] |  |  |  |  | Date: |  | [DD/MM/YYYY]

## Aux. Invoice
INVOICE
IMHO GEN
Engineering Ideas Into Impact |  |  | Invoice No: | IMHO-INV26-ADV-012
Designing solutions. Building skills. |  |  | Invoice Type: | ADV / MIL / FIN
Powering industry. |  |  | Invoice Date: | 2026-04-06
|  |  | Due Date: | 21 working days
KBI, Near UPK, Opoku WareII Museum |  |  | Project Code: | CAD-1775340276795
KNUST, Kumasi – Ghana admin@imhogen.com |  |  | Project Title: | Prototype Digitization & Patent Documentation Package
BILLED BY: |  |  | BILLED TO:
IMHOGEN LTD |  |  | Client Organisation: | Syntropy Engineering Solutions
Reg No: CS011410126 |  |  | Client Address: | Suame Magazine
TIN: C006744075 |  |  | Contact Person: | Frederick Opoku
Prepared by: |  |  | Email: | dir@syntropyengineeringsolutionss.com
Clifford Fiannaa |  |  | Phone: | 0267384812
Kumasi, Ghana
ENGAGEMENT DESCRIPTION
Provision of reverse engineering, 3D CAD modeling, technical drafting, and patent-compliant documentation services for the digitization and formal representation of an existing prototype
Item | Description |  |  | Amount (GHS)
1 | Reverse Engineering & 3D Modeling |  |  | 3312
2 | Technical Drawing Package (ISO Standard) |  |  | 662.4
3 | Patent Drawing Development (Compliance Formatting) |  |  | 993.6
4 | Measurement, proportionation & Validation |  |  | 331.2
5 | Rendering & Documentation Packaging |  |  | 1324.8
Subtotal |  |  |  | 6624
AMOUNT DUE |  |  |  | 6624
PAYMENT MILESTONE |  |  | PAYMENT DETAILS
Project Value: |  | 6624 | Bank: | FIDELITY BANK
Contract signing (50%): |  | 3312 | Account Name: | IMHOGEN LTD
|  |  | Account Number: | 1050432877614
Please reference: |  |  | Branch: | KNUST
Invoice No: |  | IMHO-INV26-ADV-012
PAYMENT TERMS
This invoice is valid within 21 days from date of issue
Work commencement is subject to receipt of the required advance payment.
IMHO GEN reserves the right to suspend services or withhold deliverables until outstanding payments are settled.
IMHOGEN LTD ¦ Trading as IMHO GEN (A company incorporated under the laws of the Republic of Ghana)
Engineering Design ¦ Eng. Design Skills Development ¦ R&D ¦ QMS ¦ Productivity Consulting ¦ Innovation for Africa