## Tier 1 Product and Process Focu
PROCESS IDENTIFICATION |  |  | OPERATIONAL RESPONSIBILITY | OPERATIONAL RESPONSIBILITY |  |  | OPERATIONAL SYSTEM | OPERATIONAL SYSTEMS |  |  |  | CONTROL AND GOVERNANCE | CONTROL AND GOVERNANCE
PID | MAIN PROCESS | ACTIVITY DESCRIPTION |  | ACTIVITY OWNER | SUPPORTING ROLES | OPERATOR CATEGORY |  | TOOLS/TECHNOLOGIES | INFORMATION SYSTEMS | DOCUMENT USED | DOCUMENT GENERATED |  | MANAGEMENT POLICY | QUALITY CONTROL POINT | RISK CONSIDERATIONS
1.1 | Project Onboarding | Filter inquiries, translate needs into systems engineering operands. |  | Onboarding Mgr | Lead Engineer | Human System |  | Web Browser | Project Request Portal | D1.1 / D1.2 | D1.3 |  | Request Handling Policy | Verify notification contains readable technical data. | Wasting engineering time on out-of-scope inquiries.
1.2 | Technical Feasibility | Evaluate institutional capability, hardware, and specific project risks. |  | Lead Engineer | Head of Ops | Technical System |  | Workshop Audit | Capability Matrix | D1.8 / D1.9 | D1.10 / D1.11 |  | Feasibility Policy | Ensure workshop tools can reach required tolerances. | Accepting a project that exceeds machine precision limits.
1.3 | Draft Scope & Budget | Develop detailed SOW and multi-layer cost estimation for the project brief. |  | Project Manager | Finance Officer | Information System |  | Spreadsheet | Costing Engine | D1.13 | D1.14 / D1.15 |  | Pricing Policy | Verify markup layers cover regional supply chain volatility. | Underestimating direct costs for imported components.
2.1 | Contract Administration | Map technical variables into legal clauses and secure executive risk sign-off. |  | Contract Admin | Project Manager | Management System |  | Legal Templates | CRM / Drive | D1.16 / D2.1 | D2.2 / D2.5 |  | Contracting Policy | Confirm 'Background IP' is protected in Section 6. | Client assuming full ownership of IMHO background IP.
3.1 | Fund Management | Verify advance payment clearance and authorize engineering to commence. |  | Finance Officer | Project Manager | Information System |  | Bank Portal | Finance Database | D2.12 / D3.1 | D3.10 |  | Revenue Protection | Cross-reference payment with milestone trigger D3.3. | Beginning engineering work without cleared liquidity.
4.1 | Capacity & Baseline | Formally assign team roster and freeze the project schedule/budget baseline. |  | Project Manager | Head of Engineering | Human System |  | Resource Roster | Capacity Tracker | D2.14 / D4.3 | D4.8 |  | Agile Allocation | Verify assigned engineer has correct CAD license. | Assigning personnel who are already 100% utilized.
5.1 | Engineering Design | Execute functional synthesis, morphological matrices, and 3D layout construction. |  | Lead Engineer | CAD Engineer | Technical System |  | Autodesk Inventor | CAD Server | P1.0 / P3.1 | P5.4.1 / D5.0 |  | Design Intent Policy | Validate 'Organ Structure' against client wishes. | Designing a system that is functional but unmanufacturable.
6.1 | Drafting & Detailing | Decompose the master model into production drawings with standard GD&T. |  | CAD Engineer | Lead Draftsman | Technical System |  | AutoCAD / PDM | Drawing Hub | D6.5.1 / D6.5.2 | D6.5.3 / D6.5.4 |  | Drafting Standard | Verify view arrangements are logical and clear. | Missing dimensions leading to fabrication errors.
7.1 | Procurement | Extract BOM from locked CAD and manage vendor selection/receiving. |  | Operations Mgr | Lead Engineer | Information System |  | ERP / Drive | Inventory Ledger | D6.10 / D7.1 | D7.5 / D7.6 |  | Sourcing Policy | Verify incoming goods match technical spec (D7.6). | Delayed lead times for long-lead COTS components.
8.1 | Fabrication & Construction | Execute physical build following work orders and routing travelers. |  | Workshop Supr. | Technician | Human System |  | Welders / Machinery | Shop Floor Tracker | D8.1 / D8.4 | D8.5 / D8.6 |  | Safety & Mfg Policy | dimensional checks before final welding. | Welding distortion rendering parts out of tolerance.
9.1 | QA & Testing | Perform dimensional audits and dynamic load/function validation. |  | QA Officer | Test Engineer | Technical System |  | Calibrated Gauges | QA Database | D9.1 / D9.3 | D9.5 / D9.7 |  | Validation Standard | Test E-Stops and safety interlocks (D9.4). | Releasing a machine with undetected structural defects.
10.1 | Archiving & Handover | Lock native CAD, compile TDP, and transfer liability to client. |  | Project Manager | IT Admin | Management System |  | PDF Proofing | Project Vault | D10.1 / D10.3 | D10.4 / D11.4 |  | Archival Policy | Verify Final Handover Certificate (D11.4) is signed. | Maintaining liability for machines after physical delivery.

## Tier 3 Draftwork SOP Focus
PROCESS IDENTIFICATION |  |  | OPERATIONAL RESPONSIBILITY | OPERATIONAL RESPONSIBILITY |  |  | OPERATIONAL SYSTEMS | OPERATIONAL SYSTEMS |  |  |  | CONTROL AND GOVERNANCE | CONTROL AND GOVERNANCE
PID | MAIN PROCESS | ACTIVITY DESCRIPTION |  | ACTIVITY OWNER | SUPPORTING ROLES | OPERATOR CATEGORY |  | TOOLS/TECHNOLOGIES | INFORMATION SYSTEMS | DOCUMENT USED | DOCUMENT GENERATED |  | MANAGEMENT POLICY | QUALITY CONTROL POINT | RISK CONSIDERATIONS
3.1 | Technical Intake & Metrology | Capture physical dimensions and source asset quality to ensure CAD accuracy. |  | Lead Engineer | Technician | Human System |  | Calipers / Scanners | CAD Workspace | T3.D1.3a | T3.D1.8a |  | Metrology Standard | Verify calibration of measuring tools. | Inaccurate field data leads to unusable CAD models.
3.2 | Tier 3 Commercial Offer | Generate a combined scope and price offer to bypass heavy feasibility stages. |  | Project Manager | Finance Officer | Information System |  | Spreadsheet | ERP / Drive | T3.D1.8a | T3.D1.15a |  | Pricing Policy | Ensure IP Buyout fee is discussed if native files are requested. | Underpricing high-complexity reverse engineering work.
3.3 | Drafting Contract Mapping | Define IP ownership (Native vs PDF) and waive liability for client-provided data errors. |  | Contract Admin | Project Manager | Management System |  | Legal Templates | CRM / Drive | T3.D1.15a | T3.D2.2a |  | IP Protection Policy | Confirm 'Liability Waiver' is signed for client-provided models. | Legal disputes over ownership of source CAD files.
3.4 | Digital Asset Release Auth | Verify final payment in Fidelity Bank before authorizing digital file delivery. |  | Finance Officer | Lead Engineer | Information System |  | Bank Portal | Finance Database | D3.8 / D3.9 | T3.D3.10a |  | Revenue Protection | Cross-reference IP Buyout payment with contract terms. | Releasing native CAD before final GHS clearance.
3.5 | Direct Team Assignment | Assign drafting tasks directly to a CAD engineer, bypassing full capacity reviews. |  | Project Manager | CAD Engineer | Human System |  | Resource Roster | Capacity Tracker | T3.D3.10a | T3.D4.8a |  | Agile Allocation | Confirm assigned engineer has correct software license. | Assigning an engineer without specific 'Surfacing' or 'Reverse Eng' skills.
3.6 | 3D Modeling & Validation | Execute the 3D construction from field measurements and validate against design intent. |  | CAD Engineer | Lead Engineer | Technical System |  | Autodesk Inventor | CAD Server | T3.D1.8a | T3.D6.5.1a |  | Design Intent Policy | Validate 'As-Built' vs 'Corrected' features with Lead Eng. | Modeling 'wear and tear' instead of functional design intent.
3.7 | Final Approval & Asset Handover | Secure client digital sign-off and formally archive the technical data package. |  | Project Manager | CAD Engineer | Management System |  | PDF Proofing | Project Vault | T3.D6.5.1a | T3.D6.10a |  | Project Closure Policy | Verify 'Finance Unblock' is active before emailing final assets. | Sending high-res assets to client before formal CAD Lock.

## GENERAL FRAMEWORK
PROCESS IDENTIFICATION |  |  |  | OPERATIONAL RESPONSIBILITY |  |  |  | OPERATIONAL SYSTEMS |  |  |  |  | CONTROL AND GOVERNANCE
PID | MAIN PROCESS | ACTIVITY DESCRIPTION |  | ACTIVITY OWNER | SUPPORTING ROLES | OPERATOR CATEGORY |  | TOOLS/TECHNOLOGIES | INFORMATION SYSTEMS | DOCUMENT USED | DOCUMENT GENERATED |  | MANAGEMENT POLICY | QUALITY CONTROL POINT | RISK CONSIDERATIONS
1 | Project Onboarding and Definition Process |  | OPERATIONAL RESPONSIBILITY |  |  |  | OPERATIONAL SYSTEMS |  |  |  |  | CONTROL AND GOVERNANCE
1.1.1 | Inquiry Receipt & Logging | Receive automatic notification of a new client inquiry via website form or email. |  | Project Onboarding Manager | None | Information System |  | Email / Web Browser | Project Request Portal | Client Email / Web Form | Initial Inquiry Notification |  | Form Submission Protocol | Verify the notification contains readable text and contact info. | Email filtering to spam; missed notifications.
1.1.2 | Inquiry Receipt & Logging | Read the inquiry to perform a preliminary spam/relevance filter. |  | Project Onboarding Manager | None | Human System |  | Computer Display | Email Client | Initial Inquiry Notification | N/A |  | Project Request Handling Policy | Ensure the request broadly aligns with IMHOGEN's engineering services. | Wasting time on spam or out-of-scope solicitations.
1.1.3 | Inquiry Receipt & Logging | Create a new project entry in the tracker and copy/paste all client details into the respective fields. |  | Admin Support | Project Onboarding Manager | Information System |  | Keyboard/Mouse | Project Tracking Software | Initial Inquiry Notification | Received Request Record |  | Data Entry Protocol | Double-check that phone numbers and email addresses are copied without typos. | Typos in contact info leading to lost leads.
1.1.4 | Inquiry Receipt & Logging | Send standard acknowledgment email to the client stating the inquiry was received and outlining the next step. |  | Project Onboarding Manager | Admin Support | Information System |  | Email Templates | Email Client / CRM | Received Request Record | Acknowledgment Email |  | Client Communication Policy | Verify the client's name is spelled correctly in the template. | Client feels ignored if acknowledgment is delayed.
1.2.1 | Initial Needs Assessment | Contact the client to propose 2-3 available time slots for a technical discovery meeting. |  | Admin Support | Project Onboarding Manager | Information System |  | Scheduling Tool | Email Client / CRM | Received Request Record | Meeting Time Proposal |  | Meeting Scheduling Policy | Ensure proposed times fall within standard operating hours. | Scheduling conflicts causing delays.
1.2.2 | Initial Needs Assessment | Generate a calendar invite with a video conferencing link and a standard meeting agenda, and send it to the client. |  | Admin Support | None | Information System |  | Calendar App, Video Conferencing | Meeting Repository | Meeting Time Proposal | Calendar Invite & Agenda |  | Meeting Scheduling Policy | Verify the video link works and the time zone is correct. | Technical difficulties joining the meeting.
1.2.3 | Initial Needs Assessment | Conduct the discovery meeting to extract exact technical needs, operational constraints, and expected outcomes. |  | Project Onboarding Manager | Technical Support Provider | Human System |  | Video Conferencing, Note-taking app | Communication Channels | Calendar Invite & Agenda | Raw Meeting Notes |  | Meeting Facilitation Process | Ensure the client explicitly states their budget constraints and timelines. | Failing to ask critical constraint questions.
1.2.4 | Initial Needs Assessment | Clean up raw meeting notes and upload them into the central documentation repository. |  | Technical Support Provider | Project Onboarding Manager | Information System |  | Word Processor | Documentation Repository | Raw Meeting Notes | Needs Assessment Notes |  | Documentation Standards | Ensure all technical jargon and constraints are accurately transcribed. | Loss of critical technical details post-meeting.
1.3.1 | Project Feasibility Assessment | Share the Needs Assessment Notes with the Engineering and R&D team for internal review. |  | Project Onboarding Manager | Engineering Risk Officer | Information System |  | Internal Chat/Email | Project Tracking Software | Needs Assessment Notes | Internal Review Request |  | Internal Communication Protocol | Confirm receipt of the document by the Engineering team. | Bottlenecks if the engineering team misses the notification.
1.3.2 | Project Feasibility Assessment | Evaluate if the department has the required CAD software, tooling, and skills to execute the client's request. |  | R&D Coordinator | Technical Support Provider | Human System |  | Capability Checklist | Engineering Knowledge Repository | Needs Assessment Notes | Capability Assessment |  | Strategic Performance Protocols | Cross-check required software (e.g., Inventor) against current licenses. | Committing to a project without the necessary software/skills.
1.3.3 | Project Feasibility Assessment | Evaluate the request for regulatory, safety, and operational risks. |  | Engineering Risk & Safety Officer | R&D Coordinator | Management System |  | Risk Matrix | Project Data Analytic Platform | Needs Assessment Notes | Risk Assessment |  | Risk & Safety Policy | Ensure all physical safety standards related to the request are flagged. | Accepting a project with severe liability risks.
1.3.4 | Project Feasibility Assessment | Compile the Capability and Risk assessments into a final Go/No-Go Feasibility Report. |  | Engineering Risk Officer | Project Manager | Information System |  | Word Processor | Document Management System | Capability & Risk Assessments | Feasibility Report |  | Review and Approval Workflow | Final managerial review of the Go/No-Go recommendation. | Incorrect Go/No-Go decision based on flawed data.
1.4.1 | Scope & Budget Generation | If "Go", write out the exact technical deliverables (CAD models, BOMs, reports) the department will provide. |  | Project Manager | Engineering Team | Human System |  | Word Processor | Document Management System | Feasibility Report | Draft Scope of Work |  | Scope Definition Policy | Ensure deliverables are strictly defined to prevent scope creep. | Vague deliverables leading to client disputes later.
1.4.2 | Scope & Budget Generation | Estimate the required engineering man-hours, software usage time, and any specialized resource costs. |  | Project Manager | Finance Team | Information System |  | Cost Analysis Spreadsheet | Project Tracking Software | Draft Scope of Work | Cost Estimation Sheet |  | Financial Control Policy | Verify hourly rates match the current department standards. | Underpricing the engineering effort.
1.4.3 | Scope & Budget Generation | Combine the Scope of Work and Cost Estimation into the formal Project Brief & Draft Budget document. |  | Head of Business Operations | Project Manager | Information System |  | Publishing/Formatting Software | Document Management System | Scope & Cost Sheets | Project Brief & Draft Budget |  | Documentation Standards | Check formatting, spelling, and mathematical accuracy of the budget. | Presenting an unprofessional or mathematically incorrect brief.
1.5.1 | Internal Onboarding Handoff | Conduct a brief internal meeting to formally hand over the Project Brief to the contract administration team. |  | Project Onboarding Manager | Business Operation Team | Human System |  | Satiable Meeting Environment | Meeting Repository | Project Brief & Draft Budget | Handoff Meeting Minutes |  | Internal Handoff Protocol | Both parties must verbally agree that the scope is clear enough for contracting. | Legal drafting begins with misunderstood technical parameters.
1.5.2 | Internal Onboarding Handoff | Change the project status in the central database from "Onboarding" to "Contracting Phase". |  | Admin Support | Project Onboarding Manager | Information System |  | Keyboard/Mouse | Project Tracking Software | Handoff Meeting Minutes | Updated System Status |  | Project Portfolio Governance System | Verify the status change is reflected across all dashboards. | Tracking confusion if the system still shows "Onboarding".
1.5.3 | Internal Onboarding Handoff | Archive all onboarding raw documents (emails, initial notes) into the project's permanent digital folder. |  | Admin Support | None | Information System |  | File Explorer / Cloud Storage | Document Management System | All prior documents | Archived Onboarding Folder |  | Documentation Repository Policy | Ensure all files are correctly named and tagged before archiving. | Cluttered or lost historical files.
2 | Contract Tracking and Administration Process
2.1.1 | Contract Drafting | Receive the formal Project Brief & Draft Budget from the Onboarding handoff and review for clarity. |  | Business Operations Team | Head of Business Operations | Human System |  | Computer Display | Document Management System | Project Brief & Draft Budget | N/A |  | Contract Drafting Policy | Ensure all technical deliverables and budget figures are explicitly stated. | Ambiguous inputs leading to poorly drafted contracts.
2.1.2 | Contract Drafting | Access the central legal repository and download the appropriate standard contract templates (SLA, NDA, SOW). |  | Admin Support | Business Operations Team | Information System |  | File Explorer | Contract Management Database | N/A | Standard Contract Templates |  | Document Version Control Policy | Verify the templates are the most currently approved versions by legal. | Using outdated legal templates with voided clauses.
2.1.3 | Contract Drafting | Populate the selected templates with client details, scope of work, budget, and specific constraints. |  | Business Operations Team | Admin Support | Information System |  | Word Processor | Document Management System | Project Brief, Templates | Initial Draft Contract |  | Contract Drafting Policy | Double-check client legal name, addresses, and monetary figures. | Typos in critical financial or legal identifying information.
2.2.1 | Internal Review & Approval | Route the Initial Draft Contract to the Project Manager to verify that the technical scope matches the department's capability. |  | Business Operations Team | Project Manager | Management System |  | Internal Routing/Approval Tool | Document Management System | Initial Draft Contract | PM Reviewed Draft |  | Internal Review Protocol | PM must sign off that the timeline and technical deliverables are realistic. | Legal commitment to impossible engineering timelines.
2.2.2 | Internal Review & Approval | Route the PM Reviewed Draft to the Finance Team to verify payment milestones, taxes, and total contract value. |  | Business Operations Team | Finance Team | Management System |  | Internal Routing/Approval Tool | Document Management System | PM Reviewed Draft | Finance Reviewed Draft |  | Financial Control Policy | Finance must verify the payment schedule aligns with cash flow needs. | Unfavorable payment terms that restrict project funding.
2.2.3 | Internal Review & Approval | Submit the draft to the Legal Advisor (if applicable) for a final compliance and liability check. |  | Head of Business Operations | Legal Advisor | Human System |  | Word Processor (Track Changes) | Contract Management Database | Finance Reviewed Draft | Internally Approved Draft |  | Corporate Governance Policy | Check for excessive liability, indemnification, or IP forfeiture clauses. | Exposing IMHOGEN to severe legal or financial liabilities.
2.3.1 | Client Negotiation | Draft a formal email and send the Internally Approved Draft to the client for their review. |  | Client Experience Manager | Business Operations Team | Information System |  | Email Templates | CRM / Email Client | Internally Approved Draft | Client Transmittal Record |  | Client Communication Policy | Ensure the email clearly states the deadline for their review/redlines. | Open-ended reviews causing project scheduling delays.
2.3.2 | Client Negotiation | Receive client feedback/redlines. If changes are requested, schedule a negotiation meeting. |  | Client Experience Manager | Admin Support | Human System |  | Scheduling Tool | CRM / Calendar | Client Redlines | Negotiation Meeting Invite |  | Meeting Scheduling Policy | Ensure relevant decision-makers (Head of Ops, PM) are invited. | Inability to resolve contract disputes via email alone.
2.3.3 | Client Negotiation | Conduct the negotiation meeting, discuss disputed clauses, and agree on mutual compromises. |  | Head of Business Operations | Client Experience Manager | Human System |  | Video Conferencing | Meeting Repository | Client Redlines | Negotiation Meeting Notes |  | Client Engagement Policy | Never agree to technical or financial changes without PM/Finance input. | Verbal agreement to terms that violate department policies.
2.3.4 | Client Negotiation | Update the contract document based on the agreed compromises and conduct a final internal read-through. |  | Business Operations Team | Legal Advisor | Information System |  | Word Processor | Document Management System | Negotiation Meeting Notes | Finalized Contract |  | Contract Revision Policy | Ensure no unintended clauses were altered during the redline process. | Sneaky or accidental changes inserted into the final text.
2.4.1 | Execution & Archiving | Upload the Finalized Contract into the digital signature platform and tag the required signature fields. |  | Admin Support | Business Operations Team | Information System |  | E-Signature Platform | Contract Management Database | Finalized Contract | Pending Signature Contract |  | Document Execution Policy | Verify the correct authorized signers for both IMHOGEN and the client. | Contract sent to an unauthorized representative.
2.4.2 | Execution & Archiving | Dispatch the digital envelope to the client and monitor the platform for completion. |  | Admin Support | None | Information System |  | E-Signature Platform | Contract Management Database | Pending Signature Contract | Signature Status Log |  | Signature Authority Policy | Send automatic 48-hour reminders if the document remains unsigned. | Project stalling due to forgotten signatures.
2.4.3 | Execution & Archiving | Once signed by all parties, download the final document and its digital audit trail certificate. |  | Admin Support | None | Information System |  | E-Signature Platform | Document Management System | Pending Signature Contract | Executed Contract & Audit Trail |  | Document Execution Policy | Verify the audit certificate is attached to prove legal validity. | Inability to prove the signature's authenticity in a dispute.
2.4.4 | Execution & Archiving | Upload the Executed Contract into the central secure legal repository and apply appropriate metadata tags. |  | Admin Support | IT Support | Information System |  | Cloud Storage / Database | Contract Management Database | Executed Contract | Archived Contract Record |  | Data Retention Policy | Ensure strict access control (read-only) is applied to the final file. | Unauthorized alteration or deletion of executed contracts.
2.4.5 | Execution & Archiving | Update the CRM/Project Tracker status to "Contract Executed" and trigger a notification to the Finance Team to begin Payment Scheduling. |  | Project Onboarding Manager | Finance Team | Management System |  | Workflow Trigger | Project Tracking Software | Archived Contract Record | Phase Initiation Notice |  | Project Portfolio Governance System | Confirm the Finance Team acknowledges the trigger to start billing. | Failure to initiate invoicing after the contract is signed.
3 | Payment Scheduling and Fund Management Process.
3.1.1 | Payment Schedule Setup | Receive the "Phase Initiation Notice" and the Executed Contract from the Business Operations Team. |  | Finance Officer | Admin Support | Information System |  | Email / Internal Chat | Project Tracking Software | Phase Initiation Notice, Executed Contract | N/A |  | Inter-departmental Handoff Policy | Confirm receipt of the fully executed contract before initiating any financial setup. | Setting up billing on an unfinalized or unsigned contract.
3.1.2 | Payment Schedule Setup | Read the contract's commercial terms to extract exact milestone descriptions, payment percentages, and due dates. |  | Finance Officer | None | Human System |  | Computer Display | Document Management System | Executed Contract | Payment Terms Extract |  | Billing & Scheduling Policy | Verify that the extracted milestones exactly match the contract's language. | Misinterpreting payment terms leading to incorrect billing schedules.
3.1.3 | Payment Schedule Setup | Create a new client profile and project ledger in the accounting system, inputting the extracted payment schedule. |  | Finance Officer | Finance Manager | Information System |  | Keyboard/Mouse | ERP / Accounting Software | Payment Terms Extract | System Payment Record |  | Data Entry Protocol | Finance Manager must perform a spot-check on the entered schedule vs the contract. | Data entry errors causing missed or incorrect future invoices.
3.2.1 | Invoicing & Billing | Receive formal notification and proof of completion for a specific project milestone from the Project Manager. |  | Finance Officer | Project Manager | Information System |  | Internal Routing Tool | Project Tracking Software | Milestone Completion Report | Milestone Billing Trigger |  | Invoicing Policy | Verify the PM's proof of completion aligns with the contract's definition of the milestone. | Billing a client before the engineering value has actually been delivered.
3.2.2 | Invoicing & Billing | Generate a draft invoice in the accounting software corresponding to the achieved milestone and scheduled amount. |  | Finance Officer | None | Information System |  | Accounting Software | ERP / Accounting Software | System Payment Record | Draft Invoice |  | Invoicing Policy | Ensure PO numbers, tax IDs, and bank details are clearly visible on the invoice. | Invoices rejected by the client's accounts payable due to missing details.
3.2.3 | Invoicing & Billing | Review and approve the draft invoice for mathematical accuracy and tax compliance before issuance. |  | Finance Manager | Finance Officer | Management System |  | Accounting Software | ERP / Accounting Software | Draft Invoice | Approved Invoice |  | Financial Control Policy | Dual-authorization required for invoices exceeding a predefined monetary threshold. | Sending mathematically incorrect invoices that damage company credibility.
3.2.4 | Invoicing & Billing | Draft a formal email, attach the Approved Invoice (PDF format), and transmit it to the client's designated billing contact. |  | Finance Officer | Client Experience Manager | Information System |  | Email Templates | CRM / Email Client | Approved Invoice | Transmitted Invoice Record |  | Client Communication Policy | Verify the email address is the official accounts payable contact, not just the technical lead. | Invoice sitting unread in the wrong person's inbox.
3.3.1 | Reconciliation & Triggering | Log into the corporate banking portal daily to monitor and download reports of incoming client deposits. |  | Finance Officer | None | Information System |  | Banking Portals | Banking System | N/A | Daily Bank Statement |  | Treasury Management Policy | Ensure secure network connections and VPNs are used when accessing banking portals. | Unnoticed funds leading to unnecessary project delays.
3.3.2 | Reconciliation & Triggering | Cross-reference incoming bank deposits against outstanding invoices in the accounting software. |  | Finance Officer | None | Information System |  | Reconciliation Tools | ERP / Accounting Software | Daily Bank Statement, Transmitted Invoice | Reconciled Payment Log |  | Financial Reconciliation Policy | Match the exact deposited amount and payment reference number to the specific invoice. | Misallocating funds to the wrong client or project ledger.
3.3.3 | Reconciliation & Triggering | Generate a formal Payment Receipt and email it to the client to acknowledge successful receipt of funds. |  | Finance Officer | Admin Support | Information System |  | Accounting Software | CRM / Email Client | Reconciled Payment Log | Payment Receipt |  | Documentation Policy | Issue the receipt within 24 hours of the funds clearing the bank. | Client disputes or uncertainty regarding their account standing.
3.3.4 | Reconciliation & Triggering | Change the invoice status to "Paid" and send a "Payment Cleared - Proceed" notification to the Project Manager. |  | Finance Officer | Project Manager | Management System |  | Workflow Trigger | Project Tracking Software | Reconciled Payment Log | Phase Unblock Notice |  | Project Portfolio Governance System | PM must acknowledge the unblock notice before deploying engineering resources. | Engineering team remaining idle because they are unaware funds have cleared.
3.4.1 | Outstanding Payment Mgmt | Generate an Accounts Receivable (AR) aging report weekly to identify invoices that have crossed their payment grace period. |  | Finance Officer | Finance Manager | Information System |  | Reporting Dashboard | ERP / Accounting Software | System Payment Record | Overdue Accounts Report |  | Credit Control Policy | Ensure the report accurately reflects the net terms (e.g., Net 30) agreed in the contract. | Accumulation of bad debt and severe cash flow bottlenecks.
3.4.2 | Outstanding Payment Mgmt | Send a polite, standardized follow-up email to clients with overdue invoices, requesting payment status. |  | Finance Officer | Client Experience Manager | Human System |  | Email Templates | CRM / Email Client | Overdue Accounts Report | Payment Reminder Log |  | Outstanding Collections Policy | Maintain a professional tone to preserve the client relationship while being firm on terms. | Damaging client relations with aggressive or premature collection tactics.
3.4.3 | Outstanding Payment Mgmt | If payment is delayed beyond critical thresholds, issue a formal "Stop Work" notice to the Project Manager. |  | Finance Manager | Head of Business Operations | Management System |  | Internal Communication | Project Tracking Software | Overdue Accounts Report | Stop Work Directive |  | Risk & Financial Liability Policy | Escalate to Head of Business Operations before halting major engineering work. | Continuing to burn man-hours and resources on a defaulting client.
4 | Team Assignment and Capacity Planning Process.
4.1.1 | Resource Requirement Analysis | Receive the "Phase Initiation Notice" and the finalized Project Brief from the Business Operations Team. |  | Project Manager | None | Information System |  | Email / Internal Chat | Project Tracking Software | Phase Initiation Notice, Project Brief | N/A |  | Inter-departmental Handoff Policy | Verify the Project Brief contains explicitly approved timelines and budgets. | Initiating planning based on unapproved or draft requirements.
4.1.2 | Resource Requirement Analysis | Read the Project Brief to list the specific technical competencies, software platforms (e.g., Inventor), and estimated man-hours required. |  | Project Manager | Technical Support Provider | Human System |  | Computer Display | Document Management System | Project Brief | Technical Requirement Notes |  | Talent Management Policy | Ensure all required niche skills or specialized software modules are identified. | Realizing midway through the project that the team lacks a critical skill.
4.1.3 | Resource Requirement Analysis | Populate the standard Resource Request Form with the required roles, hours, and duration, and submit it to HR/Engineering Management. |  | Project Manager | None | Information System |  | Word Processor / Digital Form | HR Management System | Technical Requirement Notes | Resource Request Form |  | Resource Allocation Policy | Double-check that the requested man-hours align with the approved budget. | Requesting more man-hours than the project budget can afford.
4.2.1 | Capacity Assessment & Allocation | Receive the Resource Request Form and open the department's scheduling dashboard to view current staff workloads. |  | HR Manager | Engineering Manager | Information System |  | Scheduling Dashboard / Gantt | HR Management System | Resource Request Form | N/A |  | Workforce Management Policy | Ensure no single engineer is assigned a sustained workload exceeding 85% capacity. | Staff burnout, missed deadlines, and poor quality output due to overloading.
4.2.2 | Capacity Assessment & Allocation | Cross-reference the requested competencies with the skills matrix of available engineers, draftsmen, and QA/QC staff. |  | Engineering Manager | HR Manager | Management System |  | Skills Competency Matrix | HR Management System | Resource Request Form | N/A |  | Talent Management Policy | Match the complexity of the project with the seniority level of the assigned engineer. | Assigning a junior engineer to a high-risk, complex system design without proper support.
4.2.3 | Capacity Assessment & Allocation | Select the specific personnel for the project and formally log their assigned hours and roles into the tracking system. |  | HR Manager | Admin Support | Information System |  | Keyboard/Mouse | Project Tracking Software | Resource Request Form | Team Assignment Record |  | Resource Allocation Policy | Verify that planned leave or PTO does not conflict with critical project milestones. | Key personnel going on vacation during a critical design deadline.
4.3.1 | Workspace & Access Setup | Receive the Team Assignment Record and trigger the IT/Admin provisioning workflow. |  | IT / Admin Support | HR Manager | Information System |  | IT Ticketing System | Project Tracking Software | Team Assignment Record | Provisioning Ticket |  | Information Security Policy | Ensure only the individuals listed on the Assignment Record receive access. | Providing confidential client data access to unauthorized personnel.
4.3.2 | Workspace & Access Setup | Create dedicated project folders in the central Document Management System and CAD PDM Vault, applying strict access controls. |  | IT / Admin Support | None | Information System |  | Admin Consoles | Document Management System / PDM | Provisioning Ticket | N/A |  | Documentation Standards | Apply standardized naming conventions to all newly created digital folders. | Chaotic file storage leading to lost CAD models or overwritten documents.
4.3.3 | Workspace & Access Setup | Set up dedicated internal communication channels (e.g., specific chat groups or email threads) and invite the assigned team. |  | IT / Admin Support | Project Manager | Information System |  | Communication Platforms | Communication Channels | Provisioning Ticket | Access Confirmation Log |  | Internal Communication Protocol | Ensure the Project Manager is granted "Admin" rights over the new communication channels. | Fragmented communication happening outside the official project channels.
4.4.1 | Internal Kick-off Execution | Draft a structured kick-off presentation summarizing the client's goals, the technical constraints, the budget, and the timeline. |  | Project Manager | None | Information System |  | Presentation Software | Document Management System | Project Brief, Team Assignment Record | Internal Kick-off Deck |  | Internal Communication Protocol | Ensure all proprietary client details are masked if the presentation is stored broadly. | Team members lacking a holistic understanding of the project's 'why'.
4.4.2 | Internal Kick-off Execution | Send a calendar invite for the internal kick-off meeting to the assigned team and attach the Project Brief for pre-reading. |  | Admin Support | Project Manager | Information System |  | Calendar App | Meeting Repository | Internal Kick-off Deck | Calendar Invite |  | Meeting Scheduling Policy | Verify that the scheduled time works for all assigned critical personnel. | Key technical experts missing the foundational alignment meeting.
4.4.3 | Internal Kick-off Execution | Conduct the video/in-person kick-off meeting, explicitly outlining the roles, expectations, and the "black-box" input/output deliverables. |  | Project Manager | Assigned Team | Human System |  | Video Conferencing / Whiteboard | Communication Channels | Internal Kick-off Deck | Kick-off Meeting Minutes |  | Project Initiation Policy | Require verbal confirmation from the Lead Engineer that the timeline is understood. | The technical team leaving the meeting with misaligned expectations.
4.4.4 | Internal Kick-off Execution | Log into the Project Tracking Software, formally lock the baseline schedule/budget, and change the project status to "Engineering Design Phase". |  | Project Manager | None | Management System |  | Keyboard/Mouse | Project Portfolio Governance System | Kick-off Meeting Minutes | Locked Project Baseline |  | Baseline Governance Policy | Ensure the baseline matches the kick-off agreements exactly; restrict editing access. | Unapproved changes creeping into the schedule after the kick-off.
5 | Standard Engineering Design Process (P1 - P6 Framework)
5.1.1 | P1: Requirements Elaboration | Establish rough factors for all life phases (technology, operators, inputs, outputs) and analyze the TP environment. |  | Lead Engineer | Design Engineer | Technical System |  | Requirement Tool (P1.1 - P1.3) | Engineering Database | Project Brief (P0) | Draft Life Phase Requirements |  | Requirements Engineering Policy | Verify all input/output operands match the Project Brief constraints. | Missing a critical operational environment constraint early on.
5.1.2 | P1: Requirements Elaboration | Quantify requirements, assign tolerances, and allocate properties across functional life phases and operators. |  | Lead Engineer | QA/QC Officer | Management System |  | Requirement Tool (P1.4 - P1.7b) | Engineering Database | Draft Life Phase Requirements | Weighted Requirements List |  | Tolerance & Capability Policy | Validate tolerances against available standard workshop capabilities. | Over-tolerancing leading to unmanufacturable or costly designs.
5.1.3 | P1: Requirements Elaboration | Compile, review, and lock the formal, multi-dimensional design specifications. |  | Lead Engineer | Project Manager | Management System |  | Spec Tool (Pr1 - Pr8, P1.8) | Document Management System | Weighted Requirements List | Final Design Specification (Pr-Set) |  | Design Specification Governance | Formal sign-off on the Pr-Set before any design work begins. | Proceeding to conceptual design with ambiguous or conflicting specifications.
5.2.1 | P2: Design Work Planning | Analyze the technical process viewpoints, assess difficulty, and assign specific design tasks to operators. |  | Lead Engineer | Project Manager | Human System |  | Planning Tool (P2.1 - P2.4) | Project Tracking Software | Final Design Specification | Design Task Allocation |  | Resource Allocation Policy | Ensure assigned engineers have the required technical competency. | Assigning complex datum calculations to junior staff.
5.2.2 | P2: Design Work Planning | Estimate design costs, map the schedule, and set up phase progress tracking mechanisms. |  | Project Manager | Lead Engineer | Information System |  | Planning Tool (P2.5 - P2.8) | Project Portfolio System | Design Task Allocation | EDPM Gantt & Progress Trackers (Pr2.2a-f) |  | Baseline Governance Policy | Baseline schedule must align with overall project budget and timeline. | Underestimating required man-hours for complex FEA or CAD modeling.
5.3.1 | P3: Transformation Process (TrfP) | Establish the operands (Material, Energy, Information) and the technological principles of the operations process. |  | Systems Engineer | Lead Engineer | Technical System |  | Process Tool (P3.1, P3.1a-b) | Engineering Database | Final Design Specification | Transformation Process Diagram |  | Systems Engineering Policy | Verify logical flow: all input operands must logically convert to outputs. | Incomplete transformation mapping leading to missing mechanical functions.
5.3.2 | P3: TS-Function Structure | Distribute effects between technical/human systems, defining main, assisting, and evoked functions. |  | Systems Engineer | Design Engineer | Technical System |  | Function Tool (P3.2, P3.2a-b, P3.3) | Engineering Database | Transformation Process Diagram | Optimal Functional Structure |  | Functional Decomposition Protocol | Ensure no critical load-bearing or safety function is overlooked. | Functional black-boxes left unresolved before structural synthesis.
5.4.1 | P4: Organ Structure Synthesis | Populate the morphological matrix with action principles and combine function carriers (organs) into unified concepts. |  | Design Engineer | Systems Engineer | Technical System |  | Morphological Tool (P4.1) | Concept Repository | Optimal Functional Structure | Synthesized Concept Proposals |  | Concept Generation Protocol | Ensure at least 3 distinct conceptual variants are generated. | Fixation on a single design path without exploring optimal alternatives.
5.4.2 | P4: Topology & Organ Selection | Establish spatial topologies (Iconic/Principle) and evaluate proposals to select the optimal Final Organ Structure. |  | Lead Engineer | Design Engineer | Management System |  | Topology Tool (P4.2) | Document Management System | Synthesized Concept Proposals | Final Organ Structure |  | Design Evaluation Policy | Justify the selected organ structure mathematically against the Pr-Set. | Selecting a suboptimal layout due to bias rather than technical merit.
5.5.1 | P5: Constructional Structure | Establish preliminary layouts, rough forms, and define constructional design groups from the organ structure. |  | Design Engineer | Draftsman | Technical System |  | Layout Tool (P5.1 - P5.3.1) | CAD Environment | Final Organ Structure | Preliminary Spatial Layout |  | Spatial Design Policy | Clash detection and clearance check at the preliminary layout stage. | Components interfering spatially during assembly.
5.5.2 | P5: Definitive Dimensional Layout | Definitively establish dimensions, material treatments, part decompositions, and perform strength analyses. |  | Design Engineer | Technical Expert | Technical System |  | Constructional Tool (P5.4, P5.4.1) | PDM Vault / CAE Software | Preliminary Spatial Layout | Detailed 3D CAD Models |  | Geometric Dimensioning & Tolerancing (GD&T) Policy | Tolerance stack-up analysis and FEA validation against the Pr-Set. | Structural failure or excessive deflection under operational loads.
5.6.1 | P6: Detailing & Assembly Control | Generate individual detailed manufacturing drawings, control assembly drawings, and hierarchical part lists. |  | Draftsman | Design Engineer | Technical System |  | Drafting Tool (P6, P6.1) | PDM / Document Control System | Detailed 3D CAD Models | Engineering Drawings & CAD BOM |  | Documentation Standards Policy | Drawing checker review (Title blocks, GD&T, notes) by Lead Engineer. | Releasing incomplete or inaccurate drawings to the fabrication floor.
5.6.2 | P6: Final Release & Audit | Prepare manufacturing instructions, conduct a final design audit, and release the complete technical data package. |  | Lead Engineer | Project Manager | Management System |  | Phase Control Tool (P6.4 - P6.6) | Document Management System | Engineering Drawings & CAD BOM | Approved Technical Data Package |  | Engineering Release Protocol | Complete sign-off matrix verification prior to manufacturing release. | Manufacturing unapproved or obsolete file versions.
6 | Client Review and Approval Process.
6.1.1 | Deliverable Submission | Receive the "Approved Technical Data Package" (CAD, Drawings, BOM, Reports) from the Lead Engineer. |  | Project Manager | None | Information System |  | Internal Routing Tool | Document Management System | Approved Technical Data Package | N/A |  | Internal Handoff Protocol | Verify all files possess the required internal QA/QC signature before sending to the client. | Submitting unverified or draft engineering files to the client.
6.1.2 | Deliverable Submission | Upload the deliverables into a secure, client-facing digital portal or package them into a secure file-transfer link. |  | Admin Support | Project Manager | Information System |  | File Sharing Platforms | Client Portal / CRM | Approved Technical Data Package | Client Delivery Link |  | Data Security & Sharing Policy | Ensure access permissions are strictly limited to the authorized client contacts. | Unauthorized interception of proprietary IMHOGEN designs.
6.1.3 | Deliverable Presentation | Draft and send a calendar invite for a formal "Deliverable Presentation Meeting" to walk the client through the design. |  | Client Relations Team | Admin Support | Information System |  | Calendar App / CRM | Meeting Repository | Client Delivery Link | Meeting Invite |  | Client Engagement Policy | Schedule the meeting within 48 hours of sending the deliverables to maintain momentum. | Client reviewing complex technical files without proper context, leading to confusion.
6.1.4 | Deliverable Presentation | Conduct the presentation meeting, using 3D viewers to explain technical decisions, constraints, and functional compliance. |  | Project Manager | Lead Engineer | Human System |  | Video Conferencing / 3D CAD Viewers | Communication Channels | Approved Technical Data Package | Presentation Meeting Minutes |  | Meeting Facilitation Process | Ensure the Lead Engineer explains why certain design constraints were enforced. | Client rejecting a design because they do not understand the underlying engineering logic.
6.2.1 | Feedback Collection | Send the standardized "Client Feedback Form" to the client immediately following the presentation. |  | Client Relations Team | None | Information System |  | Digital Forms (e.g., Google Forms) | CRM | Presentation Meeting Minutes | Client Feedback Form (Blank) |  | Feedback Handling Procedure | Formally state the deadline (e.g., 5 business days) for submitting the feedback form. | Open-ended feedback timelines stalling the project indefinitely.
6.2.2 | Feedback Collection | Receive the completed feedback form from the client and extract all requested changes into the central Revision Log. |  | Admin Support | Client Relations Team | Information System |  | Spreadsheet | Project Tracking Software | Completed Feedback Form | Master Revision Log |  | Documentation Standards | Ensure every single client comment is captured line-by-line without summarization. | Losing or ignoring a specific client request, leading to dissatisfaction.
6.3.1 | Feedback Evaluation | Review the Master Revision Log against the original signed Contract/Project Brief to classify changes as "Minor" or "Major". |  | Project Manager | Lead Engineer | Management System |  | Scope Analysis Tools | Contract Management System | Master Revision Log, Executed Contract | Scope Assessment Report |  | Change Management Policy | "Major" changes (out of scope) must immediately trigger a financial Change Order request. | Performing out-of-scope engineering redesigns for free (Scope Creep).
6.3.2 | Revision Execution | Route approved "Minor" revisions back to the engineering team, assigning specific PID tasks for CAD/Drawing updates. |  | Project Manager | Engineering Manager | Information System |  | Task Management Dashboard | Project Tracking Software | Scope Assessment Report | Engineering Revision Tickets |  | Revision Control Policy | Ensure the revision tickets explicitly link back to the specific client feedback line item. | Engineers misunderstanding the requested change and altering the wrong component.
6.3.3 | Revision Execution | Execute the requested changes in the CAD models and update the associated 2D drawings and BOMs. |  | Design Engineer | Draftsman | Technical System |  | 3D CAD Software / Drafting Tools | PDM Vault | Engineering Revision Tickets | Revised Technical Data Package |  | Iterative Design Policy | Save the revised files as a new version (e.g., V1.1) to preserve the original baseline. | Overwriting the original design files and losing previous work.
6.3.4 | Revision Verification | Perform a QA/QC check on the revised files to ensure the specific feedback was addressed without breaking other system functions. |  | QA/QC Officer | Lead Engineer | Management System |  | Traceability Matrix | Requirements Management System | Revised Technical Data Package, Revision Log | Revision QA Sign-off |  | Quality Assurance Guidelines | Verify that the new changes still comply with the original Pr-Set safety and load requirements. | A minor revision inadvertently causing a critical structural or functional failure.
6.4.1 | Final Sign-off & Acceptance | Generate the formal "Delivery & Acceptance Form" stating that all design requirements and revisions have been met. |  | Business Operations Team | Project Manager | Information System |  | Word Processor | Document Management System | Revision QA Sign-off | Delivery & Acceptance Form |  | Sign-off & Acceptance Protocol | Cross-check the final deliverable list on the form against the original contract. | Missing a contracted deliverable on the final acceptance sheet.
6.4.2 | Final Sign-off & Acceptance | Upload the Acceptance Form and the Final Revised Technical Data Package into the e-signature platform. |  | Admin Support | Client Relations Team | Information System |  | E-Signature Platform (DocuSign, Adobe Sign) | Contract Management Database | Delivery & Acceptance Form | Pending Signature Envelope |  | Document Execution Policy | Verify the digital envelope is sent to the client's authorized legal/financial signatory. | Obtaining a sign-off from an unauthorized client representative.
6.4.3 | Final Sign-off & Acceptance | Conduct a brief final Handover Meeting (if requested by the client) to officially close the design phase and answer final questions. |  | Project Manager | Client Relations Team | Human System |  | Video Conferencing | Meeting Repository | Final Revised Technical Data Package | Handover Meeting Minutes |  | Client Engagement Policy | Confirm verbally during the meeting that no further engineering changes will be made. | Client attempting to request more changes after the handover meeting.
6.4.4 | Final Sign-off & Acceptance | Receive the executed e-signature, archive all final documents, and trigger the Finance Team to issue the final invoice. |  | Admin Support | Project Manager | Management System |  | Workflow Trigger | Project Tracking Software | Signed Delivery & Acceptance Form | Project Phase Closure Notice |  | Project Portfolio Governance System | Ensure all finalized CAD models are locked in the PDM vault to prevent further editing. | Accidental alterations to the finalized, client-approved engineering files.
7 | Procurement Process
7.1.1 | BOM Handover & Review | Receive the "Project Phase Closure Notice" and the finalized, QA-approved Bill of Materials (BOM) from the Project Manager. |  | Procurement Officer | Project Manager | Information System |  | Internal Routing Tool | Project Tracking Software | Approved Technical Data Package (BOM) | N/A |  | Inter-departmental Handoff Policy | Verify the BOM has the formal "Released for Manufacturing" digital signature. | Procuring materials based on an obsolete or unapproved draft BOM.
7.1.2 | BOM Handover & Review | Import the digital BOM into the procurement dashboard and categorize items into raw materials, standard hardware, and custom components. |  | Procurement Officer | None | Information System |  | Spreadsheet / ERP Software | Procurement Dashboard | Final CAD BOM | Categorized Procurement List |  | Documentation Standards | Ensure units of measure (e.g., mm, meters, kg) are correctly mapped during import. | Unit conversion errors leading to massive over/under ordering of steel sections.
7.2.1 | Budget Validation & Sourcing | Cross-reference the Categorized Procurement List against the locked financial budget established in the Project Brief. |  | Procurement Officer | Finance Officer | Management System |  | Budgeting Spreadsheet | Financial Tracking System | Categorized Procurement List, Locked Budget | Initial Budget Variance Report |  | Financial Control Policy | Flag any item where the current market price exceeds the estimated baseline budget by >10%. | Material price fluctuations destroying the project's profit margin.
7.2.2 | Budget Validation & Sourcing | Generate a Request for Quotation (RFQ) for required materials, specifying exact tolerances, grades, and quantities. |  | Procurement Officer | None | Information System |  | Word Processor / ERP | Document Management System | Categorized Procurement List | Request for Quotation (RFQ) |  | Vendor Sourcing Policy | Ensure RFQs for standard structural steel clearly state acceptable tolerance limits for local market variations. | Vendors quoting for sub-standard or incorrect material grades.
7.2.3 | Budget Validation & Sourcing | Dispatch RFQs to approved local suppliers (e.g., Suame/Kumasi market vendors) and specialized international distributors via email. |  | Admin Support | Procurement Officer | Information System |  | Email Client | CRM / Vendor Database | Request for Quotation (RFQ) | RFQ Dispatch Log |  | Vendor Communication Protocol | Verify vendor email addresses and set a strict deadline (e.g., 48 hours) for quote returns. | Project delays due to endlessly waiting on vendor quotes.
7.2.4 | Budget Validation & Sourcing | Receive quotes, compile a comparative vendor matrix (price, lead time, quality history), and select the optimal suppliers. |  | Procurement Officer | Project Manager | Management System |  | Decision Matrix / Spreadsheet | Procurement Dashboard | Vendor Quotes | Vendor Selection Matrix |  | Vendor Sourcing Policy | Justify selection if the cheapest vendor is not chosen (e.g., due to faster lead time or better quality). | Selecting an unreliable vendor solely because they offered the lowest price.
7.3.1 | Purchasing & PO Issuance | Generate formal Purchase Orders (POs) in the accounting system for the selected vendors, attaching the required engineering specs. |  | Procurement Officer | None | Information System |  | Accounting / ERP Software | Financial Tracking System | Vendor Selection Matrix | Draft Purchase Order (PO) |  | Purchasing Policy | Double-check payment terms, delivery address, and required delivery dates on the PO. | Materials shipped to the wrong address or on the wrong timeline.
7.3.2 | Purchasing & PO Issuance | Route the Draft PO to the Finance Manager for final financial authorization and fund allocation. |  | Procurement Officer | Finance Manager | Management System |  | Internal Approval Workflow | Financial Tracking System | Draft Purchase Order (PO) | Approved Purchase Order |  | Financial Control Policy | Finance Manager must verify that sufficient cash flow exists to clear the PO upon delivery. | Issuing POs without the capital to pay the vendor, damaging IMHOGEN's credit.
7.3.3 | Purchasing & PO Issuance | Transmit the Approved PO to the vendor and obtain a formal acknowledgment and confirmed delivery schedule. |  | Admin Support | Procurement Officer | Information System |  | Email Client | Vendor Database | Approved Purchase Order | PO Acknowledgment Receipt |  | Vendor Communication Protocol | Do not mark the item as "Ordered" until the vendor explicitly confirms receipt and capacity. | Assuming an order is placed when the vendor never actually saw the PO.
7.4.1 | Material Receiving & QA | Receive the physical delivery at the workshop. Cross-reference the vendor's packing slip against the original PO. |  | Admin Support | Procurement Officer | Human System |  | Clipboard, Pen | Inventory Management System | Approved PO, Packing Slip | Initial Receiving Log |  | Receiving Protocol | Verify physical box counts and part numbers before the delivery driver leaves the premises. | Signing for missing boxes and losing leverage to claim missing items.
7.4.2 | Material Receiving & QA | Perform incoming Quality Control (QC) on the raw materials using measuring tools (calipers, micrometers) to verify dimensions against the BOM. |  | QA/QC Officer | Fabrication Supervisor | Technical System |  | Measurement Tools, Material Certs | Quality Tracking System | Final CAD BOM, Initial Receiving Log | Incoming Inspection Report |  | Quality Assurance Guidelines | Mandate a dimensional and visual check for warping, rust, or incorrect thickness on structural steel. | Accepting sub-standard, out-of-tolerance steel that will ruin the welding jig's accuracy.
7.4.3 | Material Receiving & QA | If materials pass QC, formally log them into the digital inventory system and assign them to the specific project storage zone. |  | Procurement Officer | IT/Admin Support | Information System |  | Barcode Scanners / Keyboard | Inventory Management System | Incoming Inspection Report | Updated Inventory Ledger |  | Inventory Management Policy | Apply physical project tags/labels to the materials to prevent them from being used on other jobs. | Usable project materials being cannibalized by other workshop teams.
7.4.4 | Material Receiving & QA | Trigger a notification to the Fabrication Supervisor that all required materials are in stock, QA-approved, and ready for production. |  | Procurement Officer | Fabrication Supervisor | Management System |  | Workflow Trigger | Project Tracking Software | Updated Inventory Ledger | Fabrication Readiness Notice |  | Project Portfolio Governance System | Supervisor must acknowledge the notice to trigger the Fabrication timeline. | Fabrication team sitting idle while materials gather dust in the storage zone.
8 | Fabrication and Construction Process
8.1.1 | Fabrication Planning | Receive the "Fabrication Readiness Notice", Final BOM, and 2D Engineering Drawings from Procurement and Engineering. |  | Fabrication Supervisor | Project Manager | Information System |  | Internal Routing Tool | Project Tracking Software | Fabrication Readiness Notice, Final Drawings | N/A |  | Inter-departmental Handoff Policy | Ensure all 2D drawings have the correct "Released for Manufacturing" stamp and GD&T notes. | Fabricating from obsolete or unapproved drawing versions.
8.1.2 | Fabrication Planning | Review the 2D drawings and BOM to sequence the manufacturing operations (e.g., rough cut → machine → form → join → finish). |  | Fabrication Supervisor | Lead Engineer | Human System |  | Clipboard / Whiteboard | PDM / Document Control System | 2D Drawings, Final BOM | Job Process Sheet |  | Production Sequencing Policy | Verify that the sequence logically prevents impossible tool-access or assembly situations later in the build. | Assembling components out of order, blocking access for final fastening or machining.
8.1.3 | Fabrication Planning | Identify, reserve, and calibrate all required workshop machinery, CNC centers, fixtures, and hand tools needed for the job. |  | Fabrication Supervisor | QA/QC Officer | Active Environment |  | Workshop Machinery / Tooling | Tool Lifecycle Monitoring System | Job Process Sheet | Tooling & Setup Checklist |  | Workshop Resource Policy | QA/QC must verify that measuring tapes, calipers, and gauges are properly calibrated. | Dimensional errors caused by using uncalibrated or worn-out measuring tools.
8.2.1 | Pre-Fabrication Briefing | Conduct a mandatory "Toolbox Talk" to brief the shop floor team on the exact structural goals, GD&T tolerances, and specific process hazards. |  | Fabrication Supervisor | QA/QC Officer | Human System |  | Whiteboard, Printed Drawings | Meeting Repository | Job Process Sheet, 2D Drawings | Briefing Attendance Log |  | Occupational Health & Safety Policy | Require machine operators and fabricators to verbally confirm their understanding of the critical datum planes. | Floor workers misunderstanding the drawing symbols or safety risks.
8.2.2 | Pre-Fabrication Briefing | Issue the necessary Personal Protective Equipment (PPE) tailored to the specific fabrication processes (e.g., eye protection, respirators, hearing protection). |  | Fabrication Supervisor | Admin Support | Active Environment |  | PPE Inventory | Inventory Management System | Briefing Attendance Log | PPE Issuance Record |  | Risk & Safety Policy | Deny workshop floor access to any operator lacking complete, functional PPE. | Severe workplace injuries due to lack of appropriate process protection.
8.3.1 | Material Preparation | Perform initial shaping, cutting, or blanking of raw materials to the exact preliminary dimensions specified in the BOM/Cut List. |  | Shop Floor Team | Fabrication Supervisor | Technical System |  | Saws, Shears, CNC Routers | N/A | Final BOM, 2D Drawings | Prepped Material Batch |  | Material Handling Policy | Verify the dimensions of the first piece before processing the rest of the batch (First-Article Inspection). | Wasting expensive raw materials due to an incorrect initial machine setup or measurement.
8.3.2 | Material Preparation | Deburr, chamfer, and clean the edges/surfaces of all prepped materials to prepare them for safe handling and high-integrity joining or final machining. |  | Shop Floor Team | None | Technical System |  | Grinders, Tumblers, Solvents | N/A | Prepped Material Batch | Cleaned Material Batch |  | Manufacturing Standards | Visually inspect surfaces to ensure no burrs, oil, or scale remains that could interfere with alignment. | Poor joint integrity or machine tool damage caused by contaminated/burred base materials.
8.4.1 | Active Fabrication & Assembly | Load the prepped materials into the designated fixtures, jigs, or machine beds, aligning them strictly to the primary datum planes. |  | Shop Floor Team | QA/QC Officer | Technical System |  | Production Fixtures, Clamps | N/A | 2D Drawings, Cleaned Material | Fixtured Assembly / Setup |  | Assembly Modeling Protocol | Ensure all locating pins and clamps are fully seated before initiating the primary manufacturing process. | Manufacturing a skewed part because the material was not fully seated in the fixture.
8.4.2 | Active Fabrication & Assembly | Execute preliminary forming, temporary fastening, or rough machining passes to establish the baseline geometry. |  | Shop Floor Team | None | Technical System |  | Presses, Fasteners, Machine Tools | N/A | Fixtured Assembly / Setup | Semi-Finished Structure |  | Manufacturing Standards | QA/QC must perform a quick squareness and dimensional check before final, irreversible joining/machining begins. | Discovering a dimensional error after the entire assembly is permanently joined or finish-machined.
8.4.3 | Active Fabrication & Assembly | Execute the final manufacturing sequence (e.g., final joining, structural fastening, or finishing machine passes) utilizing methods to evenly distribute stress and prevent distortion. |  | Shop Floor Team | Fabrication Supervisor | Technical System |  | Automated/Manual Production Equipment | N/A | Semi-Finished Structure | Fully Assembled Structure |  | Process Distortion & Tolerance Control Policy | Strictly enforce the defined process sequence to mitigate mechanical or thermal distortion across the structure. | Severe structural distortion (warping) rendering the assembly unusable and out-of-tolerance.
8.5.1 | In-Process QC & Finishing | Perform visual, dimensional, and (if required) Non-Destructive Testing (NDT) on the structural joints and critical machined surfaces. |  | QA/QC Officer | Fabrication Supervisor | Technical System |  | Measurement Gauges, NDT Equipment | Quality Tracking System | Fully Assembled Structure | In-Process QC Log |  | In-Process Quality Control Policy | Flag any defective joint or out-of-tolerance surface for immediate rework before moving to the next stage. | Micro-fractures or weak connections failing under operational load.
8.5.2 | In-Process QC & Finishing | Execute final finishing operations (e.g., grinding flush, polishing, edge routing) to meet the aesthetic and functional surface requirements. |  | Shop Floor Team | None | Technical System |  | Finish Grinders, Polishers | N/A | In-Process QC Log | Finished Raw Structure |  | Surface Finish Standards | Ensure finishing operations do not reduce material thickness or alter dimensions below the safe minimum limits. | Weakening the structural integrity or altering critical tolerances by over-finishing.
8.6.1 | Surface Coating & Protection | Apply standard environmental protections (e.g., primer, paint, anodizing, or anti-rust oil) as dictated by the engineering specifications. |  | Shop Floor Team | Fabrication Supervisor | Technical System |  | Spray Equipment, Chemical Baths | N/A | Finished Raw Structure | Coated Final Product |  | Environmental Protection Standards | Ensure coatings are applied evenly and do not obstruct any threaded holes, sliding rails, or moving joints. | Premature degradation or coating interference with dynamic mechanical assemblies.
8.6.2 | Fabrication Handoff | Move the Coated Final Product to the designated testing staging area and update the project tracker to "Ready for Final QA Testing". |  | Fabrication Supervisor | Project Manager | Management System |  | Workflow Trigger | Project Tracking Software | Coated Final Product | Fabrication Completion Notice |  | Project Portfolio Governance System | Supervisor must digitally sign off that all fabrication steps on the Job Process Sheet were completed. | Handing over an unfinished, unchecked physical unit to the final testing phase.
9 | Quality Control and Testing Process
9.1.1 | Inspection Preparation | Receive the "Fabrication Completion Notice" and physically transfer the fabricated structure to the QA/QC staging area. |  | QA/QC Officer | Fabrication Supervisor | Active Environment |  | Pallet Jacks / Hoists | Project Tracking Software | Fabrication Completion Notice | N/A |  | Inter-departmental Handoff Policy | Ensure the structure is securely staged and safe to inspect before beginning work. | Handling damage occurring during transfer to the QA area.
9.1.2 | Inspection Preparation | Retrieve the locked Design Specification (Pr-Set), 2D Drawings, and the original Project Brief from the digital vault. |  | QA/QC Officer | Lead Engineer | Information System |  | Computer Display | PDM / Document Control System | Pr-Set, 2D Drawings | QA Testing Checklist |  | Documentation Standards | Verify that the retrieved drawings are the exact versions used by the fabrication team. | Inspecting a physical part against an outdated or incorrect digital drawing.
9.2.1 | Visual & Surface Inspection | Perform a comprehensive visual sweep of the structure, checking for sharp edges, burrs, spatter, and coating uniformity. |  | QA/QC Officer | None | Human System |  | Flashlights, Magnifying Glasses | N/A | QA Testing Checklist | Visual Inspection Log |  | Surface Finish Standards | Flag any exposed, uncoated raw steel that violates the environmental protection specs. | Premature corrosion or operator injury due to missed burrs/sharp edges.
9.2.2 | Dimensional & GD&T Inspection | Measure all critical datums, hole centers, and overall bounding dimensions against the defined GD&T tolerances (e.g., ±1.0mm). |  | QA/QC Officer | None | Technical System |  | Calipers, Micrometers, Height Gauges | Quality Tracking System | 2D Drawings | Dimensional Audit Report |  | Tolerance & Capability Policy | Ensure measuring tools are zeroed and calibrated before taking the first measurement. | Falsely passing an out-of-tolerance dimension due to an uncalibrated caliper.
9.3.1 | Functional & Load Setup | Prepare the structure for physical testing by securely anchoring it and gathering test operands (e.g., inserting sample pipes into the welding jig). |  | QA/QC Officer | Shop Floor Team | Technical System |  | Clamps, Anchors, Test Operands | N/A | QA Testing Checklist | N/A |  | Risk & Safety Policy | Ensure all anchors are tight before applying any dynamic or static loads. | Structure tipping or collapsing during the load test, causing severe injury.
9.3.2 | Functional & Load Execution | Actuate all moving parts, clamps, and mechanisms to verify smooth operation, clamping force, and structural deflection under load (e.g., ≤ 0.5 mm). |  | QA/QC Officer | Technical Expert | Technical System |  | Load Cells, Dial Indicators | Quality Tracking System | Pr-Set (Design Spec) | Load & Function Test Report |  | Design Validation Policy | Verify that the structure returns to absolute zero (no permanent deformation) after the load is removed. | Plastic deformation indicating a fundamental structural design or material failure.
9.4.1 | Non-Conformance Handling | If any dimension or test fails, immediately tag the physical structure with a red "DO NOT USE" marker and log the defect. |  | QA/QC Officer | None | Human System |  | Physical Tags / Labels | Quality Tracking System | Dimensional / Test Reports | Non-Conformance Report (NCR) |  | In-Process Quality Control Policy | The NCR must cite the specific drawing coordinate or Pr-Set line item that failed. | Ambiguous defect reporting leading to the wrong area being reworked.
9.4.2 | Non-Conformance Handling | Route the NCR back to the Fabrication Supervisor and Lead Engineer to determine if the part must be reworked, repaired, or scrapped. |  | Lead Engineer | Fabrication Supervisor | Management System |  | Workflow Trigger | Project Tracking Software | Non-Conformance Report (NCR) | Rework Action Order |  | Change Management Policy | Do not authorize a "repair" if the structural integrity has been fundamentally compromised. | Attempting to weld over a critical failure, hiding a fatal flaw from the client.
9.5.1 | Final Validation & Release | Once all tests pass (or rework is successfully re-tested), compile all inspection logs into the final validation package. |  | QA/QC Officer | Lead Engineer | Information System |  | Word Processor | Document Management System | All QA Logs and Reports | Final QA Release Certificate |  | Final Testing & Inspection Policy | The Lead Engineer must countersign the QA Certificate to accept ultimate technical liability. | Releasing a product solely on a technician's signature without engineering oversight.
9.5.2 | Final Validation & Release | Attach the physical QA Release Certificate to the structure and update the digital project status to "Ready for Delivery/Handover". |  | Admin Support | QA/QC Officer | Management System |  | Workflow Trigger | Project Tracking Software | Final QA Release Certificate | Delivery Authorization Notice |  | Project Portfolio Governance System | Ensure the Finance Team is copied on the notice to prepare the final invoice. | Product sitting in the staging area indefinitely because the delivery team was not notified.
10 | Engineering Documentation and Archiving Process
10.1.1 | As-Built Documentation Update | Receive the "Final QA Release Certificate" and interview the Fabrication Supervisor for any on-the-fly workshop modifications made during the build. |  | Design Engineer | Fabrication Supervisor | Human System |  | Clipboard / Voice Recorder | PDM / Document Control System | Final QA Release Certificate, NCRs | As-Built Modification Notes |  | Change Management Policy | Ensure every authorized rework or dimensional shift is captured from the QA reports. | "As-built" physical product not matching the final delivered digital CAD files.
10.1.2 | As-Built Documentation Update | Update the 3D CAD models, 2D Drawings, and BOM to reflect the exact "As-Built" physical reality of the approved structure. |  | Draftsman | Design Engineer | Technical System |  | 3D CAD Software / Drafting Tools | PDM Vault | As-Built Modification Notes | As-Built Engineering Drawings |  | Revision Control Policy | Increment the file revision number (e.g., Rev A to Rev B) to indicate the final As-Built status. | Overwriting original design intent data without a traceable version history.
10.2.1 | Technical Authoring | Draft the User Manual, detailing safe operational procedures, ergonomic handling limits, and visual cues for correct use. |  | Technical Support Provider | Lead Engineer | Information System |  | Word Processor / Publishing Tools | Document Management System | Pr-Set (Design Spec), As-Built Drawings | Draft User Manual |  | Documentation Standards | Ensure the manual addresses all Human System constraints defined in Pr5 (Safe handling, low skill requirement). | Client operators injuring themselves due to unclear usage instructions.
10.2.2 | Technical Authoring | Draft the Maintenance & Adjustment Guide, specifying lubrication points, replaceable wear element part numbers, and calibration steps. |  | Technical Support Provider | QA/QC Officer | Information System |  | Word Processor / CAD (for exploded views) | Document Management System | BOM, QA Testing Logs | Draft Maintenance Guide |  | Quality Assurance Guidelines | Include specific tolerance limits (e.g., maximum wear limits before part replacement is required). | Premature equipment failure due to lack of defined preventative maintenance.
10.3.1 | Final Package Assembly | Compile the As-Built Drawings, BOM, User Manual, Maintenance Guide, and QA Certificates into a single, cohesive Technical Data Package (TDP). |  | Admin Support | Technical Support Provider | Information System |  | PDF Compilation Software | Document Management System | All Draft Manuals, Drawings, Certificates | Final Client Technical Data Package (TDP) |  | Documentation Delivery Policy | Verify that the document title blocks, page numbers, and IMHOGEN branding are consistent across the package. | Delivering a disorganized, unprofessional stack of unlinked documents to the client.
10.3.2 | Final Package Assembly | Route the compiled Final TDP to the Project Manager and Lead Engineer for a final administrative and technical sign-off. |  | Admin Support | Project Manager | Management System |  | Internal Routing Tool | Document Management System | Final Client TDP | Approved Client TDP |  | Engineering Release Protocol | Both the PM and Lead Engineer must digitally sign the master cover page of the TDP. | Releasing unverified instructional documents containing technical errors.
10.4.1 | Digital Archiving & Vault Locking | Move all finalized native CAD files, FEA simulation data, and internal emails into the project's permanent "Closed/Archived" digital folder. |  | IT / Admin Support | Project Manager | Information System |  | Server Admin Consoles | Document Management System | All Project Files | Archived Project Folder |  | Data Retention Policy | Apply strict "Read-Only" permissions to the archived folder for all staff except IT Admins. | Accidental deletion or unauthorized alteration of closed project data.
10.4.2 | Digital Archiving & Vault Locking | Change the state of all associated CAD files within the PDM software to "Released / Locked" to prevent further parametric editing. |  | Lead Engineer | IT / Admin Support | Technical System |  | PDM Dashboard | PDM Vault | As-Built CAD Models | Locked CAD Vault Record |  | Information Security Policy | Verify that the PDM system registers the lock and severs check-out privileges for design staff. | Engineers accidentally opening and modifying archived CAD files for new projects.
10.5.1 | Knowledge Base Extraction | Conduct a brief project post-mortem to extract key technical lessons, reusable CAD sub-assemblies, and standard parts for the internal library. |  | R&D Coordinator | Lead Engineer | Human System |  | Meeting / Note-taking | Engineering Knowledge Repository | Archived Project Folder | R&D Lessons Learned Log |  | Research & Development Policy | Strip all confidential client IP from CAD assemblies before adding them to the general IMHOGEN parts library. | Violating client NDAs by reusing proprietary geometries in future public designs.
10.5.2 | Project Closure Handoff | Update the central tracking system status to "Documentation Complete" and trigger the Client Relations Team to initiate physical/digital handover. |  | Project Manager | Admin Support | Management System |  | Workflow Trigger | Project Tracking Software | Approved Client TDP | Delivery & Handover Notice |  | Project Portfolio Governance System | Confirm the Client Relations Team has acknowledged receipt of the Approved TDP. | The physical product is ready, but delivery stalls because the paperwork was never handed over.
11 | Product / Process Delivery Process
11.1.1 | Logistics & Dispatch Planning | Receive the "Delivery & Handover Notice" and coordinate a delivery date/time with the client's receiving department. |  | Client Relations Team | Admin Support | Information System |  | Email / Phone | CRM / Project Tracking Software | Delivery & Handover Notice | Dispatch Schedule |  | Client Engagement Policy | Confirm the client has the necessary lifting equipment (e.g., forklift/hoist) available on-site for unloading. | Delivery vehicle arriving at a site unequipped to unload the heavy physical structure.
11.1.2 | Logistics & Dispatch Planning | Secure an appropriate transport vehicle (e.g., standard pickup or flatbed) based on the structural dimensions and weight. |  | Admin Support | Project Manager | Management System |  | Transport Booking System | Logistics / ERP System | Approved Client TDP (Dimensions) | Transport Waybill |  | Distribution Properties Policy | Verify the vehicle payload capacity exceeds the final As-Built weight of the delivered equipment. | Transport vehicle failure or legal violations due to overloading.
11.2.1 | Packaging & Load Securing | Prepare the physical structure for transport by securing any movable clamps, applying protective wrap to precision datums, and loading it onto the transport vehicle. |  | Fabrication Supervisor | Shop Floor Team | Active Environment |  | Pallet Jacks, Ratchet Straps, Protective Wrap | N/A | Dispatch Schedule | N/A |  | Material Handling Policy | Ensure ratchet straps do not apply crushing force to delicate precision locating pins. | Irreversible dimensional damage or scratching of precision surfaces during transit.
11.2.2 | Packaging & Load Securing | Print physical copies of the Approved Client TDP (User Manual, Maintenance Guide, QA Certificates) and place them in a weatherproof document pouch attached to the shipment. |  | Admin Support | None | Human System |  | Printer, Weatherproof Pouches | Document Management System | Approved Client TDP | Physical Document Packet |  | Documentation Delivery Policy | Verify all pages are printed clearly and bound professionally before dispatch. | Client receiving damaged, unreadable, or missing operational manuals.
11.3.1 | On-Site Unloading & Setup | Arrive at the client site, supervise the safe unloading of the equipment, and move it to the designated operational footprint (e.g., workshop floor). |  | Project Manager | Logistics Team | Active Environment |  | Client Hoists / Forklifts | N/A | Transport Waybill | N/A |  | Liquidation Properties Policy | Ensure the equipment is placed on a stable, level surface as defined in the initial site requirements. | Equipment instability due to placement on an uneven or unprepared workshop floor.
11.3.2 | On-Site Unloading & Setup | Perform a post-transit visual inspection and basic leveling/alignment using standard hand tools to ensure the structure survived transport intact. |  | QA/QC Officer | Project Manager | Technical System |  | Levels, Squares, Basic Hand Tools | N/A | QA Testing Logs | Post-Transit Inspection Log |  | Quality Assurance Guidelines | Re-verify the primary datum plane squareness before handing it over to the client operators. | Handing over equipment that was subtly warped or knocked out of tolerance during the drive.
11.4.1 | Site Acceptance Walkthrough | Conduct a physical walkthrough with the client's operators, demonstrating how to load a workpiece, engage clamps, and safely operate the equipment. |  | Technical Support Provider | Lead Engineer | Human System |  | Physical Demonstration | N/A | Physical Document Packet (User Manual) | N/A |  | Client Training & Handover Policy | Force the client operators to physically perform the loading/clamping sequence themselves while you observe. | Operators nodding in agreement but failing to actually understand the safe handling procedures.
11.4.2 | Formal Handover & Sign-Off | Present the formal "Final Handover Certificate" to the client's authorized representative for signature, legally transferring ownership and liability. |  | Project Manager | Client Relations Team | Human System |  | Clipboard, Pen | N/A | Final Handover Certificate | Signed Handover Certificate |  | Document Execution Policy | Ensure the signatory is a legally authorized client representative, not just a junior workshop floor technician. | Disputed project closure because the wrong person signed the acceptance forms.
11.5.1 | Commercial Close-Out | Return the Signed Handover Certificate to the office, scan it, and upload it to the central database. |  | Admin Support | Project Manager | Information System |  | Scanner / Computer | Document Management System | Signed Handover Certificate | Digitized Handover Record |  | Data Retention Policy | Ensure the scan is high-resolution and the signatures are clearly legible. | Loss of the physical paper leaving the company with no proof of delivery.
11.5.2 | Commercial Close-Out | Trigger a "Project Delivered" notification to the Finance Team to immediately issue the final milestone invoice for the remaining contract balance. |  | Project Manager | Finance Team | Management System |  | Workflow Trigger | Project Tracking Software / ERP | Digitized Handover Record | Final Billing Authorization |  | Financial Control Policy | Finance must issue the final invoice within 24 hours of receiving the handover authorization. | Delayed revenue collection causing unnecessary cash flow strain at the end of the project.
12 | Training and Post-Delivery Support Process
12.1.1 | Training Preparation | Receive the "Digitized Handover Record" and contact the client to schedule formal operator training sessions. |  | Client Relations Team | Technical Support Provider | Information System |  | Scheduling Tool / Phone | CRM | Digitized Handover Record | Training Schedule |  | Client Engagement Policy | Ensure the scheduled training aligns with the shift patterns of the actual floor operators, not just management. | Training the wrong personnel, leaving actual machine operators uninstructed.
12.1.2 | Training Preparation | Extract the "Safe Handling and Operation" guidelines from the User Manual to structure a targeted, hands-on training module. |  | Technical Support Provider | Lead Engineer | Human System |  | Presentation / Demonstration Prep | Document Management System | Approved Client TDP (User Manual) | Operator Training Syllabus |  | Training & Development Policy | Verify the syllabus directly addresses all Human System constraints identified in the Pr5 Specification. | Omitting critical safety or ergonomic warnings during training preparation.
12.2.1 | Training Execution | Conduct on-site, hands-on training with the client's operators, demonstrating loading, clamping, safe operation, and basic maintenance. |  | Technical Support Provider | Project Manager | Human System |  | Physical Equipment Demonstration | N/A | Operator Training Syllabus | N/A |  | Occupational Health & Safety Policy | Force each operator to independently perform a full operational cycle while being observed. | Operators passively watching but failing to grasp the tactile operational requirements.
12.2.2 | Training Execution | Administer a brief verbal or practical competency check and have all trained operators sign the attendance log. |  | Technical Support Provider | Admin Support | Human System |  | Clipboard, Pen | N/A | Operator Training Syllabus | Training Completion Log |  | Client Training & Handover Policy | Only grant certification to operators who successfully complete the practical demonstration without critical errors. | Unqualified operators damaging the equipment or injuring themselves post-handover.
12.3.1 | Support Window Activation | Activate the formal 7 to 30-day "Post-Delivery Support" window in the tracking system, starting from the date of the signed Handover Certificate. |  | Admin Support | Client Relations Team | Information System |  | Keyboard/Mouse | Project Tracking Software / CRM | Digitized Handover Record | Active Support Ticket |  | Post-Delivery Support Policy | Set automated system alerts for the expiration date of the support window. | Providing indefinite free support due to a lack of formal boundary tracking.
12.3.2 | Support Ticketing & Resolution | Receive, log, and route any client feedback, minor adjustments, or operational questions that arise during the active support window. |  | Client Relations Team | Technical Support Provider | Information System |  | Digital Helpdesk / Ticketing | CRM | Active Support Ticket | Support Resolution Log |  | Feedback Handling Procedure | Categorize requests strictly: verify if the issue is a genuine defect vs. a request for a new (out-of-scope) feature. | Executing out-of-scope engineering changes under the guise of "post-delivery support".
12.4.1 | Operational Audit | Schedule and conduct a final operational audit near the end of the support window to verify the equipment is performing optimally under standard production loads. |  | QA/QC Officer | Technical Support Provider | Human System |  | Visual Inspection, Operator Interviews | Quality Tracking System | Original Pr-Set, Support Resolution Log | Final Operational Audit Report |  | Quality Assurance Guidelines | Cross-reference operator feedback against the original "Wishes and Fixed Requirements" to measure ultimate project success. | Assuming the equipment is functioning perfectly just because the client hasn't called to complain.
12.5.1 | Project & Support Closure | Formally close the active support ticket and notify the client that standard warranty/maintenance contract terms now apply. |  | Client Relations Team | Head of Business Operations | Information System |  | Email Templates | CRM | Final Operational Audit Report | Support Closure Notice |  | Corporate Governance Policy | Offer a long-term preventative maintenance contract to the client concurrently with the closure notice. | Losing an opportunity for recurring revenue via maintenance contracts.
12.5.2 | Final System Archival | Conduct a final sweep to ensure all logs (training, audit, support) are archived, and permanently lock the project ledger. |  | Admin Support | Project Manager | Management System |  | Server Admin Consoles | Project Portfolio Governance System | All remaining project documents | Completely Closed Project Record |  | Data Retention Policy | Verify the Finance Team confirms the final invoice has been fully paid and reconciled before locking the ledger. | Closing a project ledger when outstanding debt remains uncollected.