## D4.i Document Control Index
Prepared by |  |  | Tool title | Resource Document Control |  | Date filled |  | Quality Target | 4 | Related Tool
Role |  |  | Project Reg. ID | ALL ACTIVE |  | Time Started |  | Bus. Target | Qlty Delivery | Prev. Sheet Ref | D3
Checked by |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const | Cost and Risk | Next Sheet Ref | D4.1 | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Document Index |  | Duration |  | Iteration Num. | 0 | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4-Index |  | Date Checked |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [5 empty] | All Rights Reserved
1.0 CAPACITY PLANNING DOCUMENT CONTROL INDEX
DocID | Document Title |  |  |  | Link |  | Description
D4 | Master Capacity Tracker |  |  |  | ➡️ |  | The central Hub tracking all engineering utilization
D4.1 | Technical Requirement Notes |  |  |  | ➡️ |  | The translation of the D2.12 Contract into specific engineering skills
D4.2 | Resource Request Form |  |  |  | ➡️ |  | The formal request from the Project Manager to the Head of Engineering to reserve specific staff for specific dates.
D4.3 | Team Assignment & Provisioning Record |  |  |  | ➡️ |  | The official roster locking in which engineers are on the project and the hardware/software allocated to them.
D4.4 | Access Confirmation Log |  |  |  | ➡️ |  | The IT/Admin checklist ensuring engineers actually have access to the client folders, CAD servers, and project repos.
D4.5 | Internal Kick-off Deck (Link) |  |  |  | ➡️ |  | The standardized presentation template used to brief the assigned engineers on the project scope and constraints.
D4.6 | Kick-off Calendar Invite & Agenda |  |  |  | ➡️ |  | The structured meeting agenda to ensure the internal handover from Contract Admin to the Engineering team is flawless.
D4.7 | Kick-off Meeting Minutes |  |  |  | ➡️ |  | The live capture of engineer questions, immediate technical risks, and Day-1 task assignments.
T3.D4.8a | Drafting Assignment & Baseline |  |  |  | ➡️ |  | Drafting Assignment & Baseline (Fast-Track bypass for Tier 3 jobs).
D4.8 | Locked Project Baseline |  |  |  | ➡️ |  | The final operational lock. The schedule and budget are frozen here against which all future project performance is measured.

## D4.1 Technical Requirement Note
Prepared by |  |  | Tool title | Technical Requirement Notes |  | Date filled |  | Quality Target |  | 4 | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target |  | Qlty Delivery | Prev. Sheet Ref |  | D2.14
Checked by |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const |  | Cost and Risk | Next Sheet Ref |  | D4.2 | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Scope Breakdown |  | Duration |  | Iteration Num. |  | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4.1 |  | Date Checked |  |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.1 TECHNICAL REQUIREMENT NOTES (Scope Translation)
1.0 BREAKDOWN METADATA
Project Manager: | [10 empty] | Reference Contract: |  |  | [Insert Hyperlink to D2.12]
Date of Breakdown: | [10 empty] | Project / Client Name: |  |  | [Type Name]
Target Project Start Date: |  |  | [DD/MM/YYYY] | [7 empty] | [DD/MM/YYYY]
2.0 SKILL & LABOR REQUIREMENTS
SN | Engineering Module (From Pricing Matrix) |  |  |  | Required Role / Skill Level |  |  |  | Estimated Effort (Days) |  |  | Specific Constraints / Notes
2.1 | [e.g. Mechanical Design] |  |  |  | [e.g. Mid-Level CAD Engineer] |  |  |  | [e.g. 15 Days] |  |  | [e.g. Must be prolific in Autodesk Inventor]
2.2 | [e.g. Thermal System Design] |  |  |  | [e.g. Senior Thermal Engineer] |  |  |  | [e.g. 10 Days] |  |  | [e.g. Requires background in consumer appliance heating]
2.3 | [e.g. Prototype Fabrication] |  |  |  | [e.g. Junior Technician] |  |  |  | [e.g. 5 Days] |  |  | [e.g. 3D printing and basic soldering skills needed]
3.0 SOFTWARE & EQUIPMENT REQUIREMENTS
SN | Resource Category |  |  |  | Specific Tool / Machine Needed |  |  |  | Duration Required |  |  | Status (Available/Needs Procurement)
3.1 | Software License |  |  |  | [e.g. Autodesk Inventor 2025] |  |  |  | [e.g. 15 Days] |  |  | [Available]
3.2 | Specialized Equipment |  |  |  | [e.g. 3D Printer (High Temp Resin)] |  |  |  | [e.g. 3 Days] |  |  | [Available]
3.3 | Testing Apparatus |  |  |  | [e.g. Digital Anemometer / Thermal Camera] |  |  |  | [e.g. 2 Days] |  |  | [Needs Procurement]
4.0 ROUTING & APPROVAL
Is the technical breakdown complete and ready for Resource Request (D4.2)? | [6 empty] | [Yes/No]
Project Manager Signature: | [6 empty] | [Type here] |  |  | Date: | [DD/MM/YYYY]

## D4.2 Resource Request Form
Prepared by |  |  | Tool title | Resource Request Form |  | Date filled |  | Quality Target | 4 |  | Related Tool | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target | Qlty Delivery |  | Prev. Sheet Ref | D4.1
Checked by |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const | Cost and Risk |  | Next Sheet Ref | D4.3 | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Resource Allocation |  | Duration |  | Iteration Num. | 0 |  | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4.2 |  | Date Checked |  |  |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.2 RESOURCE REQUEST FORM (Internal Staffing)
1.0 REQUEST METADATA
Requesting PM: | [10 empty] | Date of Request: |  | [DD/MM/YYYY]
Project Name: | [10 empty] | Total Budgeted Labor (GHS): |  | [From D1.14 / Pricing Tool]
2.0 HUMAN RESOURCE REQUEST
SN | Role Required |  |  |  | Preferred Engineer (Optional) |  |  |  |  | Dates Needed (Start to End) |  |  | Total Days Requested
2.1 | [e.g. Senior Mechanical Eng.] |  |  |  | [e.g. Daniel Asanti] |  |  |  |  | [DD/MM to DD/MM] |  |  | [e.g. 15]
2.2 | [e.g. Junior Electronics Eng.] |  |  |  | [e.g. Any available] |  |  |  |  | [DD/MM to DD/MM] |  |  | [e.g. 10]
2.3 | [Type here] |  |  |  | [Type here] |  |  |  |  | [Type here] |  |  | [Type here]
3.0 CONFLICT & OVERLAP CHECK (To be filled by Head of Engineering)
SN | Requested Engineer |  |  |  | Current Utilization Status |  |  |  |  | Approved for this Project? (Yes/No) |  |  | Alternative Assignment
3.1 | [e.g. Daniel Asanti] |  |  |  | [e.g. 80% booked on SAYeTECH project] |  |  |  |  | [No] |  |  | [Assign Kelvin instead]
3.2 | [e.g. Junior Electronics Eng.] |  |  |  | [e.g. Fully available] |  |  |  |  | [Yes] |  |  | [Assign Michael]
4.0 APPROVAL & ROUTING
Are all requested roles filled and approved by Engineering Leadership? | [6 empty] | [Yes/No]
Head of Engineering / R&D Signature: | [6 empty] | [Type here] |  | Date: |  | [DD/MM/YYYY]

## D4.3 Team Assignment & Provisio
Prepared by |  |  | Tool title | Team Assignment & Provisioning |  | Date filled |  | Quality Target |  | 4 | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target |  | Qlty Delivery | Prev. Sheet Ref |  | D4.2
Checked by |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const |  | Cost and Risk | Next Sheet Ref |  | D4.4 | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Team Lock-in |  | Duration |  | Iteration Num. |  | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4.3 |  | Date Checked |  |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.3 TEAM ASSIGNMENT & PROVISIONING RECORD
1.0 ASSIGNMENT METADATA
Project Manager: | [10 empty] | Reference Request: |  |  | D4.2 Resource Request
Project Name: | [10 empty] | Assignment Date: |  |  | [DD/MM/YYYY]
2.0 OFFICIAL PROJECT ROSTER (Locked Team)
SN | Role / Discipline |  |  |  | Assigned Engineer |  |  |  | Allocated Days |  |  | Project Phase Involvement
2.1 | [e.g. Lead Mechanical] |  |  |  | [e.g. Daniel Asanti] |  |  |  | [e.g. 15] |  |  | [e.g. Phases 1 & 2]
2.2 | [e.g. Electronics/Firmware] |  |  |  | [e.g. Kelvin] |  |  |  | [e.g. 10] |  |  | [e.g. Phase 2 Only]
2.3 | [Type here] |  |  |  | [Type here] |  |  |  | [Type here] |  |  | [Type here]
3.0 HARDWARE & SOFTWARE PROVISIONING TICKET
SN | Assigned Engineer |  |  |  | Asset / License Required |  |  |  | Date Required |  |  | Provisioning Status (IT/Admin)
3.1 | [e.g. Daniel Asanti] |  |  |  | [e.g. Autodesk Inventor 2025 License] |  |  |  | [DD/MM/YYYY] |  |  | [Pending / Provisioned]
3.2 | [e.g. Kelvin] |  |  |  | [e.g. Oscilloscope / Multimeter] |  |  |  | [DD/MM/YYYY] |  |  | [Pending / Provisioned]
4.0 APPROVAL & ROUTING
Are all engineers officially locked in the Master Capacity Tracker (D4 Hub)? | [6 empty] | [Yes/No]
Head of Engineering Signature: | [6 empty] | [Type here] |  |  | Date: | [DD/MM/YYYY]

## D4.4 Access Confirmation Log
Prepared by |  |  |  | Tool title | Access Confirmation Log |  | Date filled |  | Quality Target | 4 | Related Tool | Doc Control
Role |  |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target | Qlty Delivery | Prev. Sheet Ref | D4.3
Checked by |  |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const | Cost and Risk | Next Sheet Ref | D4.5 |  | IMHO GEN
Org/Dept. |  | Administration |  | Activity Name | Digital Access |  | Duration |  | Iteration Num. | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  |  | Docu. ID | D4.4 |  | Date Checked |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  |  | Sheet Version | v1.0 |  | Date Approved | [6 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.4 ACCESS CONFIRMATION LOG (Digital Onboarding)
1.0 ONBOARDING METADATA
Executing Admin/IT: | [10 empty] | Project / Client Name: |  | [Type Name]
Date Executed: | [10 empty] | Total Team Size: |  | [e.g. 3 Engineers]
2.0 CLOUD & SERVER ACCESS CHECKLIST
SN | Digital Workspace |  |  |  |  | Required Action | [5 empty] | Verification Check |  |  | Status
2.1 | Google Drive Workspace |  |  |  |  | Create Client Root Folder & Add Team | [5 empty] | [Link provided?] |  |  | [Done]
2.2 | CAD Vault / Server |  |  |  |  | Create Project Repo & Grant Read/Write | [5 empty] | [Permissions verified?] |  |  | [Done]
2.3 | Communication Channel |  |  |  |  | Create WhatsApp/Slack Group & Add Team | [5 empty] | [PM made Admin?] |  |  | [Done]
2.4 | QMS Documentation Hub |  |  |  |  | Link this Spoke to the D4 Master Hub | [5 empty] | [Linked?] |  |  | [Done]
3.0 ENGINEER CONFIRMATION
Have all assigned engineers explicitly confirmed they can open the shared folders? | [7 empty] | [Yes/No]
Admin Signature: |  |  | [Type here] | [6 empty] | Date: | [DD/MM/YYYY]

## D4.5 Internal Kick-off Deck(Lin
Prepared by |  |  | Tool title | Internal Kick-off Deck |  | Date filled |  | Quality Target |  | 4 | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target |  | Qlty Delivery | Prev. Sheet Ref |  | D4.4
Checked by |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const |  | Cost and Risk | Next Sheet Ref |  | D4.6 |  | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Briefing Prep |  | Duration |  | Iteration Num. |  | 0 | Rev Reason |  |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4.5 |  | Date Checked |  |  |  |  | Change Dscrpt. |  |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [8 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.5 INTERNAL KICK-OFF DECK (Compliance Tracker)
1.0 DECK METADATA
Prepared By (Project Manager): | [10 empty] | Project / Client Name: |  |  | [Type Name]
Link to Presentation Deck: |  |  | [Insert Hyperlink Here]
2.0 MANDATORY SLIDE INCLUSION CHECKLIST
SN | Required Briefing Topic |  |  |  | Source Document Reference |  |  |  | Included in Deck? (Yes/No) |  |  | PM Notes
2.1 | Client Background & Ultimate Vision |  |  |  | [D1.8 Needs Assessment] |  |  |  | [Yes / No] |  |  | [Type here]
2.2 | Hard Scope Boundaries (What we are NOT doing) |  |  |  | [D1.13 Scope of Work] |  |  |  | [Yes / No] |  |  | [Type here]
2.3 | Strict Timeline & Handover Dates |  |  |  | [D2.12 Executed Contract] |  |  |  | [Yes / No] |  |  | [Type here]
2.4 | Financial/Budget Constraints for Prototyping |  |  |  | [D1.14 Cost Estimation] |  |  |  | [Yes / No] |  |  | [Type here]
2.5 | Known Technical & Operational Risks |  |  |  | [D1.11 Risk Matrix] |  |  |  | [Yes / No] |  |  | [Type here]
3.0 ROUTING
Is the deck complete and ready for the Internal Kick-off Meeting? | [6 empty] | [Yes/No]
Project Manager Signature: |  |  | [Type here] | [6 empty] | Date: | [DD/MM/YYYY]

## D4.6 Kick-off Calendar Invite a
Prepared by |  |  | Tool title | Kick-off Invite & Agenda | Date filled | Quality Target | 4 | Related Tool | Doc Control
Role |  |  | Project Reg. ID |  | Time Started | Bus. Target | Qlty Delivery | Prev. Sheet Ref | D4.5
Checked by |  |  | Phase Name | Capacity Planning | Time cmpltd | Bus. Const | Cost and Risk | Next Sheet Ref | D4.7 | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Meeting Setup | Duration | Iteration Num. | 0 | Rev Reason |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4.6 | Date Checked |  |  | Change Dscrpt. |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 | Date Approved |  |  |  |  | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.6 KICK-OFF CALENDAR INVITE & AGENDA
1.0 MEETING METADATA
Meeting Date: |  |  | [DD/MM/YYYY] |  |  | Time: |  | [00:00 AM/PM]
Location / Link: |  |  | [HQ / Google Meet] |  |  | Lead Facilitator: |  | [PM Name]
Required Attendees: |  |  | [All Engineers from D4.3 Roster]
2.0 STANDARD INVITE SCRIPT (Internal)
Team
We are officially kicking off engineering execution for [Project Name]. The contract is signed | the advance payment has cleared (D3.10) | and your time has been secured.
Please review the attached project documentation before the meeting. The agenda is as follows:
1. Review of Client Objectives & Scope (10 mins)
2. Timeline & Deliverable Breakdown (10 mins)
3. Technical Risk Assessment & Brainstorming (15 mins)
4. Day 1 Task Assignments (5 mins)
Attendance is mandatory to establish our project baseline.
3.0 SCHEDULING VERIFICATION
Calendar Invite sent to all rostered engineers? |  |  | [Yes/No]
Room/Platform booked? |  |  | [Yes/No]

## D4.7 Kick-off Meeting Minutes
Prepared by |  |  | Tool title | Kick-off Meeting Minutes |  | Date filled |  | Quality Target |  | 4 | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target |  | Qlty Delivery | Prev. Sheet Ref |  | D4.6
Checked by |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const |  | Cost and Risk | Next Sheet Ref |  | D4.8 |  | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Alignment |  | Duration |  | Iteration Num. |  | 0 | Rev Reason |  |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4.7 |  | Date Checked |  |  |  |  | Change Dscrpt. |  |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [8 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.7 KICK-OFF MEETING MINUTES (Live Capture)
1.0 MEETING EXECUTION METADATA
Actual Meeting Date: |  |  | [DD/MM/YYYY] |  |  |  |  | Start / End Time: |  |  | [00:00 to 00:00]
Lead Facilitator (PM): |  |  | [Type Name] |  |  |  |  | Note Taker: |  |  | [Type Name]
2.0 ATTENDANCE & VERIFICATION
SN | Required Attendee (From D4.3) |  |  |  | Role |  |  |  | Present? (Yes/No) |  |  | Notes (If absent)
2.1 | [e.g. Daniel Asanti] |  |  |  | [Lead Mechanical] |  |  |  | [Yes / No] |  |  | [Type here]
2.2 | [e.g. Kelvin] |  |  |  | [Electronics/Firmware] |  |  |  | [Yes / No] |  |  | [Type here]
3.0 TECHNICAL RESOLUTIONS & RISKS IDENTIFIED
SN | Topic Discussed |  |  |  | Engineer Raising Point |  |  |  | Decision / Resolution Agreed | [5 empty] | Action Required
3.1 | [e.g. Prototype Material] |  |  |  | [e.g. Daniel Asanti] |  |  |  | [e.g. Standard PLA will melt. Must use ABS.] | [5 empty] | [Update BOM]
3.2 | [e.g. Timeline Constraints] |  |  |  | [e.g. Kelvin] |  |  |  | [e.g. PCB fabrication takes 14 days minimum.] | [5 empty] | [Order PCBs on Day 1]
3.3 | [Type here] |  |  |  | [Type here] |  |  |  | [Type here] | [5 empty] | [Type here]
4.0 DAY 1 IMMEDIATE ACTION ITEMS (Unblocking the Team)
Task Description | [7 empty] | Assigned To | [5 empty] | Deadline
[e.g. PM to formally order ABS filament and PCBs] | [7 empty] | [PM Name] | [5 empty] | [DD/MM/YYYY]
[e.g. Lead Engineer to set up Master CAD Assembly file] | [7 empty] | [Daniel Asanti] | [5 empty] | [DD/MM/YYYY]
5.0 ROUTING
Are all team members fully clear on their Phase 1 objectives? | [6 empty] | [Yes/No]
Project Manager Signature: |  |  | [Type here] | [6 empty] | Date: | [DD/MM/YYYY]

## D4.8 Locked Project Baseline
Prepared by |  |  | Tool title | Locked Project Baseline |  | Date filled |  | Quality Target |  | 4 | Related Tool |  | Doc Control
Role |  |  | Project Reg. ID |  |  | Time Started |  | Bus. Target |  | Qlty Delivery | Prev. Sheet Ref |  | D4.7
Checked by |  |  | Phase Name | Capacity Planning |  | Time cmpltd |  | Bus. Const |  | Cost and Risk | Next Sheet Ref |  | Phase 5 | IMHO GEN
Org/Dept. |  | Engineering | Activity Name | Project Freeze |  | Duration |  | Iteration Num. |  | 0 | Rev Reason |  |  | IMHOGEN LTD
Signature |  |  | Docu. ID | D4.8 |  | Date Checked |  |  |  |  | Change Dscrpt. |  |  | Copyright IMHO GEN 2026.
|  |  | Sheet Version | v1.0 |  | Date Approved | [7 empty] | All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
D4.8 LOCKED PROJECT BASELINE (The Golden Record)
1.0 BASELINE METADATA
Locked By (Project Manager): | [10 empty] | Date Locked: |  | [DD/MM/YYYY]
Project / Client Name: | [10 empty] | Total Approved Budget (GHS): |  | [From D1.14]
2.0 SCHEDULE BASELINE (Frozen Milestones)
SN | Major Project Phase |  |  |  | Baseline Start Date |  |  |  | Baseline End Date |  |  | Allocated Working Days
2.1 | Phase 1: Conceptual Design & CAD |  |  |  | [DD/MM/YYYY] |  |  |  | [DD/MM/YYYY] |  |  | [e.g. 15 Days]
2.2 | Phase 2: Client Review & Iteration |  |  |  | [DD/MM/YYYY] |  |  |  | [DD/MM/YYYY] |  |  | [e.g. 5 Days]
2.3 | Phase 3: Prototype Fabrication |  |  |  | [DD/MM/YYYY] |  |  |  | [DD/MM/YYYY] |  |  | [e.g. 20 Days]
TOTAL PROJECT DURATION: | [11 empty] | [e.g. 40 Days]
3.0 RESOURCE BASELINE (Frozen Labor Hours)
SN | Assigned Engineer |  |  |  | Role |  |  |  | Total Baseline Hours/Days Allocated |  |  |  |  | Cost Impact Buffer
3.1 | [e.g. Daniel Asanti] |  |  |  | [Lead Mechanical] |  |  |  | [e.g. 15 Days] |  |  |  |  | [e.g. Max 2 days overtime]
3.2 | [e.g. Kelvin] |  |  |  | [Electronics/Firmware] |  |  |  | [e.g. 10 Days] |  |  |  |  | [e.g. None]
4.0 BASELINE LOCK AUTHORIZATION
Does this baseline perfectly match the timeline promised in the Contract (D2.12)? | [6 empty] | [Yes/No]
Head of Operations / Engineering Signature: |  |  |  | [Type here] |  |  |  | Date: | [DD/MM/YYYY]

## DT3.D4.8a Drafting Assignment &
Prepared by |  |  | Tool title |  | T3 Drafting Assignment & Baseline | Date filled | Quality Target |  | 4 | Related Tool | D4.i
Role |  |  | Project Reg. ID |  |  | Time Started | Bus. Target |  | Speed to Execution | Prev. Sheet Ref | D3.10a
Org/Dept. |  | Engineering | Activity Name |  | Direct Assignment | Duration | Iteration Num. |  | 0 | Rev Reason |  |  | IMHO GEN
Signature |  |  | Docu. ID |  | T3.D4.8a | Date Checked |  |  |  | Change Dscrpt. | Tier 3 Fast-Track |  | IMHOGEN LTD
Copyright IMHO GEN 2026.
All Rights Reserved
PROJECT REQUEST ID: [Enter ID]
T3.D4.8a (Drafting Assignment & Baseline)
1.0 ENGINEER ASSIGNMENT (Replaces D4.2 & D4.3)
The following engineer is directly assigned to this drafting request. No formal capacity review required if under 5 days.
SN | Assigned Engineer |  |  | Primary Skillset |  |  |  | Allocated Hours |  | Start Date |  |  | Target Delivery Date
1.1 | [e.g. Ocran] |  |  | [e.g. 3D Modeling/Surfacing] |  |  |  | [e.g. 16 Hrs] |  | [DD/MM] |  |  | [DD/MM]
2.0 DIGITAL ACCESS & ASSETS (Replaces D4.4)
SN | Resource Required |  |  |  |  | Status |  | Direct Link / Asset ID |  |  |  | Notes
2.1 | Client Source Data |  |  |  |  | [Ready/Missing] |  | [Link to D1.1 Uploads]
2.2 | Project CAD Folder |  |  |  |  | [Created] |  | [Link to Workspace]
2.3 | Software License |  |  |  |  | [Verified] |  | [e.g. Autodesk Inventor]
3.0 TECHNICAL BASELINE & STANDARDS (Replaces D4.1 & D4.8)
SN | Parameter |  |  |  |  | Requirement |  | Reference Standard |  |  |  | Notes
3.1 | Drafting Standard |  |  |  |  | [e.g. ISO 128] |  | [Must match T3.D1.3a]
3.2 | Tolerance Class |  |  |  |  | [e.g. ISO 2768-m] |  | [Linear & Angular]
3.3 | Deliverable Format |  |  |  |  | [e.g. PDF & STEP] |  | [As per T3.D2.2a]
4.0 KICK-OFF BYPASS ACKNOWLEDGMENT (Replaces D4.5,D4.6,D4.7)
By signing below, the Lead Engineer confirms they have reviewed the T3.D1.3a Technical Intake and require no further internal briefing.
5.0 FINAL AUTHORIZATION
Project Manager Signature | [6 empty] | Date |  |  | [DD/MM/YYYY]
Assigned Engineer Signature | [6 empty] | Date |  |  | [DD/MM/YYYY]